## Read me
TRK-NCR Non-conformance, site observation and field observation register
SOR and field observations answered in 3 working days or converted to an NCR; NCR closed only after the corrective action is verified by an approved inspection request.
How to use
1. Save a copy into the project folder as a container named CLIENT-BBM-PROJ-ZZ-XX-SH-Z-NNNN.xlsx (O-DEC-177). Never work in this library copy.
2. Fill Settings first: project code, client code, holidays. Contract turnaround days replace the office defaults.
3. Type only in white cells. Grey cells are formulas (record ID, due date, ageing, overdue, current revision): do not overwrite them.
4. A resubmission is a new row with the same Seq and the next Rev; never overwrite a returned row (O-DEC-175).
5. Close a row only with its evidence link (signed form, transmittal or authority decision in the CDE); never delete a row: set it Void with a reason (O-DEC-179).
6. For a report, set Settings Data date to the report date, print the Dashboard to PDF and file it with the period and population (O-DEC-180).
7. Rules: BBM-STD-99 Project trackers and registers; BBM-STD-13 Architect of Record services; BBM-STD-97 QP-07/09/10 (04-DOCUMENTS).
Office form for each record: NCR, Site Observation Report (SOR), Field Observation (02-SUPERVISION-FORMS).
Fields
Sheet | Field | Type | Rule
Register | Record ID | formula | Formula: PROJ-KIND-ROLE-NNNN (O-DEC-177). Do not type
Register | Kind | list NCRKIND | SOR site observation, FO field observation, NCR non-conformance
Register | ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2)
Register | Seq | num | Sequence per KIND and ROLE, from 1, never reused
Register | Issued | date
Register | Location | text
Register | Level | text
Register | Description | text
Register | Requirement type | list NCRREF | Document not conformed with (office NCR form)
Register | Requirement ref | text
Register | Originator | text
Register | Severity | list SEV
Register | Root cause | list ROOT
Register | Design origin | list YN | Y raises an office NC under QP-11
Register | Contractor reply | list AGREE
Register | Corrective action proposed | date
Register | Consultant decision | list DECISION3 | On the proposed corrective action
Register | Implemented | date | Contractor implementation date
Register | Verification IR | text | Approved IR closing it (TRK-IR)
Register | Closed | date | Close-out date
Register | Converted to NCR | text | For SOR/FO not answered in time: the NCR ID
Register | Due | formula | Formula: NCR = Issued + NCR days; SOR/FO = Issued + SOR working days
Register | Days open | formula | Formula: Closed (or the data date) minus Issued
Register | Overdue | formula | Formula: OVERDUE when no Closed and the data date is past Due
Register | Status | formula | Formula: Closed once the close-out date is entered
Register | Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179)
Register | Remarks | text | Free text; "held: <condition>" when the office refuses to sign

## Dashboard
TRK-NCR dashboard
Counts, ageing and KPIs from the register; every value is a formula (no data is typed here). "no data" = no population in the register.
Measure | Value | Rule
Records |  | Rows with an ID
Status: Open
Status: Closed
Overdue now |  | Open and past due at the data date
Average days (closed and open)
KPI (BBM-STD-98) | Actual | Target | Indicator
K-SV-04 |  | Baseline | Design-origin site NCRs (count; divide by 10,000 m2 GFA under construction for the KPI)
By discipline (ROLE) | Open | Closed
A
S
M
E
L
P
F
I
C
G
Q
W
Z

## Settings
Settings
Project codes, data date and turnaround days used by every formula. Contract values override the office defaults (O-DEC-176).
Setting | Value | Note | Public holidays (one date per cell)
Project code (PROJ token, BBM-STD-93 §2.2) |  | Required. Used in every record ID
Client code (CLIENT token)
Project title |  | Shown on the dashboard only
Data date (ageing computed to this date) |  | Overwrite with a fixed date for a reported snapshot (O-DEC-180)
Weekend code for working days (1 = Saturday + Sunday) | 1 | Excel WORKDAY.INTL weekend code
Submittal review, calendar days | 14 | O-DEC-176; contract value governs (FIDIC 2017: 21 days)
RFI answer, calendar days | 7 | O-DEC-176; KPI K-SV-03
Inspection request notice, working days | 1 | O-DEC-176
SOR / field observation response, working days | 3 | Office SOR form: then converted to NCR
NCR close-out, calendar days | 14 | Office NCR log practice
Site instruction acknowledgement, working days | 2 | O-DEC-176
Site visit report issue, working days | 2 | O-DEC-152; KPI K-SV-01
Transmittal acknowledgement, working days | 2 | QP-10
Minutes issue, working days | 2 | O-DEC-176
Review comment response, working days | 10 | O-DEC-176; KPI K-DR-02
Variation evaluation, calendar days | 14 | From a complete proposal
Authority decision when a row gives none, calendar days | 14 | Enter the authority service time per row where known
Warn before NOC or warranty expiry, days | 30
Contract sum (variation % of contract) |  | Currency of the contract

## Register
TRK-NCR Register
SOR and field observations answered in 3 working days or converted to an NCR; NCR closed only after the corrective action is verified by an approved inspection request.
Record ID | Kind | ROLE | Seq | Issued | Location | Level | Description | Requirement type | Requirement ref | Originator | Severity | Root cause | Design origin | Contractor reply | Corrective action proposed | Consultant decision | Implemented | Verification IR | Closed | Converted to NCR | Due | Days open | Overdue | Status | Evidence (CDE link) | Remarks
Formulas:
Due = IF([Issued]="","",IF([Kind]="NCR",[Issued]+TA_NCR,WORKDAY.INTL([Issued],TA_SOR,WEEKEND,HOL)))

## Lists
Lists
Validation lists (one source for every drop-down). Edit only through a BBM-STD-93 change.
ROLE | REVIEW | CLIENTDEC | SUBKIND | YN | YNT | PRIORITY | RFISTATUS | PARTY | NOCGROUP | GATE | JURIS | AUTHORITY | NOCSTATUS | RECSTATE | SUIT | CDE | STAGE | SISTATUS | IMPACT | NCRKIND | NCRREF | ROOT | SEV | AGREE | DECISION3 | VOKIND | VOSTATUS | MTYPE | ACTSTATUS | DCNORIGIN | DCNDEC | DELSTATUS | IRKIND | HOLDPT | HOCAT | FORMAT | HOSTATUS | CMTLEVEL | REVIEWER | DISPO | OPENCLOSED
A | A | No objection - proceed | MS | Y | Yes | High | Open | Client | 1 Project registration | Concept/planning | Dubai | DM Dubai Municipality | Unverified | Draft | SU-WIP | WIP | 0 | Issued | None | SOR | Specification | Workmanship | Major | Agree | Approved | VI | Draft | Progress | Open | Client | Pending | Not started | WIR | Hold | O&M manual | Hard copy | Not submitted | 0 | Client | Accepted | Open
S | B | Objection - resubmit | SD | N | No | Normal | Answered | PMC | 2 Studies | Permit/final design | Abu Dhabi | DDA | Planned | Active | SU-COORD | Shared | 1 | Acknowledged | Possible | FO | Design drawing | Material | Minor | Disagree | Approved as noted | VP | Under evaluation | Design | In progress | Authority | Approved | In progress | MIR | Witness | As-built drawings | Soft copy | Submitted | 1 | PMC | Not accepted | Closed
M | C | Not required | MT |  | TBC | Low | Closed | Design architect | 3 NOCs and affection plan | Construction activity | Sharjah | Trakhees | Submitted | Superseded | SU-INFO | Published | 2 | Executed | Yes | NCR | Shop drawing | Method |  |  | Not approved | VC | Recommended | Coordination | Closed | Consultant | Rejected | Shared |  | Surveillance | Warranty / guarantee | Both | Under review | 2 | Authority | Carried to next stage
E | D |  | SC |  |  |  | Void | Consultant | 4 Preparatory approvals | Completion/operation | Other emirate | Dubai Civil Defence | Conditionally approved | Closed | SU-REVIEW | Archive | 3 | Closed |  |  | Technical submittal | Design |  |  |  | VS | Approved | Authority | Carried | Contractor | Deferred | Submitted |  |  | Spare parts |  | Approved | 3 | Design architect
L | E |  | SP |  |  |  |  | Contractor | 5 Access approvals | None | Free zone | DEWA | Approved | Void | SU-ISSUE |  | 4 | Cancelled |  |  | Method statement | Supervision |  |  |  |  | Rejected | Client | Dropped | Value engineering |  | Accepted |  |  | Extra material |  | Rejected | 4 | Peer
P | UR |  | AB |  |  |  |  | Subcontractor | 6 Municipality submissions |  |  | RTA | Rejected |  |  |  | 5 |  |  |  | Other | Subcontractor |  |  |  |  | Withdrawn | Site |  | Coordination |  | Rejected |  |  | Keys and access cards |  |  |  | Internal L1
F |  |  | TS |  |  |  |  | Supplier | 7 Design approvals |  |  | DMT municipality (ADM/AAM/DRM) | Expired |  |  |  | 6 |  |  |  |  | Equipment | [5 empty] | Internal |  |  |  | On hold |  |  | Testing and commissioning |  |  |  | Internal L2
I |  |  | DS |  |  |  |  | Authority | 8 Construction |  |  | DMT planning (UPC) | Not applicable |  |  |  | 7 |  |  |  |  | Documentation | [12 empty] | Training record |  |  |  | Internal L3
C | [8 empty] | 9 Completion |  |  | DMT Estidama | [9 empty] | Other | [12 empty] | Authority completion certificate
G | [11 empty] | ITC Abu Dhabi | [22 empty] | Asset register / COBie
Q | [11 empty] | Abu Dhabi Civil Defence | [22 empty] | Decennial liability documents
W | [11 empty] | TAQA Distribution | [22 empty] | Snag list close-out
Z | [11 empty] | TAQA Water Solutions
Transco
EAD
AD Police
Etisalat (e&)
du
Awqaf
Gas network operator
Master developer / landlord
Free zone authority
Other