# Architect of Record and consultant-of-record services

BBM-STD-13-ARCHITECT_OF_RECORD_SERVICES-V0.1 | Office standard | 5 November 2026 | V0.1 | Private controlled WIP draft for office review

| Version | Date | Change |
| --- | --- | --- |
| V0.1 | 2026-11-05 | First issue: what the office does, signs and is liable for when it is the Architect of Record (AOR) or consultant of record in the UAE; service models, stage duties RIBA 0–7, the authority and NOC sequence, construction-stage administration, sign-off authority, liability, RACI and the links to BBM-STD-97 QP-07, QP-09, QP-10, BBM-STD-85 and the tracker set BBM-STD-99. Decisions O-DEC-170–O-DEC-183. |

# 1 Purpose ownership and boundaries

This standard fixes one office way of acting as Architect of Record. It applies to every appointment in which the office submits to a UAE authority under its own registration, signs or stamps design or supervision documents as the registered engineering consultancy, or administers a construction contract as the Engineer or supervision consultant. The practice director owns it and approves each AOR appointment at contract review (BBM-STD-97 QP-01). The consultant of record function of BBM-STD-55 §2 carries it out; actual holders and their registration cards live in the private Directory.

It does not repeat the authority detail of BBM-STD-85 and BBM-STD-57, the quality steps of QP-07, QP-09 and QP-10, or the tracker fields of BBM-STD-99. It states who does what, who signs, and what the office may refuse. The appointment and the construction contract always govern the office's actual powers: this standard never gives the office an authority the contract did not give. It is not legal advice; contract terms go through QP-01 contract review.

Basis in office practice. A read-only survey of the office servers and connected PC shares on 2026-11-05 (file names, sizes and dates, and the column structure of byte copies; no project data reused) showed how the office already works as AOR and supervision consultant: per-project authority tracking sheets that follow one stage sequence (§5); client and AOR comment trackers with a five-level comment classification (§4.2); design-and-supervision agreements, novations of the design consultant, supervision variations and extensions of time, and appointment orders for sub-consultants (§3); site submittal registers that relay each submittal through the client before it returns to the contractor (§6); and a full set of construction QA/QC logs and close-out registers (BBM-STD-99 §1). This standard writes that practice down as one rule set and adds what the primary sources below require.

# 2 Terms

| Term | Meaning in this office |
| --- | --- |
| Architect of Record (AOR) /​ consultant of record | The engineering consultancy registered with the permit authority of the emirate, for the discipline and building category, that submits and signs for the permit and/​or supervises the works and carries the statutory responsibility for them. In Dubai an "Engineering Firm" registered in the DM register and licensed under Dubai Law No. 14 of 2025; in Abu Dhabi an engineering consultancy office classified by DMT (TAMM) with registered engineers. One consultant of record per discipline per permit (O-DEC-171). |
| Design architect | The author of the concept or design intent. It may be unregistered in the emirate (for example a foreign studio); then it works through the AOR, and the AOR reviews and adopts its information before anything is signed (O-DEC-172). |
| Lead design consultant | The party coordinating all design disciplines under the appointment (BBM-STD-55). Often the AOR, not always. |
| Supervision consultant /​ Engineer | The consultant that supervises the works for the employer. Under the FIDIC 2017 Red Book it is "the Engineer" acting within Clause 3; under Abu Dhabi UPPC Circular No. 9 of 2026 it is jointly liable with the contractor within its scope. |
| Employer's representative /​ PMC | The client's project manager. It may relay or co-sign decisions; it never replaces the consultant's statutory signature. |
| Registered engineer | The individual engineer whose registration (Abu Dhabi engineer grades under DMT Administrative Decision 113/​2025; Dubai professional competency certificate under Law No. 14 of 2025) is shown on the drawings and submissions of the discipline. |

# 3 Service models

Every AOR appointment is one of these models (O-DEC-183). The model is recorded at contract review and in the BEP; it decides the stages, signatures and liability the office takes.

| Model | Office role | Typical scope | What changes |
| --- | --- | --- | --- |
| M1 Design and supervision | Lead design consultant, AOR and supervision consultant | RIBA 0–7 | Full scope of this standard; decennial liability as designer and supervisor (§8) |
| M2 AOR for a design architect | AOR, technical design, authority, supervision | Concept review, RIBA 3–7 | AOR review of every design-architect package before adoption (§4.2); the office signs only what it has reviewed and adopted |
| M3 Supervision only /​ replacement consultant | Supervision consultant | RIBA 5–6 | On replacement in Dubai a technical report on the works to date is endorsed (DM Administrative Resolution 275 of 2024); open design responsibility stays with its author |
| M4 Novated design consultant | Designer novated to a design-and-build contractor | RIBA 4–6 | The contractor becomes the client for services; duties to authorities and decennial liability as designer remain (§8) |
| M5 Design only | Designer and AOR for the permit | RIBA 0–4 | No supervision; Art. 822 limits decennial liability to design defects (§8) |

A change of model during the project (novation, added supervision, extension of time for supervision services, extra supervision staff) is a services variation logged in TRK-VO kind "Services variation" (BBM-STD-99) and approved in writing before the new work starts.

# 4 Duties per stage

## 4.1 Stage table

Stages follow the RIBA Plan of Work 2020 and the gate families of BBM-STD-93 §6. The column "Trackers" names the BBM-STD-99 workbooks that hold the record.

| RIBA stage | UAE stage /​ gate | AOR duties | Office records | Trackers |
| --- | --- | --- | --- | --- |
| 0 Strategic definition | Feasibility | Jurisdiction test J1–J6 (BBM-STD-85 §2); confirm the office registration and classification category cover the building height and use; service model (§3) | Go/​no-go, contract review (QP-01) | TRK-NOC (Unverified rows), TRK-DEL |
| 1 Preparation and briefing | Project registration, site data | Register the project on the authority portal; obtain site plan, affection plan, topographic and geotechnical scopes; open the authority sequence (§5) | Brief, BoD (BBM-STD-12) | TRK-NOC, TRK-MOM |
| 2 Concept design | Concept /​ planning approval (G1) | Concept submission and planning conformity; utility capacity enquiries; master-developer concept NOC where applicable; review of the design-architect concept (M2) | Concept report, comment responses | TRK-NOC, TRK-CMT, TRK-DCN |
| 3 Spatial coordination | Preparatory approvals and NOCs | Civil Defence, power and water demand, telecom, sewerage, access and traffic NOCs; coordinated design freeze | NOC decisions with conditions | TRK-NOC, TRK-CMT, TRK-DCN |
| 4 Technical design | Building permit /​ final design (G2) | Permit packages per discipline signed by registered engineers; authority comments answered; IFC issue; tender documents | Permit drawings, specification, IFC transmittal | TRK-NOC, TRK-DWG, TRK-CMT, TRK-DEL |
| 5 Manufacturing and construction | Construction activity (G3) | Supervision under QP-09: submittals, RFIs, site instructions, inspections, NCRs, variations, progress meetings; phase notices and joint phase reports in Abu Dhabi; authority inspections | Site visit reports, decisions, certificates | TRK-SUB, TRK-RFI, TRK-SI, TRK-IR, TRK-NCR, TRK-VO, TRK-MOM, TRK-DWG |
| 6 Handover | Completion /​ occupancy (G4) | Snagging, testing and commissioning results, authority completion inspections, consultant approval of the completion certificate, taking-over certificate, as-built drawings and O&M review | Completion approval, taking-over certificate | TRK-HO, TRK-NOC, TRK-NCR |
| 7 Use | Defects liability, use /​ renewal (G5) | Defects inspections, final handing-over certificate, decennial records kept (§8) | Final certificate, closeout | TRK-HO |

## 4.2 AOR review of other parties' design

When the office is AOR for information it did not author (model M2, sub-consultants, contractor design portions), it reviews before it adopts, and records the review in TRK-CMT. Each comment carries the five-level classification the office's clients already use (O-DEC-173):

| Level | Meaning | Effect |
| --- | --- | --- |
| 0 Rejected | Non-compliant with the brief, code or scope; immediate action | Package not adopted; no signature |
| 1 Significant | Response and corrective action required, or an agreed mitigation plan and date | Package not adopted until resolved |
| 2 Minor | Response required; may be closed at the next stage | Package may proceed; a Level 2 not answered at the next review becomes Level 1 |
| 3 Closed | Satisfactory response received | Closed |
| 4 Note | Editorial; no response needed | Information |

The AOR stamps a drawing, report or model only when its review is recorded, no Level 0 or Level 1 comment is open on that container, and the registered engineer of the discipline has checked it (O-DEC-172).

# 5 Authority interface and NOCs

The AOR is the office's single interface to the authorities for the appointment. The authority liaison prepares, the consultant of record signs, the portal submitter uploads and the LAP authorises (QP-07). The sequence below is the one the office's authority tracking sheets already follow; every line is a row in TRK-NOC, which is the BBM-STD-57 §4 submission register in working form (O-DEC-178). Requirements, checklists and portals are in BBM-STD-85; this table only orders them.

| Step | Group | Abu Dhabi (typical) | Dubai (typical) |
| --- | --- | --- | --- |
| 1 | Project registration | MePS /​ Binaa project registration and authorisation letter | DM building permit system registration (or DDA, Trakhees or the other competent entity) |
| 2 | Studies | Topographic survey, geotechnical investigation (work permit), spatial data, existing services | Topographic survey, soil investigation, existing services |
| 3 | NOCs and clear affection plan | Authorities' NOC round; clear affection plan | Affection plan; master-developer NOC |
| 4 | Preparatory approvals | TAQA Distribution power (LDN) and water (WDN) demand; Civil Defence; Etisalat /​ du; sewerage (TAQA Water Solutions); Transco where applicable | DEWA load confirmation and water; Dubai Civil Defence; du /​ Etisalat; coastal or environment NOCs where applicable |
| 5 | Access approvals | ITC access and traffic (IDAS, road safety audit, TPD), access eNOCs, master-developer access NOC | RTA access and traffic NOC |
| 6 | Municipality submissions | Concept design approval, phase /​ foundation permit, architectural and structural packages, building permit, fence permit | Final design approval, building permit, enabling or shoring permit |
| 7 | Design approvals by system | Architectural, structural, HVAC, plumbing and drainage, storm water, electrical, water supply; Estidama design rating | Discipline approvals; Al Sa'fat compliance; Dubai BIM permit where triggered |
| 8 | Construction | Phase notices and joint certified technical reports through the Unified Permitting System (Circular No. 9 of 2026); authority inspections | DM inspections; authority site inspections |
| 9 | Completion | Completion inspections, Civil Defence, utilities connection and final approvals; Estidama construction rating | Completion certificate under DM Administrative Resolution 275 of 2024; DEWA and Civil Defence completion |

Rules:

•  Every NOC row records the authority, service, application or receipt number, decision, conditions and expiry. "Approved" without the authority's decision document is not approved. A conditional approval releases the activity only when its conditions are closed. A rejected submission is resubmitted as a new row linked to the old one (BBM-STD-93 §7).

•  An NOC that expires before the dependent activity is a hold. TRK-NOC flags expiry within 30 days.

•  The AOR never uploads a package that has not passed QP-03/04 review, the BIM checklist "Authority submission" sheet where BIM applies, and LAP authorisation.

•  Utility, master-developer and landlord NOCs are applications by the AOR on the client's behalf; fees and owner undertakings are the client's and are recorded as client actions in TRK-NOC.

# 6 Construction-stage administration

The supervision duties are QP-09. This section fixes the AOR's limits and the record for each instrument. Times are the BBM-STD-99 defaults (O-DEC-176) unless the construction contract states others; the project values sit in each tracker's Settings sheet.

| Instrument | Office form (01-TEMPLATES\04-DOCUMENT-CONTROL) | AOR action and limit | Default time | Tracker |
| --- | --- | --- | --- | --- |
| Material, shop drawing, method statement, subcontractor and programme submittals | Material Submittal 04 01, Shop Drawing Submittal 04 03, SubContractor Submittal 04 05, Time Schedule Approval 04 08 | Review against the contract documents; code A Approved, B Approved as noted, C Revise and resubmit, D Rejected, E Information/​records (O-DEC-174); the client's "No objection /​ Objection" is recorded separately where the appointment requires it. Approval never relieves the contractor of its obligations | 14 calendar days from complete receipt; FIDIC 2017 sets the Engineer's review at 21 days; the contract value governs | TRK-SUB |
| Request for information | Request For Information; RFI form | Answer within the agreed time with the revised drawing or sketch; state whether the answer is a variation ("This clarification will constitute a variation: Yes /​ No") | 7 calendar days | TRK-RFI |
| Site instruction | Site Instruction (office form built 2026-11-05) | Written only; only within the authority the contract gives the consultant; client approval first where cost or time changes. Under FIDIC 2017 Sub-Clause 3.5 the contractor notifies an instruction it considers a variation before starting the work | Acknowledgement in 2 working days | TRK-SI |
| Inspection request (work and material) | Inspection Request; Material Inspection Request | Inspect hold and witness points before concealment; result coded A–E | By the requested inspection time, with at least 1 working day notice | TRK-IR |
| Site observation, field observation, NCR | SOR, Field Observation, NCR | The contractor answers an SOR within 3 working days, otherwise it becomes an NCR (office SOR form); an NCR is closed only after the corrective action is verified by an approved inspection request | NCR close-out 14 days | TRK-NCR |
| Variation | VO Template | Evaluate and recommend; the employer approves. FIDIC 2017 Sub-Clause 13.3: variation by instruction or by request for proposal | Evaluation in 14 days from a complete proposal | TRK-VO |
| Meetings | Minutes of Meeting (office form built 2026-11-05); Contractor's Monthly Report format | Chair or attend; minutes with numbered actions | Minutes issued in 2 working days | TRK-MOM |
| Drawings and transmittals | Project Transmittal; Transmittal Form | Issue only checked, authorised containers; every issue has a transmittal | Acknowledgement in 2 working days | TRK-DWG |
| Completion and taking over | Initial and Final Handing Over Certificates, Taking Over Certificate, snagging list | Approve completion only when the works conform and no NCR affecting conformity is open; FIDIC 2017 Sub-Clause 10.1 taking over | Per contract | TRK-HO |

In Abu Dhabi the supervision consultant also receives the contractor's notice before each major construction phase and submits the joint certified technical report at the end of each phase through the Unified Permitting System (UPPC Circular No. 9 of 2026); each phase report is a TRK-NOC row of step 8.

# 7 Sign-off authority

| Document | Prepared by | Checked by | Signed /​ stamped by | Condition |
| --- | --- | --- | --- | --- |
| Authority submission (NOC, permit package) | Authority liaison and discipline team | Discipline lead (L1), QP-03/​04 review | Consultant of record (registered engineer of the discipline) | LAP authorisation recorded; portal account valid |
| Permit and IFC drawings | Discipline team | Discipline lead; AOR review of others' information (§4.2) | Registered engineer of the discipline; office stamp | No open Level 0/​1 comment; BIM checklist issue sign-off |
| Submittal, RFI, inspection, NCR response | Discipline reviewer | Supervising engineer | Supervising /​ resident engineer | Within the contract authority |
| Site instruction | Supervising engineer | Project director where cost or time is affected | Supervising engineer; client approval where required | Written; logged before issue |
| Variation recommendation | Supervising engineer with cost input | Project director | Project director | Employer approval recorded before execution |
| Phase report (Abu Dhabi) | Contractor with the supervising engineer | Supervising engineer | Supervision consultant and contractor jointly | Inspection results attached |
| Completion approval, taking-over certificate | Supervising engineer | Project director | Consultant of record /​ project director | No open conformity NCR; authority inspections passed |
| Services variation, novation | Project manager | Practice director | Practice director | Written before the new scope starts |

The office refuses to sign or stamp when the condition is not met. The refusal is one line in the tracker row ("held: <condition>"), not a dispute (O-DEC-172).

# 8 Liability notes

•  Decennial liability. For contracts concluded from 1 June 2026, Federal Decree-Law No. 25 of 2025 (Civil Transactions Law) Art. 821 makes the engineer who designed and supervised and the contractor jointly liable for ten years, from the employer taking delivery, for total or partial collapse and for defects threatening the structural integrity and safety of the building, even when the defect is in the land. Art. 822 limits a design-only engineer to design defects; clauses excluding or reducing this liability are void (Art. 823); claims are brought within three years of the collapse or discovery (Art. 824). Contracts concluded before 1 June 2026 stay under Federal Law No. 5 of 1985 Arts. 880–883 (O-DEC-181).

•  Abu Dhabi. Circular No. 9 of 2026 makes the supervision consultant and the contractor jointly liable for non-compliance, defects or non-conforming works within their legislative scopes.

•  Dubai. An engineering office keeps the originals of its consultancy contracts and all records, drawings and digital copies for at least ten years from the completion certificate or the end of the contract, and does not reuse a design made for one client for another without that client's prior written consent (Dubai Law No. 14 of 2025, obligations of engineering offices). The office keeps project records for at least 13 years after handover (BBM-STD-90, O-DEC-138), which covers both.

•  Insurance. Professional indemnity cover is confirmed at contract review for every AOR appointment and kept for at least the decennial period of each project.

•  Scope of signature. The office signs for the disciplines and building category of its registration only. In Dubai the local firm categories are First (unlimited floors), Second (G+12) and Third (G+4) under DM Administrative Resolution 255 of 2021; a building above the office's category needs a consultant of record of a higher category.

# 9 RACI

R performs, A is the single accountable party, C is consulted, I is informed (one A per row, BBM-STD-55 §3). Model M2 (AOR for a design architect) is shown; in M1 the design architect column falls to the office.

| Activity | Client | Design architect | AOR (office) | Contractor | Authorities | PMC |
| --- | --- | --- | --- | --- | --- | --- |
| Brief, budget and programme | A | C | C | – | – | R |
| Concept design | A | R | C | – | I | C |
| Concept and planning approval | I | C | A/​R | – | C | I |
| NOCs and permit packages | I | C | A/​R | – | C | I |
| Technical design and IFC | I | C | A/​R | – | – | C |
| AOR review of design-architect packages | I | R | A | – | – | I |
| Tender documents | I | C | A/​R | – | – | C |
| Shop drawings and material submittals | I | C | A | R | – | I |
| RFIs during construction | I | C | A | R | – | I |
| Site instructions | C | – | A/​R | I | – | C |
| Inspections and NCRs | I | – | A/​R | R | C | I |
| Variations | A | C | R | R | – | C |
| Phase reports and authority inspections | I | – | A/​R | R | C | I |
| Completion approval and taking over | A | – | R | R | C | C |
| As-built and O&M review | I | – | A | R | – | I |
| Records retention (decennial) | I | I | A/​R | R | – | – |

# 10 Records, trackers and links

Each instrument above has one office form (the record) and one tracker row (the index): the form is filed in the CDE with its evidence and the tracker row links to it (BBM-STD-99 §6). Links: QP-07 authority submissions, QP-09 site supervision and QP-10 document control (BBM-STD-97); authority detail BBM-STD-85; submission register BBM-STD-57; approvals and criteria BBM-STD-12; KPIs K-AU-01/02 and K-SV-01 to 04 (BBM-STD-98); handover BBM-STD-75; retention BBM-STD-90.

# 11 Acceptance

| Check | Evidence |
| --- | --- |
| Model recorded | Contract review and BEP name the service model M1–M5 |
| Registration valid | The Directory holds the firm registration, classification category and each signing engineer's card, valid on the submission date |
| Review before stamp | Every stamped container has a TRK-CMT record with no open Level 0/​1 comment |
| One authority record | Every authority submission is one TRK-NOC row with receipt number, decision and conditions |
| Written administration | Every instruction, variation and completion approval is a signed form with a tracker row |

# References

All checked 2026-11-05.

•  Federal Decree-Law No. 25 of 2025 promulgating the Civil Transactions Law, Art. 821 (issued 1 Oct 2025, Official Gazette 809, in force 1 June 2026): https://uaelegislation.gov.ae/en/legislations/4011?keyword=Article%20(821)

•  Mayer Brown, Examining the New UAE Civil Code, Part 2: Muqawala Contracts (Arts. 821–824; old Arts. 880–883), 3 June 2026: https://www.mayerbrown.com/en/insights/publications/2026/06/examining-the-new-uae-civil-code-part-2-muqawala-contracts

•  Dubai Law No. 14 of 2025 Regulating the Practice of Engineering Consultancy Activities (issued 18 Sep 2025, Official Gazette 741; repeals Local Order 89 of 1994): https://slc.dubai.gov.ae/en/legislation-portal/detail?id=0900000a80471caa

•  Government of Dubai Media Office, Law No. 14 of 2025, 5 Oct 2025: https://www.mediaoffice.ae/en/news/2025/october/05-10/mohammed-bin-rashid

•  DM Administrative Resolution No. 275 of 2024, replacing engineering firms and contractors and issuing completion certificates (Art. 16 repeals Resolution 10 of 2019): https://dlp.dubai.gov.ae/Legislation%20Reference/2024/Administrative%20Resolution%20No.%20(275)%20of%202024%20Replacing%20Engineering%20Firms%20and%20Contracting%20Companies.html

•  DM Administrative Resolution No. 255 of 2021 amending Resolution 51 of 1998 (classification categories): https://dlp.dubai.gov.ae/Legislation%20Reference/2021/Administrative%20Resolution%20No.%20%28255%29%20of%202021%20Amending%20Administrative%20Resolution%20No.%20%2851%29%20of%201998.html

•  Local Order No. 3 of 1999 Regulating Construction Works in Dubai: https://dlp.dubai.gov.ae/Legislation%20Reference/1999/Local%20Order%20No.%20(3)%20of%201999%20Regulating%20Construction%20Works.pdf

•  Dubai Law No. 3 of 2026 Concerning the Quality and Safety of Buildings: https://dlp.dubai.gov.ae/Legislation%20Reference/2026/Law%20No.%20%283%29%20of%202026%20Concerning%20the%20Quality%20and%20Safety%20of%20Buildings.html

•  Project, UPPC Circular No. 9 of 2026 on supervision consultant and contractor roles, 14 Oct 2026: https://www.Project.ae/en/article/c2qm3pn-uppc-issues-circular-streamline-construction

•  DMT classification requirements and classified firms: https://pages.dmt.gov.ae/en/Classification-Category and https://pages.dmt.gov.ae/en/engineering-firms; DMT and ADGM unified classification and Administrative Decision 113/2025 engineer grades, 25 Mar 2026: https://www.dmt.gov.ae/en/Media-Centre/News/DMT-ADGM-Launch-Unified-Engineering-Classification-System-for-Abu-Dhabi

•  FIDIC 2017 Rainbow Suite (Sub-Clauses 3.5, 3.7, 5.2, 10.1, 13.3): https://fidic.org/sites/default/files/press%20release_rainbow%20suite_2018_03_1.pdf; Fenwick Elliott, The role of the Engineer in FIDIC 2017 contracts (21-day review, written instructions): https://www.fenwickelliott.com/sites/default/files/the_role_of_the_engineer_in_fidic_contracts_-_fenwick_elliott.pdf

•  FIDIC Client/Consultant Model Services Agreement, 5th edition 2017 (White Book): https://fidic.org/books/clientconsultant-model-services-agreement-5th-ed-2017-white-book

•  AIA contract administration forms G710–2017 Architect's Supplemental Instructions, G714–2017 Construction Change Directive, G716–2004 Request for Information (prior art): https://learn.aiacontracts.com/contract-doc-pages/27516-contract-administration-and-project-management-forms

•  RIBA Plan of Work 2020: https://www.riba.org/work/insights-and-resources/riba-plan-of-work

•  Office: BBM-STD-12, 55, 57, 85, 90, 93, 96, 97, 98, 99; office supervision forms in BABOOM-BIM-STANDARD\01-TEMPLATES\04-DOCUMENT-CONTROL.