## README
Purpose
Template | BBM-STD-50-CLASH_MATRIX-V0.2 / V0.2
Purpose | Use this register to plan, run and evidence model coordination across the office delivery team and its supply chain. It covers physical intersections, installation clearances, operational access and model duplicates. A model test supports competent design review; it does not establish structural adequacy, accessibility, fire compliance or construction approval by itself.
How to fill
1. Start a project copy | Delete every orange synthetic row labelled EXAMPLE - delete. Retain office reference tables; default changes need an approved project mapping.
2. Populate registers | Fill linked operational tables. Keys are text; one delivery row represents a container at one ExchangeID. Supply actual appointment, source revisions, approvals, tests and acceptance records.
3. Use dropdowns | Dropdowns cover input rows 5:504. Suitability, issue severity, CDE state and progress have distinct meanings. Blank fields are permitted during drafting; verify required fields before approval.
4. Dates and capacity | Use real Excel dates (yyyy-mm-dd), numeric millimetres and working-day durations. Confirm calendar, holidays, timezone, reviewer capacity and independence. Package review allowances are not repeated per container.
5. Preserve records | Keep immutable approved baseline, current forecast and actual evidence separate. Apply the same authorised ChangeID to all affected TIDP/MIDP commitments. Never overwrite rejection or retest evidence.
6. Extend input rows | Copy formatting and validation beyond row 504; extend filters and print area to populated rows. Default print area includes examples and 20 reserved input rows only.
7. Validate before use | Check unique keys, foreign keys, required fields, exact revisions, links, capacity, dates, rule coverage and mandatory acceptance gates. Dropdowns do not qualify tools or establish relational/design acceptance.
Revision box
Document ID | BBM-STD-50-CLASH_MATRIX
Template revision | V0.2
Template date | 2026-10-14
Project / appointment
Plan / register ID
Project revision (Rnn)
Immutable baseline ID
Prepared by / date
Checked by / date
Verified by / date
Approved by / date / evidence
ChangeID / summary
Next review / distribution
Source and schema notes
Decided specification | office-rev/Project/BBM-STD-50-CLASH_MATRIX-V0.2.md
Decision source | office-rev/Project/BBM-STD-11-DECISIONS-LOG-V0.1.md; BIM Manager, 2026-10-14.
Source revision discrepancy | The V0.2 specification files retain V0.1 body/control labels. Reference content remains as supplied; this workbook is V0.2. Template revision is separate from project Rnn and historic approvals.
Column interpretation | Reference-table headers/order are exact Markdown text. The operational field specification uses compressed prose, not enumerated Excel columns. Keys precede fields; comma/slash groups expand left-to-right into separate typed inputs using source labels. Field specification retains the original grouping; the schema manifest records the expansion. Progress status is the separate controlled status prescribed after the TIDP field table; stage evidence/dates remain distinct.
Legacy reference | Important Information; Trades; Master Clash Matrix; Master Clash Test; Clash Matrix; structure read only from office-source/Project/BBM-STD-50-CLASH_MATRIX.md. No server or source xlsx opened; no client branding or historic entries copied.
Examples | Orange rows, row-2 banners and visible row markers identify EXAMPLE - delete. Operational descriptions also carry the marker where available. Synthetic keys preserve joins; no executed test or genuine approval is asserted.
Boolean representation | Yes / No dropdowns represent enabled / disabled and mandatory / optional in registers.
Code-list protection | README code lists are locked with ordinary worksheet protection; revision-box inputs and project selectors are unlocked. Unprotect only to apply an authorised mapping. No password/security claim is made.
Tolerance authority | Tolerances in BBM-STD-50-CLASH_MATRIX-V0.2.xlsx is the single section 3 baseline. C/A need actual source/envelope; H has 0 mm deliberate penetration allowance; D exact duplicate investigation; V approved evidence method. 150/600 mm are fictitious examples, never office defaults.
Activation | Real appointments, approved requirements/source sets, competent designer/tool evidence, independent checks/retests and release/recipient decisions must be populated before operational approval.
Applicable decisions
O-DEC-001 | Retire all blanket RIBA-stage tolerances, including the conflicting Stage 5 15 mm and 5 mm settings; apply the single test-type table in section 3 at every stage. Basis: Purpose, pair, zone and clearance evidence determine the test; stage and LOD do not determine an allowable intersection. Source: [S07](RESEARCH.md#s07)
O-DEC-002 | Use CLIENT-ORG-PROJ-VOLUME-LEVEL-TYPE-ROLE-NUMBER.ext when an appointment supplies no grammar; retain internal Rnn revisions and the suitability list below. Basis: Adopts the Manual/BEP external candidate and existing Rnn convention consistently; appointment requirements take precedence through one recorded mapping. Source: [G-C](RESEARCH.md#g-c)
O-DEC-003 | Require 100% valid applicable mandatory geometry, data and documentation and zero unresolved required hard-intersection or mandatory access/safety failures in the issued scope. Basis: An issue count or optional-data percentage cannot average away a mandatory exchange failure. Source: [S04](RESEARCH.md#s04)
O-DEC-004 | Run weekly, every coordination comment round, on affected source/rule changes and before exchange; use Manual severity S1 Critical, S2 Major, S3 Minor. Basis: Retains the office issue-management service levels and adds revision-specific evidence and independent retest. Source: [S04](RESEARCH.md#s04)
O-DEC-005 | Reserve L1 discipline QC 2 working days, L2 cross-discipline review 2 working days, correction/retest contingency 2 working days, L3 technical committee 1 working day, authorisation/release 1 working day and appointing-party acceptance 3 working days per normal exchange package. Basis: A visible allowance protects checks and exchange decisions; these are office planning minima and must increase for complexity or binding recipient terms. Source: [S04](RESEARCH.md#s04)
O-DEC-006 | Use unique stable ExchangeIDs allocated from the approved project exchange register; separate RIBA Stage 2 Concept Design and Stage 3 Spatial Coordination unless an appointment explicitly groups their outcomes. Basis: Duplicate #01 and numbering gaps cannot establish the intended historic mapping; distinct decisions and dates must remain traceable. Source: [G-F](RESEARCH.md#g-f)
O-DEC-007 | The task-team lead owns the TIDP commitment; the LAP owns the coordinated MIDP baseline; every approved delivery-row change must propagate by the same ChangeID before the affected new commitment takes effect. Basis: Separate production ownership and coordinated delivery authority with exact source-row lineage and review evidence. Source: [G-F](RESEARCH.md#g-f)
O-DEC-013 | Keep controlled masters in the restricted office standards CDE with document ID, revision, approval and exact URI; distribute read-only approved office views and retain superseded editions without overwriting issued project baselines. Basis: Controlled identity, access and history must survive publication and change. Source: [G-C](RESEARCH.md#g-c), [S05](RESEARCH.md#s05)
O-DEC-019 | Use WIP / Shared / Published / Archive as logical CDE states; retain 02.PUBLISH only as the existing platform alias for Published; keep revision, suitability, permitted use and acceptance as separate metadata. Basis: Logical workflow maps to platform labels without changing issued identity or reliance. Source: [G-C](RESEARCH.md#g-c)
O-DEC-021 | Use R00 for initial WIP, then R01, R02 and never-recycled per-container revisions, expanding digits beyond R99; unchanged containers retain their actual revision; appointment codes override through one approved mapping. Basis: Carries forward O3 Rnn without forcing equal revisions on unchanged content. Source: [G-C](RESEARCH.md#g-c)
O-DEC-022 | Use local SU-WIP = team work, SU-COORD = coordination, SU-INFO = reference, SU-REVIEW = formal review, SU-ISSUE = authorised defined use; record permitted use and recipient acceptance separately; map appointment codes in one register. Basis: The O3 list prevents confusion with S1/S2/S3 severity and RACI. Source: [G-C](RESEARCH.md#g-c), [S04](RESEARCH.md#s04)
O-DEC-030 | Use ISO 8601 dates (YYYY-MM-DD), access timestamps with UTC offset, and explicit units/source for service intervals; validate chronology and receiver mappings with actual calendars/time zones. Basis: Unambiguous dates/units support traceable schedules and exchanges. Source: [S16](RESEARCH.md#s16), [G-F](RESEARCH.md#g-f)
O-DEC-041 | Use 95% valid applicable non-mandatory values as informational progress only; define numerator, denominator, scope and cut-off and report missing/invalid/excluded/not-applicable separately; all applicable mandatory geometry/data/documentation must pass before release. Basis: O3 acceptance forbids averaging away mandatory failures. Source: [S04](RESEARCH.md#s04)
O-DEC-049 | Require isolated representative mobilisation pack: native seed, known-value IFC/data/documents, valid/invalid fixtures, coordinates, allowed/denied access, BCF round trip, correction/retest log and restored backup; project tests stay NOT EXECUTED until evidenced. Basis: Specified test design and workshop screenshots do not prove live exchange success. Source: [P02](RESEARCH.md#p02), [S04](RESEARCH.md#s04)
O-DEC-078 | No blanket omission of cables/wires/conduits/items ≤50 mm needed for safety, coordination, quantities or assets; permitted omissions need scoped requirement, owner, alternative documentation and receiving approval. Basis: Information need is purpose-led, not blanket size/LOD. Source: [S07](RESEARCH.md#s07), [S06](RESEARCH.md#s06)
O-DEC-083 | Maintain exact source TIDP ID/row/revision, exchange/EIR/container IDs, parties, dependencies, production dates, separate L1/L2/rework/L3/release/acceptance windows, forecast/actual evidence and ChangeID in MIDP; synchronise all affected TIDPs. Basis: O3 ownership and source-row lineage govern. Source: [G-F](RESEARCH.md#g-f)
O-DEC-087 | Use BCF 3.0 XML as default qualification route; BCF 3.0 API requires separately approved endpoints/permissions and returned-issue test; preserve issue ID/revision/GUID/viewpoint/assignment/status/retest. Basis: XML/API are separate implementations needing endpoint compatibility. Source: [S13](RESEARCH.md#s13)
O-DEC-088 | Use audited IDS 1.0 where supported for IFC data with rule IDs/hash/checker and valid/invalid fixtures; geometry/access/competent review remain separate. Basis: IDS scope is information validation, not full geometric/safety assurance. Source: [S20](RESEARCH.md#s20), [S04](RESEARCH.md#s04)
O-DEC-099 | LAP/task leads own information risks and review resources/dependencies/requirements/tools/security/safety before commitment/mobilisation/exchange and material change. Basis: Risk ownership follows actual delivery functions. Source: [G-E](RESEARCH.md#g-e), [G-F](RESEARCH.md#g-f)
O-DEC-100 | Record defaults as decided office policy on 2026-10-14 with linked IDs; activation still requires actual authorised holders, scoped registers, signed rights, installed builds and passing mobilisation/receiver evidence; preserve NOT EXECUTED/NOT VERIFIED facts. Basis: Founder-authorised choices settle defaults without fabricating contract approval or implementation. Source: [G-E](RESEARCH.md#g-e), [S04](RESEARCH.md#s04)
Office policy to apply
Naming | CLIENT-ORG-PROJ-VOLUME-LEVEL-TYPE-ROLE-NUMBER.ext; uppercase tokens, four-digit NUMBER, approved lowercase extension. One appointment mapping overrides defaults; preserve issued identities.
Revision | R00 initial WIP then R01/R02; never recycle; expand beyond R99. Unchanged containers retain actual revision.
Acceptance | 100% valid applicable mandatory geometry/data/documentation; zero unresolved required hard-intersection or mandatory access/safety failures. Optional 95% progress is informational only.
Review minima | L1 2, L2 2, correction/retest 2, L3 1, authorisation/release 1, recipient acceptance 3 working days; normally sequential. Increase for complexity or binding recipient terms. Production estimated by actual team.
Ownership | Task-team lead owns TIDP; LAP owns MIDP. Every affected plan uses the same approved ChangeID before changed commitments take effect.
Severity | S1 Critical: acknowledge 4 working hours, target correction 2 working days, immediately stop affected unsafe/release work. S2 Major: 5 working days or earlier gate. S3 Minor: permissible disposition/correction before next gate.
Example calendar | CAL-SYN-01: Monday-Friday, 8 h/day, Asia/Dubai, no scenario holidays. Inclusive durations; FS+0 starts the next working day. Actual holiday/capacity records required.
Release | L1/L2 precede L3 Release/Resubmit; delivery-team authorisation and PM release precede separate recipient acceptance. Missing mandatory evidence blocks affected release.
Controlled project inputs
Project progress status
Issue status
Suitability
CDE state
Trade
Discipline block
Severity
Test type
Yes / No
L3 decision
Controlled code lists
Suitability | SU-WIP
Suitability | SU-COORD
Suitability | SU-INFO
Suitability | SU-REVIEW
Suitability | SU-ISSUE
CDE_state | WIP
CDE_state | Shared
CDE_state | Published
CDE_state | Archive
Trades | AR
Trades | ID
Trades | ST
Trades | ME
Trades | EL
Trades | LI
Trades | WS
Trades | DR
Trades | FF
Trades | LS
Trades | CI
Trades | DU
Trades | WU
Disciplines | BIM / information coordination
Disciplines | ARC
Disciplines | ID
Disciplines | LSC
Disciplines | STR
Disciplines | ELEC
Disciplines | MEC
Disciplines | PLU
Severity | S1 Critical
Severity | S2 Major
Severity | S3 Minor
Test_types | H
Test_types | C
Test_types | A
Test_types | D
Test_types | V
Yes_No | Yes
Yes_No | No
Progress_status | Planned
Progress_status | In Production
Progress_status | In Discipline Check
Progress_status | Checked for Shared
Progress_status | In Coordination Review
Progress_status | Authorised
Progress_status | Submitted
Progress_status | Accepted
Progress_status | Rejected
Progress_status | Superseded
Progress_status | Hold
Issue_status | Open
Issue_status | In Progress
Issue_status | Ready for Review
Issue_status | Closed
Issue_status | Reopened
Run_result | pass
Run_result | fail
Run_result | blocked
Relations | FS
Relations | SS
Relations | FF
RIBA_stage | 0
RIBA_stage | 1
RIBA_stage | 2
RIBA_stage | 3
RIBA_stage | 4
RIBA_stage | 5
RIBA_stage | 6
RIBA_stage | 7
Exclusion_type | intended join
Exclusion_type | opening
Exclusion_type | duplicate-reference
Exclusion_type | out-of-scope
Input_event | Prepared
Input_event | Checked
Input_event | Shared
Input_event | Authorised
Input_event | Submitted
Input_event | Accepted
Input_event | Rejected
Committee | Release
Committee | Resubmit
Disposition | pass
Disposition | rework
Change_decision | approve
Change_decision | reject
Applicability | Applicable
Applicability | NA
Applicability | U
Units | mm
Pair_index | H,D
Pair_index | H,CA
Pair_index | H,D,CA
Pair_index | U
Pair_index | NA
Pair_index | —
Discipline_trade | AR
Discipline_trade | ID
Discipline_trade | ST
Discipline_trade | ME
Discipline_trade | EL
Discipline_trade | LI
Discipline_trade | WS
Discipline_trade | DR
Discipline_trade | FF
Discipline_trade | LS
Discipline_trade | CI
Discipline_trade | DU
Discipline_trade | WU
Discipline_trade | BIM / information coordination
Discipline_trade | ARC
Discipline_trade | LSC
Discipline_trade | STR
Discipline_trade | ELEC
Discipline_trade | MEC
Discipline_trade | PLU
Tolerance_rule_labels | H: hard intersection
Tolerance_rule_labels | C: installation clearance
Tolerance_rule_labels | A: access / maintenance / safety
Tolerance_rule_labels | D: duplicates
Tolerance_rule_labels | V: verified existing condition
Sheet / specification map
Document control | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 11; 1. Purpose, scope and document control
O3 policy | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 31; 2. One office decision baseline
Tolerances | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 44; 3. Test semantics, tolerances and release thresholds
RIBA stages | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 56; 3. Test semantics, tolerances and release thresholds
Trades | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 71; 4. Trades, selections and generated pair matrix
Pair index example | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 89; 4. Trades, selections and generated pair matrix
Field specification | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 105; 5. Workbook structure and column / field specification
Rule examples | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 119; 6. Completed original examples — synthetic, not live approval
Issue examples | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 126; 6. Completed original examples — synthetic, not live approval
Severity service levels | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 151; 7. Run, triage, correct and independently close
Coverage trace | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 172; 9. Correction trace and operational records still required
References | BBM-STD-50-CLASH_MATRIX-V0.2.md, line 190; References
Control | Operational register from Field specification; expanded header row recorded in PROGRESS-O.md.
Models | Operational register from Field specification; expanded header row recorded in PROGRESS-O.md.
Sets | Operational register from Field specification; expanded header row recorded in PROGRESS-O.md.
Rules | Operational register from Field specification; expanded header row recorded in PROGRESS-O.md.
Runs | Operational register from Field specification; expanded header row recorded in PROGRESS-O.md.
Issues | Operational register from Field specification; expanded header row recorded in PROGRESS-O.md.
Exclusions | Operational register from Field specification; expanded header row recorded in PROGRESS-O.md.

## Control
Control
EXAMPLE - delete: rows 5:5. Replace synthetic records before use.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 105
RegisterID | Revision | DocumentID | prepared IDs | prepared dates | checked IDs | checked dates | verified IDs | verified dates | approved IDs | approved dates | EIR references | BEP references | LOIN references | tool | build | settings hash | effective date | distribution list | approval evidence
SYN-REG-01 | R01 | BBM-STD-50-CLASH_MATRIX | [14 empty] | 2026-10-14 |  |  | EXAMPLE - delete

## Models
Models
EXAMPLE - delete: rows 5:7. Replace synthetic records before use.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 105
ModelID | Revision | ContainerID | trade | producer/team | native/source revisions | exchange revisions | URI/hash | units | CRS | transform ID | zone | level | Shared decision ID | Shared decision date | export | build | profile | included scope | excluded scope
SYN-ST | R02 | CLI-OFF-P001-Z01-L01-M3-S-0001.ifc | ST |  |  |  |  | mm | SYN-CRS01 |  | Z01 | L01 | [5 empty] | EXAMPLE - delete; replace with actual approved Shared scope |  | EXAMPLE - delete
SYN-ME | R03 | CLI-OFF-P001-Z01-L01-M3-M-0001.ifc | ME |  |  |  |  | mm | SYN-CRS01 |  | Z01 | L01 | [5 empty] | EXAMPLE - delete; replace with actual approved Shared scope |  | EXAMPLE - delete
SYN-AR | R02 | CLI-OFF-P001-Z01-L01-M3-A-0001.ifc | AR |  |  |  |  | mm | SYN-CRS01 |  | Z01 | L01 | [5 empty] | EXAMPLE - delete; replace with actual approved Shared scope |  | EXAMPLE - delete

## Sets
Sets
EXAMPLE - delete: rows 5:7. Replace synthetic records before use.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 105
SetID | Revision | ModelID | revision | native/IFC filter | category/class/property clauses | zone | insulation/support/envelope inclusion | element count | exclusion ID | tester | result URI
SYN-SET-ST | R01 | SYN-ST | R02 | EXAMPLE - delete; define actual filter |  | Z01 | Relevant insulation, fittings, supports and envelopes |  |  |  |  | EXAMPLE - delete
SYN-SET-ME | R01 | SYN-ME | R03 | EXAMPLE - delete; define actual filter |  | Z01 | Relevant insulation, fittings, supports and envelopes |  |  |  |  | EXAMPLE - delete
SYN-SET-AR | R01 | SYN-AR | R02 | EXAMPLE - delete; define actual filter |  | Z01 | Relevant insulation, fittings, supports and envelopes |  |  |  |  | EXAMPLE - delete

## Rules
Rules
EXAMPLE - delete: rows 5:8. Replace synthetic records before use.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 105
RuleID | Revision | PairKey | SetA revisions | SetB revisions | model | zone | H/C/A/D/V type | requirement IDs | LOIN IDs | numeric threshold | units | envelope ID | rationale/source | tool mode | precision fixture | severity | frequency/trigger | designer | checker | enabled | approval ID
SYN-H01 | R01 | ME-ST | SYN-SET-ST R01 | SYN-SET-ME R01 |  | Z01 | H |  |  | 0 | mm |  | EXAMPLE - delete; 0 mm deliberate penetration allowance; qualify precision fixture |  |  | S1 Critical | Weekly; each comment round; changed sources/rules; before exchange |  |  | No |  | EXAMPLE - delete
SYN-C01 | R01 | ME-ST | SYN-SET-ME R01 | SYN-SET-ST R01 |  | Z01 | C | SYN-REQ-C01 R01 |  | 150 | mm |  | EXAMPLE - delete; Fictitious installation requirement; no blanket 150 mm |  |  | S2 Major | Weekly; each comment round; changed sources/rules; before exchange |  |  | No |  | EXAMPLE - delete
SYN-A01 | R01 | AR-ME | SYN-SET-ME R01 | SYN-SET-AR R01 |  | Z01 | A | SYN-REQ-A01 R01 |  | 600 | mm |  | EXAMPLE - delete; Fictitious manufacturer envelope; no blanket access distance |  |  | S2 Major | Weekly; each comment round; changed sources/rules; before exchange |  |  | No |  | EXAMPLE - delete
SYN-D01 | R01 | AR-AR | SYN-SET-AR R01 | SYN-SET-AR R01 |  | Z01 | D | [5 empty] | EXAMPLE - delete; Exact duplicate investigation; never merge by proximity |  |  | S3 Minor | Weekly; each comment round; changed sources/rules; before exchange |  |  | No |  | EXAMPLE - delete

## Runs
Runs
EXAMPLE - delete: rows 5:5. Replace synthetic records before use.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 105
RunID | Rule revision | source-set manifest/hash | run timestamp | build | settings | counts selected | counts tested | counts raw | counts grouped | counts excluded | counts open | result URI | issue IDs | runner | checker | pass/fail/blocked
SYN-RUN-01 | SYN-H01 R01 | [14 empty] | blocked | EXAMPLE - delete

## Issues
Issues
EXAMPLE - delete: rows 5:6. Replace synthetic records before use.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 105
IssueID | Rule IDs | run IDs | source models | revisions | stable element GUIDs | title | description | viewpoint URI | camera | clipping | location | severity | assignee | due date | status | requirement | disposition/exception decision | corrected revision | retest run | reviewer | date | closure decision
SYN-ISS-001 | SYN-H01 | SYN-RUN-01 | SYN-ST; SYN-ME | R02; R03 | ST-001; ME-019 | EXAMPLE - delete; beam / duct overlap | Synthetic 12 mm penetration; no actual run supplied |  |  |  | Z01/L01 | S1 Critical | mechanical designer |  | Open | [7 empty] | EXAMPLE - delete
SYN-ISS-002 | SYN-A01 | SYN-RUN-01 | SYN-ME; SYN-AR | R03; R02 | ME-022; AR-007 | EXAMPLE - delete; equipment withdrawal | Synthetic 520 mm free space versus fictitious 600 mm need |  |  |  |  | S2 Major |  |  | In Progress | [7 empty] | EXAMPLE - delete

## Exclusions
Exclusions
EXAMPLE - delete: rows 5:5. Replace synthetic records before use.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 105
ExclusionID | Rule/set scope | element IDs | reason | evidence | permissible authority | start dates | expiry dates | review trigger | approved record | type
SYN-EXC-01 | SYN-H01 R01 |  | EXAMPLE - delete; scope and permissible authority needed before suppression | [6 empty] | opening | EXAMPLE - delete

## Document control
Document control
Reference table; approved office method.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 11
Control field | Value / entry required
Document ID / revision / effective date | BBM-STD-50-CLASH_MATRIX / V0.1 / 2026-10-14
Prepared / checked / verified / approved | BIM Coordinator / independent coordination checker / discipline leads / BIM Manager; enter identifiable IDs and dates in the project copy
Appointment and intended use | [appointment ID; delivery team; in-scope exchange and permitted use]
Requirements baseline | [EIR, BEP, LOIN, design basis, authority annex, manufacturer evidence: exact IDs/revisions]
Matrix / rule-set baseline | [register ID, revision, rule-set hash, approval record, CDE location]
Tool baseline | [federator/checker product, full build, exporter build, settings/preset hash, known-result qualification]
Supersession and distribution | Prior export retained privately; approved rules distributed to every affected task team and supplier; historic issues keep their original identity

## O3 policy
O3 policy
Reference table; approved office method.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 31
Shared O3 policy field | Controlled office value | Check / migration rule
Container identity | Eight uppercase hyphen-separated tokens; NUMBER is four digits; lowercase approved extension | Example CLI-OFF-P001-Z01-L01-M3-A-0001.ifc; ZZ means whole scope; validate every token against project code lists
Revision | R00 initial WIP, then R01, R02…; expand digits beyond R99; never recycle | Same identity for changed content; revision is metadata, not part of the identity; unchanged containers retain their actual revision
Suitability | SU-WIP: team work only; SU-COORD: coordination; SU-INFO: reference information; SU-REVIEW: formal review; SU-ISSUE: authorised defined use | Local codes, not ISO or UK national-annex codes; store permitted use and actual acceptance decision separately
CDE state | WIP / Shared / Published / Archive | SU-ISSUE does not itself prove appointing-party acceptance; Published has the explicit authorised-use/release record; preserve rejected and superseded evidence
Office drawing/model aliases | Preserve existing internal names with an ID-to-container mapping | AR→architectural trade, A→external role; ST→trade, S→role; ME/WS/DR/FF→trades, M/P/F→registered roles. Do not equate trade code with role code
Appointment override | One project register maps client grammar, revisions and suitability to these meanings | Preserve past issued identities; apply authorised mapping to future issues; no parallel active naming lists

## Tolerances
Tolerances
Reference table; approved office method.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 44
Rule type | Office detection setting | Required evidence and pass condition | Change control
H: hard intersection | 0 mm deliberate penetration allowance; tool contact/precision behavior recorded | No unresolved unintended physical overlap in required scope. Include insulation, fittings and relevant supports. Mere touching is reviewed against tool behavior; numeric noise is dispositioned, never silently dropped | Qualified precision fixture; any numerical epsilon is documented by tool/units and independently checked; it cannot authorise a physical conflict
C: installation clearance | Required separation/envelope from design, installation sequence and manufacturer requirement; no blanket 150 mm | Measured minimum distance ≥ recorded requirement or no obstruction of the explicit envelope; installation and removal sequence checked | Requirement ID, actual millimetres/envelope and competent designer required before enabling rule; missing value blocks rule activation
A: access / maintenance / safety | Exact access, swing, withdrawal and route envelope from applicable code/design/manufacturer; no blanket 500 mm | Required envelope free; route and activity usable in designer review; retain dimensions and source revision | Safety/access requirements cannot be waived by BIM Manager or model tolerance
D: duplicates | Exact coincident geometry/identity investigation; no general 10 mm merge rule | No unintended duplicate in selected population. Separate repeated elements, joins and deliberate shared-reference geometry explicitly | Never delete by proximity alone; producer corrects with before/after evidence
V: verified existing condition | Survey/design acceptance method and accuracy from approved evidence | Reconcile observed and modelled state with source uncertainty, deviations and owner decision | A 0 mm clash setting does not assert zero survey uncertainty or as-built accuracy

## RIBA stages
RIBA stages
Reference table; approved office method.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 56
Project stage | Correct RIBA 2020 term | Coordination focus / information need
0 / 1 | Strategic Definition / Preparation and Briefing | Requirements, existing-condition reliability, responsibilities and test scope
2 | Concept Design | Primary routes, space reservations and provisional interface evidence
3 | Spatial Coordination | Coordinated object locations, interfaces, clearance/access requirements
4 | Technical Design | Defined openings, sizes, installation/support detail and approved design checks
5 | Manufacturing and Construction | Fabrication/install interfaces, temporary works and sequence information where appointed
6 / 7 | Handover / Use | Verified delivered condition, service access, residual risks and operational triggers

## Trades
Trades
Reference table; approved office method.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 71
Office trade | Selection scope to define in the project copy
AR | Envelope, walls, doors/windows, floors/roofs, vertical circulation and architectural equipment
ID | Interior partitions, ceilings, finishes, interior doors and furniture
ST | Primary structure, foundations, slabs, framing and structural circulation
ME | Air systems, mechanical equipment, pipework, insulation, valves and supports
EL | Electrical containment, equipment, communications, security and alarm components
LI | Lighting devices and equipment; coordinate the EL/LI boundary to avoid double ownership
WS | Water services, fittings, equipment and insulation
DR | Drainage, fixtures, fittings, falls and inspection requirements
FF | Fire protection pipework, equipment, controls and heads
LS | Landscape, soil zones, planting, irrigation interfaces and hard surfaces
CI | Civil routes, surfaces, drainage structures and external constructed interfaces
DU | Dry utilities, cabinets, ducts, containment and network interfaces
WU | Wet utilities, chambers, pipework and network interfaces

## Pair index example
Pair index example
EXAMPLE - delete: rows 5:11. Replace synthetic records before use.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 89
Pair index (illustrative) | ST | AR | ME | EL | WS | DR | FF
ST | H,D | H,CA | H,CA | H,CA | H,CA | H,CA | H,CA | EXAMPLE - delete
AR | — | H,D | H,CA | H,CA | H,CA | H,CA | H,CA | EXAMPLE - delete
ME | — | — | H,D,CA | H,CA | H,CA | H,CA | H,CA | EXAMPLE - delete
EL | — | — | — | H,D,CA | H,CA | H,CA | H,CA | EXAMPLE - delete
WS | — | — | — | — | H,D,CA | H,CA | H,CA | EXAMPLE - delete
DR | — | — | — | — | — | H,D,CA | H,CA | EXAMPLE - delete
FF | — | — | — | — | — | — | H,D,CA | EXAMPLE - delete

## Field specification
Field specification
Reference table; approved office method.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 105
Table / key | Fields: type and validation | Owner / relationship
Control / RegisterID+Revision | DocumentID, prepared/checked/verified/approved IDs and dates, EIR/BEP/LOIN references, tool/build/settings hash, effective date, distribution list, approval evidence: text/date/URI | BIM Manager; revision-specific baseline
Models / ModelID+Revision | ContainerID, trade, producer/team, native/source and exchange revisions, URI/hash, units/CRS/transform ID, zone/level, Shared decision ID/date, export/build/profile, included/excluded scope: typed text/URI/date | Producer supplies; coordinator validates exact approved Shared set
Sets / SetID+Revision | ModelID/revision, native/IFC filter, category/class/property clauses, zone, insulation/support/envelope inclusion, element count integer ≥0, exclusion ID, tester/result URI | Producer and independent checker; stable GUIDs in run evidence
Rules / RuleID+Revision | PairKey, SetA/SetB revisions, model/zone, H/C/A/D/V type, requirement/LOIN IDs, numeric threshold and units or envelope ID, rationale/source, tool mode, precision fixture, severity, frequency/trigger, designer, checker, enabled boolean, approval ID | Lead appointed party owns coordinated baseline; no enabled C/A without source and value
Runs / RunID | Rule revision, source-set manifest/hash, run timestamp/build/settings, counts selected/tested/raw/grouped/excluded/open, result URI, issue IDs, runner/checker, pass/fail/blocked | Coordinator; immutable evidence per run, not overwritten by latest export
Issues / IssueID | Rule/run IDs; source models/revisions; stable element GUIDs; title/description; viewpoint URI/camera/clipping/location; severity, assignee, due date, status, requirement; disposition/exception decision; corrected revision; retest run and reviewer/date; closure decision | Designer owns correction; independent checker closes; BCF topic GUID stored as external key
Exclusions / ExclusionID | Rule/set scope and element IDs, reason, evidence, permissible authority, start/expiry dates, review trigger, approved record; type controlled: intended join / opening / duplicate-reference / out-of-scope | Checker verifies exclusion before result; no indefinite anonymous suppression

## Rule examples
Rule examples
EXAMPLE - delete: rows 5:8. Replace synthetic records before use.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 119
Rule / revision | Models and zone | Selections / test | Setting / source | Severity / owner / trigger
SYN-H01 / R01 | SYN-ST R02 + SYN-ME R03; Z01/L01 | Framing vs insulated ductwork; H | 0 mm; section 3; approved structural opening only via explicit exclusion | S1 if structural integrity affected; mechanical designer with structural lead; weekly and changed-source/pre-exchange rerun | EXAMPLE - delete
SYN-C01 / R01 | SYN-ME R03 + SYN-ST R02; Z01/L01 | Installation envelope vs framing; C | 150 mm synthetic design requirement SYN-REQ-C01 R01; actual projects substitute verified requirement | S2; mechanical designer; changed dimensions/sequence and each comment round | EXAMPLE - delete
SYN-A01 / R01 | SYN-ME R03 + SYN-AR R02; Z01/L01 | Equipment withdrawal envelope vs partition; A | 600 mm synthetic manufacturer requirement SYN-REQ-A01 R01; not an office-wide tolerance | S1 if safety/required access blocked, otherwise S2; mechanical and architectural designers; manufacturer/layout change | EXAMPLE - delete
SYN-D01 / R01 | SYN-AR R02; Z01/L01 | Wall population vs itself; D | Exact duplicate investigation; same-element GUID pairs removed from comparison | S3 unless consequential defect; architectural lead; every Shared submission | EXAMPLE - delete

## Issue examples
Issue examples
EXAMPLE - delete: rows 5:6. Replace synthetic records before use.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 126
Issue / source run | Location and elements | Viewpoint / assigned owner / due / status | Disposition and required closure evidence
SYN-ISS-001 / SYN-RUN-01 | Z01/L01; SYN-ST beam GUID ST-001; SYN-ME duct GUID ME-019; 12 mm penetration | SYN-VP-001 (synthetic ID); mechanical designer; Day 2; Open, S1 | Designer reroutes duct; structural lead confirms no unapproved opening. New SYN-ME R04; independent SYN-RUN-02 shows zero overlap and unchanged required access; then Ready for Review→Closed with dated checker record | EXAMPLE - delete
SYN-ISS-002 / SYN-RUN-01 | Z01/L01; equipment ME-022 and partition AR-007; 520 mm free space vs 600 mm need | SYN-VP-002; architectural designer with mechanical lead; Day 5; In Progress, S2 | Move partition or redesign equipment arrangement under competent review; retain 80 mm shortfall in record; retest H and A with new exact models before closure | EXAMPLE - delete

## Severity service levels
Severity service levels
Reference table; approved office method.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 151
Severity | Office response / deadline | Escalation and old-code migration
S1 Critical | Acknowledge within 4 working hours; target correction within 2 working days; immediately stop affected unsafe/release work | Escalate to discipline leads and project manager immediately; legacy C/priority 1 assessed for actual effect, not automatically “Low” by size
S2 Major | Correct within 5 working days or earlier gate | Escalate overdue or dependency-impacting issues; legacy H/priority 1 normally investigated here if not critical
S3 Minor | Correct or record permissible disposition before next gate | Legacy M/L/priorities 2/3 are reassessed; mandatory failures still block release regardless of severity

## Coverage trace
Coverage trace
Reference table; approved office method.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 172
Research / gap / conflict | Present evidence in this revision
T10.1 | Sections 4–7: full trade scope, model/zone/revision manifest, frequency and change triggers
T10.2 | Section 3: separate H/C/A methods and approved requirement sources; no stage-derived tolerance
T10.3 | Sections 4–7: pair coverage, exclusions, duplicate grouping, severity and permissible disposition
T10.4 | Sections 5–6: issue/BCF IDs, GUIDs, viewpoints, ownership, dates and states
T10.5 | Sections 6–8: competent design disposition, independent retest, closure and recurrence evidence
O06 P1 / C06 / C11 | Conflicting 15/5 mm retired explicitly; correct stages; broken banner replaced; actor corrected; one rule table
O06 P2 / C04 / C07 | Versioned manifests, exclusions, issue links, release threshold, separate suitability/severity and acceptance
O06 P3 | Pair matrix generated from approved register; cardinality and NA coverage check specified
C02 / C03 / C08 / C10 / C12 / C16 | Shared naming/metadata; linked MIDP/TIDP; private provenance; survey/build qualification; competent safety authority

## References
References
Reference table; approved office method.
Source: BBM-STD-50-CLASH_MATRIX-V0.2.md, line 190
Tag | Title | Publisher | Year / edition | URL / evidence
S01 | ISO 19650-1 — Concepts and principles | ISO | 2018, ed.1 | [Catalogue / abstract](https://www.iso.org/standard/68078.html?browse=tc); published, revision underway
S02 | ISO 19650-2 — Delivery phase of the assets | ISO | 2018, ed.1 | [Catalogue / abstract](https://www.iso.org/fr/standard/68080.html); publisher result exposes English abstract and status
S04 | ISO 19650-4 — Information exchange | ISO | 2022, ed.1 | [Catalogue / abstract](https://www.iso.org/cms/live/live/en/sites/isoorg/contents/data/standard/07/82/78246.html?browse=tc)
S05 | ISO 19650-5 — Security-minded approach to information management | ISO | 2020, ed.1 | [Catalogue / abstract](https://committee.iso.org/cms/live/live/en/sites/isoorg/contents/data/standard/07/42/74206.html)
S06 | ISO 19650-6 — Health and safety information | ISO | 2025, ed.1 | [Catalogue / abstract](https://www.iso.org/standard/82705.html)
S07 | ISO 7817-1 — Level of information need: concepts and principles | ISO | 2024, ed.1 | [Catalogue / abstract](https://www.iso.org/standard/82914.html?browse=tc)
S13 | BCF API — Final version of BCF 3.0; BCF REST API README | buildingSMART International | Version 3.0; release year unverified | [Releases](https://github.com/buildingSMART/BCF-API/releases); [3.0 specification](https://github.com/buildingSMART/BCF-API/blob/release_3_0/README.md?plain=1)
S21 | RIBA Plan of Work 2020 | Royal Institute of British Architects | 2020 | [Current resource page](https://www.riba.org/work/insights-and-resources/riba-plan-of-work/); [2020 template](https://www.riba.org/media/sszn5kkt/2020ribaplanofworktemplatepdf.pdf)
G-C | Guidance C — Facilitating the CDE workflow and technical solutions | UK BIM Framework | ed.1, September 2020 | [Official PDF](https://ukbimframework.org/wp-content/uploads/2020/09/Guidance-Part-C_Facilitating-the-common-data-environment-workflow-and-technical-solutions_Edition-1.pdf); archived guidance
P02 | Define Supporting Infrastructure for BIM Implementation | Penn State | v2.2, 2019 | [BEP infrastructure chapter](https://psu.pb.unizin.org/bimprojectexecutionplanningv2x2/chapter/define-supporting-infrastructure-for-bim-implementation/)
B04 | OPDC BIM Guidelines | Smithsonian Institution | November 2024 | [Guidelines](https://www.sifacilities.si.edu/sites/default/files/Files/BIM/OPDC_BIM_Guidelines_Nov2024.pdf); benchmark concepts only