## Read me
Field | Instruction
Document | BBM-STD-51-REGISTERS-V0.1
State | Private WIP template for office review and adoption
Examples | SYN-P001 is fictional. All role IDs, dates and evidence tokens in examples are synthetic.
Use | Copy blank tables into the restricted project register. Replace synthetic particulars and obtain actual authority before activation.
Inputs | Amber blank rows are editable. Dropdowns are prompts; validate required fields and joins before release.
Authority | A cell is not an appointment, permit, signed licence or receiving-system test.
Revision | Template V0.1. Project records use Rnn with stable IDs, source revisions and ChangeID.
Note 1 | Authority: BBM-STD-50 V0.2 section 2 and BBM-STD-10 V0.3 section 8.3. This pack implements the existing naming decision.
Note 2 | Research 2026-10-16: ISO catalogues 68078, 68080, 75109, 74206 and 82914; UK BIM Framework Guidance A/D/E ed.2 (2021). See Markdown References for exact URLs.
Note 3 | Master index is generated from actual local draft files. Empty approval evidence and review dates must be populated before adoption. Future W1 IDs are allocations, not current releases.
Note 4 | Number namespace and additional project codes must be recorded by the actual project naming authority. Test pack contains expected results, not measured host results.
Path base | Every local register path is relative to office-rev, one directory above this xlsx folder. Proposed targets are draft references, not approved releases.
Final W1 snapshot | Master index includes all seven W1 draft packs and their XLSX/DOCX companions at final integration. IDs/revisions remain unadopted. Dependencies record the scoped writing-plan prerequisite pins; other cited owner interfaces remain in each standard. Actual approvals/next-review dates must be completed before adoption.

## Master index
ID | Revision | Title or representation | State | Owner function | Current draft path | SHA-256 or manifest | Next review trigger | Next review date | Approval evidence | Parent standard ID
BBM-STD-00 | V0.2 | BBM-STD-00-GLOSSARY-V0.2.md | Draft | Office standards custodian | Project\BBM-STD-00-GLOSSARY-V0.2.md | df18c97dbbbd54f0347f9d4ec28cfd5f7a8e890c7c4557d96bd6222529252040 | Before adoption
BBM-STD-01 | V0.2 | BBM-STD-01-MANUAL-V0.2.md | Draft | Office standards custodian | Project\BBM-STD-01-MANUAL-V0.2.md | 0ed7c2659219b38baaa0a3fed211b7a58caf58368fead5a6ddd7fdf0dc27106f | Before adoption
BBM-STD-02 | V0.2 | BBM-STD-02-OIR-V0.2.md | Draft | Office standards custodian | Project\BBM-STD-02-OIR-V0.2.md | 6a58edfeeea6e1db204cb2624d6deae30dcabd84fd6aa1ce9057e679d645dbd4 | Before adoption
BBM-STD-03 | V0.2 | BBM-STD-03-DIRECTORY-V0.2.md | Draft | Office standards custodian | Project\BBM-STD-03-DIRECTORY-V0.2.md | a62aae59089267036310c96b304ff684572583873bf192e8b746447cdd1108cd | Before adoption
BBM-STD-10 | V0.3 | BBM-STD-10-BEP-V0.3.md | Draft | Office standards custodian | Project\BBM-STD-10-BEP-V0.3.md | 7764180236bc10183e4754ebd67882be0ae07363ad0ca1e02aada61d5a44b6c3 | Before adoption
BBM-STD-11 | V0.1 | BBM-STD-11-DECISIONS-LOG-V0.1.md | Draft | Office standards custodian | Project\BBM-STD-11-DECISIONS-LOG-V0.1.md | dd239aafca5aa5a165662f29b93ac29a106962c29542a52bdec7fb3330530cbf | Before adoption
BBM-STD-12 | V0.1 | BBM-STD-12-BASIS_OF_DESIGN_REPORT-V0.1.md | Draft | Office standards custodian | Project\BBM-STD-12-BASIS_OF_DESIGN_REPORT-V0.1.md | c16777e31f36311a1cbce897064a6c473597d57bb9e9c69f1093a54abb57bc42 | Before adoption
BBM-STD-50 | V0.2 | BBM-STD-50-CLASH_MATRIX-V0.2.md | Draft | Office standards custodian | Project\BBM-STD-50-CLASH_MATRIX-V0.2.md | 9f25d421427815892a00903c815bd6454a1ed7e6fb622db8fafa98b07d7097bf | Before adoption
BBM-STD-51 | V0.1 | BBM-STD-51-REGISTERS-V0.1.md | Draft | Office standards custodian | Project\BBM-STD-51-REGISTERS-V0.1.md | 38f65c181a5d836f89b67cfbfe3a28b6ed340929260b835492eaa87e68b7264f | Before adoption
BBM-STD-MIDP | V0.2 | BBM-STD-MIDP-V0.2.md | Draft | Office standards custodian | Project\BBM-STD-MIDP-V0.2.md | f39a1e9cd47ea9e002d6646f6078212921ce39749f56c462cbf752f4a946299c | Before adoption
BBM-STD-TIDP | V0.2 | BBM-STD-TIDP-V0.2.md | Draft | Office standards custodian | Project\BBM-STD-TIDP-V0.2.md | 172765a2f98356c2fca1c019c85af6d9ce46226832f57085dbaf72468915ad87 | Before adoption
BBM-STD-21 | V0.2 | BBM-STD-21-GUIDE-BIM_AND_REVIT_INITIATION-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-21-GUIDE-BIM_AND_REVIT_INITIATION-V0.2.md | 60c2ec89df50b4ec886dffdf33a0c221867ad99e73d6efe470ebcf220ef5cc20 | Before adoption
BBM-STD-22 | V0.2 | BBM-STD-22-GUIDE-WORK_SHARING_AND_COLLABORATION-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-22-GUIDE-WORK_SHARING_AND_COLLABORATION-V0.2.md | 06a8ccb41796396cd39aff3db29bf690a35ff5f08bf4b2560491a2039f5aeb57 | Before adoption
BBM-STD-23 | V0.2 | BBM-STD-23-GUIDE-BRINGING_IN_CAD_CLEANLY_AND_COMPLEX_WALLS-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-23-GUIDE-BRINGING_IN_CAD_CLEANLY_AND_COMPLEX_WALLS-V0.2.md | 48c09bd9f902b3b28917f20de6a43ca92d7c1f1b26ecc647c4e489e3a26b4d4c | Before adoption
BBM-STD-24 | V0.2 | BBM-STD-24-GUIDE-CURTAIN_WALLS_AND_CURTAIN_SYSTEMS-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-24-GUIDE-CURTAIN_WALLS_AND_CURTAIN_SYSTEMS-V0.2.md | 9f27f5c8e19b7bae767da040c25cac5197e0ee4f3f6fb1dee7f98f43fd39e43f | Before adoption
BBM-STD-25 | V0.2 | BBM-STD-25-GUIDE-PROJECT_INITIATION_WORKED_EXAMPLE-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-25-GUIDE-PROJECT_INITIATION_WORKED_EXAMPLE-V0.2.md | 5a8633fa7993792faa20f703ff99db6c789dff0f8aede416b5473d27d21aa39b | Before adoption
BBM-STD-26 | V0.2 | BBM-STD-26-GUIDE-INTRODUCTION_TO_FAMILIES_AND_PARAMETERS-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-26-GUIDE-INTRODUCTION_TO_FAMILIES_AND_PARAMETERS-V0.2.md | 3a3ffb51b75c936f6f9774978ceb7b466f2d5b9aaf001f6fc83e6e9f37fb1e69 | Before adoption
BBM-STD-27 | V0.2 | BBM-STD-27-GUIDE-FAMILIES_AND_PARAMETERS_IN_PRACTICE-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-27-GUIDE-FAMILIES_AND_PARAMETERS_IN_PRACTICE-V0.2.md | 529003017812f4d15fd781b3ff458b7f06a382e3f0d1b419d25101e2be52d0b4 | Before adoption
BBM-STD-28 | V0.2 | BBM-STD-28-GUIDE-DOCUMENTATION_OVERRIDES_VIEW_TEMPLATES_AND_FILTERS-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-28-GUIDE-DOCUMENTATION_OVERRIDES_VIEW_TEMPLATES_AND_FILTERS-V0.2.md | 52955280f0b399c414fa5e60ed29a9c971d11a55b277f6f7eceb70f7729e1faf | Before adoption
BBM-STD-29 | V0.2 | BBM-STD-29-GUIDE-COMPLEX_GEOMETRY_PATTERN_BASED_AND_ADAPTIVE_FAMILIES_AND_QUICK_RENDERS-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-29-GUIDE-COMPLEX_GEOMETRY_PATTERN_BASED_AND_ADAPTIVE_FAMILIES_AND_QUICK_RENDERS-V0.2.md | 37d1c3cd6311b9a61260163d30a026c47b51ee9c2aa752b5871d1eb661dc923b | Before adoption
BBM-STD-30 | V0.2 | BBM-STD-30-GUIDE-SETTING_UP_A_BUILDING_FILE_URS_LEVELS_LINKS_AND_PLUG_INS-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-30-GUIDE-SETTING_UP_A_BUILDING_FILE_URS_LEVELS_LINKS_AND_PLUG_INS-V0.2.md | 363976af545e2d850fa6a820af1680300a4b7a829b4796562198ce94688147e4 | Before adoption
BBM-STD-31 | V0.2 | BBM-STD-31-GUIDE-ENHANCED_WORKFLOW_DAILY_PROGRESS_CLEAN_DATA_AND_PRODUCTIVITY_PLUG_INS-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-31-GUIDE-ENHANCED_WORKFLOW_DAILY_PROGRESS_CLEAN_DATA_AND_PRODUCTIVITY_PLUG_INS-V0.2.md | e0f7e06cd91386d658a4807de5c0238eef61a907e30236999c6423ff29b41b88 | Before adoption
BBM-STD-32 | V0.2 | BBM-STD-32-GUIDE-ROOMS_AREAS_AND_MODEL_QUALITY_CONTROL-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-32-GUIDE-ROOMS_AREAS_AND_MODEL_QUALITY_CONTROL-V0.2.md | 5b915058ca4db296c1d27a926f93f6f5e781a6cdbebfc54255a9b78a4f2137e1 | Before adoption
BBM-STD-33 | V0.2 | BBM-STD-33-GUIDE-FINISHES_WITH_PLUG_INS_PHASES_AND_GETTING_READY_FOR_DESIGN-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-33-GUIDE-FINISHES_WITH_PLUG_INS_PHASES_AND_GETTING_READY_FOR_DESIGN-V0.2.md | 718c2e9f3edb7fcb39fa85f5487ab7a9d0a67383b76025fa6f0663ef3efa92b1 | Before adoption
BBM-STD-34 | V0.2 | BBM-STD-34-GUIDE-RAILINGS_STAIRS_AND_RAMPS-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-34-GUIDE-RAILINGS_STAIRS_AND_RAMPS-V0.2.md | 980fb3834e9b819b160fa85c4eadfcd835272873c831fe731fffd8ed05881b9f | Before adoption
BBM-STD-35 | V0.2 | BBM-STD-35-GUIDE-IMPORTING_FAMILIES_FROM_OUTSIDE-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-35-GUIDE-IMPORTING_FAMILIES_FROM_OUTSIDE-V0.2.md | 39c956b4451b7294bd995e4ba6e278648e37fd609c237df86f585ac749f8a040 | Before adoption
BBM-STD-36 | V0.2 | BBM-STD-36-GUIDE-DATA_CONTROL_WITH_SCHEDULES-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-36-GUIDE-DATA_CONTROL_WITH_SCHEDULES-V0.2.md | fd1520b6232bb9eb5296b4a9f968ef7ae18ac82a2b157c2ced4881529767a759 | Before adoption
BBM-STD-37 | V0.2 | BBM-STD-37-GUIDE-BUILDING_A_FAMILY_A_WORKED_EXAMPLE_A_CHAIR-V0.2.md | Draft | Office standards custodian | guides-v0.2\BBM-STD-37-GUIDE-BUILDING_A_FAMILY_A_WORKED_EXAMPLE_A_CHAIR-V0.2.md | 772b6fa74a0323f104d527ff046db2a3b8993b4a6cf5ee1385dfc1e72eb325c4 | Before adoption
BBM-STD-12-APPROVALS-REGISTER-V0.1-XLSX | V0.1 | BBM-STD-12-APPROVALS-REGISTER-V0.1.xlsx | Draft | Parent standard custodian | Project\BBM-STD-12-APPROVALS-REGISTER-V0.1.xlsx | bca5032584e611f499a0a07f26907cb56a4a67290a79cdaa8749f1335d02d32e | At parent adoption |  |  | BBM-STD-12
BBM-STD-50-CLASH_MATRIX-V0.2-XLSX | V0.2 | BBM-STD-50-CLASH_MATRIX-V0.2.xlsx | Draft | Parent standard custodian | xlsx\BBM-STD-50-CLASH_MATRIX-V0.2.xlsx | a260468721d5f0f4a3817327ad752524eb64bc59b18ca427a35b571cbe03797c | At parent adoption |  |  | BBM-STD-50
BBM-STD-51-REGISTERS-V0.1-FORMS-XLSX | V0.1 | BBM-STD-51-REGISTERS-V0.1-FORMS.xlsx | Draft | Parent standard custodian | xlsx\BBM-STD-51-REGISTERS-V0.1-FORMS.xlsx | External PROGRESS-W1.md manifest | At parent adoption |  |  | BBM-STD-51
BBM-STD-MIDP-V0.2-XLSX | V0.2 | BBM-STD-MIDP-V0.2.xlsx | Draft | Parent standard custodian | xlsx\BBM-STD-MIDP-V0.2.xlsx | d125d996b0857e9136702908b5217a73e7ce7855f644b91bb32fc5b69d2c0314 | At parent adoption |  |  | BBM-STD-MIDP
BBM-STD-TIDP-V0.2-XLSX | V0.2 | BBM-STD-TIDP-V0.2.xlsx | Draft | Parent standard custodian | xlsx\BBM-STD-TIDP-V0.2.xlsx | 3df75445774159edf384f2865cfe4712b86e13c772373d13e2df5e562c6f7aa0 | At parent adoption |  |  | BBM-STD-TIDP
BBM-STD-00-GLOSSARY-V0.2-DOCX | V0.2 | BBM-STD-00-GLOSSARY-V0.2.docx | Draft | Parent standard custodian | std-docx\BBM-STD-00-GLOSSARY-V0.2.docx | 446e69a232ee30d4de1d764e731bd6f8032a166cc55a27584c0cbaf5196685cb | At parent adoption |  |  | BBM-STD-00
BBM-STD-01-MANUAL-V0.2-DOCX | V0.2 | BBM-STD-01-MANUAL-V0.2.docx | Draft | Parent standard custodian | std-docx\BBM-STD-01-MANUAL-V0.2.docx | 2004a4933ff6e0e2624c779a314cde12061daf03306c9f3d7b3fe3df4bbe2d56 | At parent adoption |  |  | BBM-STD-01
BBM-STD-02-OIR-V0.2-DOCX | V0.2 | BBM-STD-02-OIR-V0.2.docx | Draft | Parent standard custodian | std-docx\BBM-STD-02-OIR-V0.2.docx | 398840ce3ae8e7f692345f33a0160d93d3067eff6bb93833ea9c9773b633ebf7 | At parent adoption |  |  | BBM-STD-02
BBM-STD-03-DIRECTORY-V0.2-DOCX | V0.2 | BBM-STD-03-DIRECTORY-V0.2.docx | Draft | Parent standard custodian | std-docx\BBM-STD-03-DIRECTORY-V0.2.docx | ad6ca3a14c323df6326f41fd036f72837fe91694ec4bb8d8e9bf38d9eb0b0478 | At parent adoption |  |  | BBM-STD-03
BBM-STD-10-BEP-V0.3-DOCX | V0.3 | BBM-STD-10-BEP-V0.3.docx | Draft | Parent standard custodian | std-docx\BBM-STD-10-BEP-V0.3.docx | c3e61ac99cc445f9a35e573304120932f4343d71b214dceaac4c4ec6f68e6cc0 | At parent adoption |  |  | BBM-STD-10
BBM-STD-11-DECISIONS-LOG-V0.1-DOCX | V0.1 | BBM-STD-11-DECISIONS-LOG-V0.1.docx | Draft | Parent standard custodian | std-docx\BBM-STD-11-DECISIONS-LOG-V0.1.docx | f6a388a4ed1f1fb59f601c7d21e19432208a869a87bfe8bd78081388964b5550 | At parent adoption |  |  | BBM-STD-11
BBM-STD-12-BASIS_OF_DESIGN_REPORT-V0.1-DOCX | V0.1 | BBM-STD-12-BASIS_OF_DESIGN_REPORT-V0.1.docx | Draft | Parent standard custodian | std-docx\BBM-STD-12-BASIS_OF_DESIGN_REPORT-V0.1.docx | 72063943377201f6e90d922d4c331150c5f32f8aeb54f3f7148009bd5f5cbb4e | At parent adoption |  |  | BBM-STD-12
BBM-STD-50-CLASH_MATRIX-V0.2-DOCX | V0.2 | BBM-STD-50-CLASH_MATRIX-V0.2.docx | Draft | Parent standard custodian | std-docx\BBM-STD-50-CLASH_MATRIX-V0.2.docx | 4d1d841943beb850c63cbf1797ad6b9d869afecf48a8113ec2475a49cd06889b | At parent adoption |  |  | BBM-STD-50
BBM-STD-51-REGISTERS-V0.1-DOCX | V0.1 | BBM-STD-51-REGISTERS-V0.1.docx | Draft | Parent standard custodian | std-docx\BBM-STD-51-REGISTERS-V0.1.docx | External PROGRESS-W1.md manifest after rebuild | At parent adoption |  |  | BBM-STD-51
BBM-STD-MIDP-V0.2-DOCX | V0.2 | BBM-STD-MIDP-V0.2.docx | Draft | Parent standard custodian | std-docx\BBM-STD-MIDP-V0.2.docx | b41b64b52d38cd30f269c5aea762b7e7e8a5862b8aee1bdfae1996a076b92ee6 | At parent adoption |  |  | BBM-STD-MIDP
BBM-STD-TIDP-V0.2-DOCX | V0.2 | BBM-STD-TIDP-V0.2.docx | Draft | Parent standard custodian | std-docx\BBM-STD-TIDP-V0.2.docx | 365c46ca1aff61d252bc5d3ffa75a11888da3db3942817cd38b7470bf59f623d | At parent adoption |  |  | BBM-STD-TIDP
BBM-STD-52 | V0.1 | BBM-STD-52-AIR-V0.1.md | Draft | Asset-information lead / appointed operator | Project\BBM-STD-52-AIR-V0.1.md | 1c6896ca31da18e7f902feff304b056ee3ed8ff897f7bc0cef88bed51fb04e8f | Before adoption / material source change
BBM-STD-52-AIR-V0.1-FORMS-XLSX | V0.1 | BBM-STD-52-AIR-V0.1-FORMS.xlsx | Draft | Asset-information lead / appointed operator | xlsx\BBM-STD-52-AIR-V0.1-FORMS.xlsx | 3d147de4a51b8acd3affc426976ae77b30f08969cd7d5788d30d85d7a63827d8 | Before adoption / material source change |  |  | BBM-STD-52
BBM-STD-52-AIR-V0.1-DOCX | V0.1 | BBM-STD-52-AIR-V0.1.docx | Draft | Asset-information lead / appointed operator | std-docx\BBM-STD-52-AIR-V0.1.docx | 41ee687a9de1f14b3a129d20376526b6bd4125d6837065d302d35c262018d555 | Before adoption / material source change |  |  | BBM-STD-52
BBM-STD-53 | V0.1 | BBM-STD-53-PIR-V0.1.md | Draft | Appointing-party representative / project director | Project\BBM-STD-53-PIR-V0.1.md | 5f60a0911e9abf0eaf7dec4cadcf16c411674f1989af207827eb1ff573299f5b | Before adoption / material source change
BBM-STD-53-PIR-V0.1-FORMS-XLSX | V0.1 | BBM-STD-53-PIR-V0.1-FORMS.xlsx | Draft | Appointing-party representative / project director | xlsx\BBM-STD-53-PIR-V0.1-FORMS.xlsx | c2d41834672de8e28922e5fbcc868362f3a9d4cc90e5c1f875d6ce83f29b1f32 | Before adoption / material source change |  |  | BBM-STD-53
BBM-STD-53-PIR-V0.1-DOCX | V0.1 | BBM-STD-53-PIR-V0.1.docx | Draft | Appointing-party representative / project director | std-docx\BBM-STD-53-PIR-V0.1.docx | 62ddd3f024231b6a6fe7012f99f68f45472285d68146b6d852669a954e9e4894 | Before adoption / material source change |  |  | BBM-STD-53
BBM-STD-54 | V0.1 | BBM-STD-54-EIR_AND_LOIN-V0.1.md | Draft | Appointing-party Information Manager | Project\BBM-STD-54-EIR_AND_LOIN-V0.1.md | 995aeef65e98267f3fdc0c930fd05a4180fb998e40704ff8b7e544cfbf02707b | Before adoption / material source change
BBM-STD-54-EIR_AND_LOIN-V0.1-FORMS-XLSX | V0.1 | BBM-STD-54-EIR_AND_LOIN-V0.1-FORMS.xlsx | Draft | Appointing-party Information Manager | xlsx\BBM-STD-54-EIR_AND_LOIN-V0.1-FORMS.xlsx | 32048f9b5054c51f44e808b7b61060cd4ab2d847b66dc37f9468f5ca15d0112f | Before adoption / material source change |  |  | BBM-STD-54
BBM-STD-54-EIR_AND_LOIN-V0.1-DOCX | V0.1 | BBM-STD-54-EIR_AND_LOIN-V0.1.docx | Draft | Appointing-party Information Manager | std-docx\BBM-STD-54-EIR_AND_LOIN-V0.1.docx | c0c97845570f146c7dada5fd2d07140ccce45a885d01158fbc63b70ec8ea68d1 | Before adoption / material source change |  |  | BBM-STD-54
BBM-STD-55 | V0.1 | BBM-STD-55-RESPONSIBILITIES-V0.1.md | Draft | Practice director / Information Manager | Project\BBM-STD-55-RESPONSIBILITIES-V0.1.md | ccd9904543f0666800a403f24e0b69f2c330be76f60437706191ba11ec38020c | Before adoption / material source change
BBM-STD-55-RESPONSIBILITIES-V0.1-FORMS-XLSX | V0.1 | BBM-STD-55-RESPONSIBILITIES-V0.1-FORMS.xlsx | Draft | Practice director / Information Manager | xlsx\BBM-STD-55-RESPONSIBILITIES-V0.1-FORMS.xlsx | 83f0437a3913ad8d8b6d7638a22dee5787a96c80525bc6cd0353d2fc93e2105e | Before adoption / material source change |  |  | BBM-STD-55
BBM-STD-55-RESPONSIBILITIES-V0.1-DOCX | V0.1 | BBM-STD-55-RESPONSIBILITIES-V0.1.docx | Draft | Practice director / Information Manager | std-docx\BBM-STD-55-RESPONSIBILITIES-V0.1.docx | 7a412f82f9b7bbba304941bbe873b06d740704c514c32cec3e0e7a340502ab00 | Before adoption / material source change |  |  | BBM-STD-55
BBM-STD-56 | V0.1 | BBM-STD-56-INFORMATION_PROTOCOL-V0.1.md | Draft | Commercial / appointed legal adviser | Project\BBM-STD-56-INFORMATION_PROTOCOL-V0.1.md | 2f88ab4dc82b85422a94b9078be7417840a578fa3a7b8b01dea4c26319d760e9 | Before adoption / material source change
BBM-STD-56-INFORMATION_PROTOCOL-V0.1-FORMS-XLSX | V0.1 | BBM-STD-56-INFORMATION_PROTOCOL-V0.1-FORMS.xlsx | Draft | Commercial / appointed legal adviser | xlsx\BBM-STD-56-INFORMATION_PROTOCOL-V0.1-FORMS.xlsx | 6b39a5e44b80a6dd4ed857480e6467634a010e711184693aba55ac9fa855083d | Before adoption / material source change |  |  | BBM-STD-56
BBM-STD-56-INFORMATION_PROTOCOL-V0.1-DOCX | V0.1 | BBM-STD-56-INFORMATION_PROTOCOL-V0.1.docx | Draft | Commercial / appointed legal adviser | std-docx\BBM-STD-56-INFORMATION_PROTOCOL-V0.1.docx | 08d8c7e7610b63bab6ecdddaddceae0d6df22f17255c72c3e383a206c6719380 | Before adoption / material source change |  |  | BBM-STD-56
BBM-STD-57 | V0.1 | BBM-STD-57-CODES_AND_SUBMISSIONS-V0.1.md | Draft | Design director / authority liaison | Project\BBM-STD-57-CODES_AND_SUBMISSIONS-V0.1.md | f78b7f395384a83a23fb8094150790b29b19a5267b00365a42314535bd096491 | Before adoption / material source change
BBM-STD-57-CODES_AND_SUBMISSIONS-V0.1-FORMS-XLSX | V0.1 | BBM-STD-57-CODES_AND_SUBMISSIONS-V0.1-FORMS.xlsx | Draft | Design director / authority liaison | xlsx\BBM-STD-57-CODES_AND_SUBMISSIONS-V0.1-FORMS.xlsx | 653d434bd92cbf0496aea15626ec52bdcafe8c2f1067275ca73c14a6db08306c | Before adoption / material source change |  |  | BBM-STD-57
BBM-STD-57-CODES_AND_SUBMISSIONS-V0.1-DOCX | V0.1 | BBM-STD-57-CODES_AND_SUBMISSIONS-V0.1.docx | Draft | Design director / authority liaison | std-docx\BBM-STD-57-CODES_AND_SUBMISSIONS-V0.1.docx | 54eeb418593c38ad217835aa2bb15df64e676655441638848e6cf159bd6c58f1 | Before adoption / material source change |  |  | BBM-STD-57

## Allocations
ID | Title | State | Queue order
BBM-STD-51 | Registers | Draft available - not adopted | 1
BBM-STD-55 | Responsibilities | Draft available - not adopted | 2
BBM-STD-57 | Codes and submissions | Draft available - not adopted | 3
BBM-STD-52 | AIR | Draft available - not adopted | 4
BBM-STD-53 | PIR | Draft available - not adopted | 5
BBM-STD-54 | EIR and LOIN | Draft available - not adopted | 6
BBM-STD-56 | Information protocol | Draft available - not adopted | 7

## Dependencies
ConsumerID | Consumer revision | RequiredID | Required revision | Applicability | Decision or condition
BBM-STD-51 | V0.1 | BBM-STD-10 | V0.3 | External naming | Read BEP 8.3; draft approval pending
BBM-STD-51 | V0.1 | BBM-STD-50 | V0.2 | O3-POL-01 | Existing shared policy source; not moved
BBM-STD-55 | V0.1 | BBM-STD-51 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-57 | V0.1 | BBM-STD-51 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-57 | V0.1 | BBM-STD-55 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-52 | V0.1 | BBM-STD-51 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-52 | V0.1 | BBM-STD-55 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-52 | V0.1 | BBM-STD-57 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-53 | V0.1 | BBM-STD-51 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-53 | V0.1 | BBM-STD-55 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-53 | V0.1 | BBM-STD-57 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-54 | V0.1 | BBM-STD-51 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-54 | V0.1 | BBM-STD-52 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-54 | V0.1 | BBM-STD-53 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-54 | V0.1 | BBM-STD-55 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-56 | V0.1 | BBM-STD-51 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-56 | V0.1 | BBM-STD-54 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending
BBM-STD-56 | V0.1 | BBM-STD-55 | V0.1 | W1 writing-plan prerequisite | Available private draft; office/project adoption pending

## Adoptions
StandardID | Edition | Publication status | Scope | Clause pointer | Source URL | Verification date | Incorporation decision | Licensed access
ISO 19650-1 | 2018 | Published | Concepts | 5 | https://www.iso.org/standard/68078.html | 2026-10-16 | Draft office baseline | Actual reader entitlement required
ISO 19650-2 | 2018 | Published | Delivery | 5.1.4; 5.1.5 | https://www.iso.org/standard/68080.html | 2026-10-16 | Draft office baseline | Actual reader entitlement required
ISO 7817-1 | 2024 | Published | LOIN | Licensed clause verification pending | https://www.iso.org/standard/82914.html | 2026-10-16 | Current researched concepts baseline | Actual reader entitlement required
BS EN 17412-1 | 2020 | Withdrawn | Legacy contract only | Do not silently replace | https://standardsdevelopment.bsigroup.com/projects/2018-02659 | 2026-10-16 | Requires appointment change if adopted | No paid text reproduced

## Codes
Token | Code | Meaning | ProjectID | Authority | State
CLIENT | CLI | Fictional client token | SYN-P001 | Synthetic naming annex R01 | Synthetic
ORG | OFF | Fictional originator | SYN-P001 | Synthetic naming annex R01 | Synthetic
PROJ | P001 | Fictional project | SYN-P001 | Synthetic naming annex R01 | Synthetic
VOLUME | Z01 | Zone 01 | SYN-P001 | Synthetic naming annex R01 | Synthetic
VOLUME | ZZ | Whole scope | SYN-P001 | Synthetic naming annex R01 | Synthetic
LEVEL | L01 | Level 01 | SYN-P001 | Synthetic naming annex R01 | Synthetic
LEVEL | LRF | Roof | SYN-P001 | Synthetic naming annex R01 | Synthetic
LEVEL | ZZ | Whole scope | SYN-P001 | Synthetic naming annex R01 | Synthetic
TYPE | M3 | 3D model | SYN-P001 | Synthetic naming annex R01 | Synthetic
TYPE | DR | Drawing | SYN-P001 | Synthetic naming annex R01 | Synthetic
TYPE | SH | Schedule | SYN-P001 | Synthetic naming annex R01 | Synthetic
TYPE | RP | Report | SYN-P001 | Synthetic naming annex R01 | Synthetic
TYPE | DT | Dataset | SYN-P001 | Synthetic naming annex R01 | Synthetic
ROLE | A | Architecture | SYN-P001 | Synthetic naming annex R01 | Synthetic
ROLE | S | Structure | SYN-P001 | Synthetic naming annex R01 | Synthetic
ROLE | M | Mechanical | SYN-P001 | Synthetic naming annex R01 | Synthetic
ROLE | E | Electrical | SYN-P001 | Synthetic naming annex R01 | Synthetic
ROLE | P | Public health | SYN-P001 | Synthetic naming annex R01 | Synthetic
ROLE | F | Fire | SYN-P001 | Synthetic naming annex R01 | Synthetic
ROLE | L | Landscape | SYN-P001 | Synthetic naming annex R01 | Synthetic
ROLE | G | Survey | SYN-P001 | Synthetic naming annex R01 | Synthetic

## Container template
ContainerID | Revision | Suitability | CDE state | Permitted use | Source hash or manifest | Authoriser | Recipient decision

## Container example
ContainerID | Revision | Suitability | CDE state | Permitted use | Source hash or manifest | Authoriser | Recipient decision
CLI-OFF-P001-Z01-L01-M3-A-0001.ifc | R01 | SU-COORD | Shared | Coordination | SYN-MAN-01 not executed | SYN-LAP01 fictional | Not executed

## Rights template
EntitlementID | Kind | Item and licence version | Holder or account reference | Permitted use | Permitted recipients | Expiry date | Renewal date | Evidence URI | Owner | State

## Rights example
EntitlementID | Kind | Item and licence version | Holder or account reference | Permitted use | Permitted recipients | Expiry date | Renewal date | Evidence URI | Owner | State
ENT-SYN-01 | Software | Fictional modeller licence 1 | SYN-USER01 | Internal named-user modelling | Named holder only | 2027-10-01 | 2027-09-01 | SYN-RIGHTS-01 fictional | Rights steward | Unverified
ENT-SYN-02 | Content | Fictional family licence R01 | SYN-CONTENT01 | Evaluation only | Internal evaluator |  |  | SYN-RIGHTS-02 fictional | Rights steward | Unverified
ENT-SYN-03 | Standard | Licensed standard portal | SYN-READER01 | Authorised reader only | No PDF redistribution |  |  | SYN-RIGHTS-03 fictional | Standards custodian | Unverified

## Migration
ChangeID | Source or guide | Old reference | Proposed target | Impact | Owner | State | Evidence | Dependency revision | Compatibility review | Effective revision | Notifications | Retest evidence
W1-C01 | Manual 12.3 | Legacy five-token external wording | BEP V0.3 8.3 and O3-POL-01 | Use legacy as internal alias only | Manual owner | Pending owner revision | No issued file rewritten | V0.3 | Pending owner comparison of affected steps | Pending approval | Pending owner-approved recipient list | Not executed
W1-MIG-002 | BBM-STD-21-GUIDE-BIM_AND_REVIT_INITIATION-V0.2.md line 117 | BBM-STD-01-MANUAL-V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-003 | BBM-STD-22-GUIDE-WORK_SHARING_AND_COLLABORATION-V0.2.md line 139 | BBM-STD-01-MANUAL-V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-004 | BBM-STD-23-GUIDE-BRINGING_IN_CAD_CLEANLY_AND_COMPLEX_WALLS-V0.2.md line 114 | BBM-STD-01-MANUAL-V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-005 | BBM-STD-24-GUIDE-CURTAIN_WALLS_AND_CURTAIN_SYSTEMS-V0.2.md line 121 | BBM-STD-01-MANUAL-V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-006 | BBM-STD-25-GUIDE-PROJECT_INITIATION_WORKED_EXAMPLE-V0.2.md line 144 | BBM-STD-01-MANUAL-V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-007 | BBM-STD-26-GUIDE-INTRODUCTION_TO_FAMILIES_AND_PARAMETERS-V0.2.md line 136 | BBM-STD-01-MANUAL-V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-008 | BBM-STD-27-GUIDE-FAMILIES_AND_PARAMETERS_IN_PRACTICE-V0.2.md line 139 | BBM-STD-01-MANUAL-V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-009 | BBM-STD-28-GUIDE-DOCUMENTATION_OVERRIDES_VIEW_TEMPLATES_AND_FILTERS-V0.2.md line 130 | BBM-STD-01-MANUAL-V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-010 | BBM-STD-29-GUIDE-COMPLEX_GEOMETRY_PATTERN_BASED_AND_ADAPTIVE_FAMILIES_AND_QUICK_RENDERS-V0.2.md line 147 | BBM-STD-01-MANUAL-V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-011 | BBM-STD-30-GUIDE-SETTING_UP_A_BUILDING_FILE_URS_LEVELS_LINKS_AND_PLUG_INS-V0.2.md line 13 | BBM-STD-01 V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-012 | BBM-STD-30-GUIDE-SETTING_UP_A_BUILDING_FILE_URS_LEVELS_LINKS_AND_PLUG_INS-V0.2.md line 14 | BBM-STD-10 V0.2 | BBM-STD-10-BEP-V0.3.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.3 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-013 | BBM-STD-31-GUIDE-ENHANCED_WORKFLOW_DAILY_PROGRESS_CLEAN_DATA_AND_PRODUCTIVITY_PLUG_INS-V0.2.md line 13 | BBM-STD-01 V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-014 | BBM-STD-31-GUIDE-ENHANCED_WORKFLOW_DAILY_PROGRESS_CLEAN_DATA_AND_PRODUCTIVITY_PLUG_INS-V0.2.md line 13 | BBM-STD-10 V0.2 | BBM-STD-10-BEP-V0.3.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.3 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-015 | BBM-STD-32-GUIDE-ROOMS_AREAS_AND_MODEL_QUALITY_CONTROL-V0.2.md line 13 | BBM-STD-01 V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-016 | BBM-STD-32-GUIDE-ROOMS_AREAS_AND_MODEL_QUALITY_CONTROL-V0.2.md line 13 | BBM-STD-10 V0.2 | BBM-STD-10-BEP-V0.3.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.3 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-017 | BBM-STD-33-GUIDE-FINISHES_WITH_PLUG_INS_PHASES_AND_GETTING_READY_FOR_DESIGN-V0.2.md line 13 | BBM-STD-01 V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-018 | BBM-STD-33-GUIDE-FINISHES_WITH_PLUG_INS_PHASES_AND_GETTING_READY_FOR_DESIGN-V0.2.md line 13 | BBM-STD-10 V0.2 | BBM-STD-10-BEP-V0.3.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.3 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-019 | BBM-STD-34-GUIDE-RAILINGS_STAIRS_AND_RAMPS-V0.2.md line 13 | BBM-STD-01 V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-020 | BBM-STD-34-GUIDE-RAILINGS_STAIRS_AND_RAMPS-V0.2.md line 13 | BBM-STD-10 V0.2 | BBM-STD-10-BEP-V0.3.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.3 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-021 | BBM-STD-35-GUIDE-IMPORTING_FAMILIES_FROM_OUTSIDE-V0.2.md line 13 | BBM-STD-01 V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-022 | BBM-STD-35-GUIDE-IMPORTING_FAMILIES_FROM_OUTSIDE-V0.2.md line 13 | BBM-STD-10 V0.2 | BBM-STD-10-BEP-V0.3.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.3 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-023 | BBM-STD-36-GUIDE-DATA_CONTROL_WITH_SCHEDULES-V0.2.md line 13 | BBM-STD-01 V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-024 | BBM-STD-36-GUIDE-DATA_CONTROL_WITH_SCHEDULES-V0.2.md line 13 | BBM-STD-10 V0.2 | BBM-STD-10-BEP-V0.3.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.3 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-025 | BBM-STD-37-GUIDE-BUILDING_A_FAMILY_A_WORKED_EXAMPLE_A_CHAIR-V0.2.md line 13 | BBM-STD-01 V0.1 | BBM-STD-01-MANUAL-V0.2.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.2 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed
W1-MIG-026 | BBM-STD-37-GUIDE-BUILDING_A_FAMILY_A_WORKED_EXAMPLE_A_CHAIR-V0.2.md line 13 | BBM-STD-10 V0.2 | BBM-STD-10-BEP-V0.3.md | Compare affected steps against revised draft; preserve issued baseline | Guide owner | Pending owner revision | Observed source line; no migration executed | V0.3 | Pending scope/meaning comparison | Pending owner approval | Pending authorised recipient list | Not executed

## Test pack
CaseID | Input or condition | Expected | Check | Actual result | Evidence
N01 | CLI-OFF-P001-Z01-L01-M3-A-0001.ifc | Accept | Syntax plus dictionaries; authority still required | Not executed
N02 | CLI-OFF-P001-Z01-M3-A-0001.ifc | Reject | Missing level | Not executed
N03 | CLI-OFF-P001-Z01-L01-M3-A-001.ifc | Reject | Four-digit number | Not executed
N04 | CLI-OFF-P001-Z01-L01-M3-A-0001-R01.ifc | Reject | Revision is metadata | Not executed
N05 | CLI-OFF-P001-Z99-L01-M3-A-0001.ifc | Reject | Unregistered volume | Not executed
N06 | Same identity/revision, different hashes | Reject | Uncontrolled overwrite | Not executed
N07 | Declared .rvt/.ifc variants with common source | Accept | Manifest and schema/receiver checks | Not executed
N08 | New issue regresses R02 to R01 | Reject | Revision history | Not executed
N09 | SU-COORD used for fabrication | Hold | Permitted use | Not executed
D01 | Absent dependency ID | Reject | Foreign-key resolution | Not executed
D02 | Issued pin older than master | Hold | Assess migration; preserve issued pin | Not executed

## Index example
ID | Revision | Owner | State | Dependency IDs and revisions | Next review date | Approval evidence
STD-SYN-001 | R01 | SYN-STANDARDS01 | Synthetic | STD-SYN-002 R01 | 2027-10-16 | SYN-DEC-001 fictional
STD-SYN-002 | R01 | SYN-STANDARDS02 | Synthetic | None | 2027-10-16 | SYN-DEC-002 fictional

## Legacy map
Old component or literal | Current meaning | Applicability | ChangeID | Approver | Effective revision | Retained history URI | State
Project / Originator | PROJ / ORG | SYN-P001 fictional historical mapping | CH-SYN-001 | SYN-AP01 fictional | R02 fictional | SYN-HISTORY-01 fictional | Synthetic
Volume or system / Level or location | VOLUME / LEVEL with reviewed scope | SYN-P001 fictional historical mapping | CH-SYN-001 | SYN-AP01 fictional | R02 fictional | SYN-HISTORY-01 fictional | Synthetic
Type / Role / Number | TYPE / ROLE / NUMBER with code validation | SYN-P001 fictional historical mapping | CH-SYN-001 | SYN-AP01 fictional | R02 fictional | SYN-HISTORY-01 fictional | Synthetic
LEG-SYN-COORD | SU-COORD in fictional project only | SYN-P001 fictional historical mapping | CH-SYN-001 | SYN-AP01 fictional | R02 fictional | SYN-HISTORY-01 fictional | Synthetic
R01 | R01 retained; no renumbering | SYN-P001 fictional historical mapping | CH-SYN-001 | SYN-AP01 fictional | R02 fictional | SYN-HISTORY-01 fictional | Synthetic