## Read me
Field | Instruction
Document | BBM-STD-53-PIR-V0.1
State | Private WIP template for office review and adoption
Examples | SYN-P001 is fictional. All role IDs, dates and evidence tokens in examples are synthetic.
Use | Copy blank tables into the restricted project register. Replace synthetic particulars and obtain actual authority before activation.
Inputs | Amber blank rows are editable. Dropdowns are prompts; validate required fields and joins before release.
Authority | A cell is not an appointment, permit, signed licence or receiving-system test.
Revision | Template V0.1. Project records use Rnn with stable IDs, source revisions and ChangeID.
Note 1 | PIR-007 applies only to this fictional replacement project. OIR-007/AIR-007 identities and separate operator ownership remain intact.
Note 2 | All dates and dimensions are fictional; 600 mm withdrawal and bounded +/-10 mm are sourced to scenario records, not universal standards.
Note 3 | EIR-011 is a proposed delivery-coordination allocation to be established in BBM-STD-54. Current plan aliases remain unchanged; no existing MIDP/TIDP or BoD files are edited.
Note 4 | CH-SYN-PIR01 is an Open proposal; pending notice rows are not actual receipts. All receiving and decision results remain Not executed.
Baseline convention | CH-SYN-BASE01 identifies the initial fictional R01 fixture only; it is not an actual approved change. Extend filters/formatting when adding rows beyond the initial form.

## PIR blank
PIR_ID | Revision | ProjectID | DecisionID | Question | OIR_ID | Brief source | BoD criterion | Decision owner | Scope and exclusions | Required information | Quality and uncertainty | Source revisions | Delivery date | Decision date | Permitted reliance | Information acceptance route | EIR_ID | ExchangeID | MilestoneID | AIR interface | ChangeID | State

## PIR example
PIR_ID | Revision | ProjectID | DecisionID | Question | OIR_ID | Brief source | BoD criterion | Decision owner | Scope and exclusions | Required information | Quality and uncertainty | Source revisions | Delivery date | Decision date | Permitted reliance | Information acceptance route | EIR_ID | ExchangeID | MilestoneID | AIR interface | ChangeID | State
PIR-007 | R01 | SYN-P001 | DEC-SYN-007 | Can replacement layout proceed with required withdrawal access? | OIR-007 | BR-SYN-01 R01 | CR-SYN-MAINT01 / SYN-BOD-MAINT01 R01 | SYN-AP01 | AHU-001; VLV-001; VLV-002; excludes fabrication/operation/permit | Model, three-asset schedule, source/access note and manifest | 600 mm task envelope; lower bound >=600; bounded +/-10 mm fictional | SYN-REQ-A01 R01; SYN-MEASURE01 R01 | 2026-11-26 | 2026-12-02 | Next replacement-design step only | SYN-RR01 checks; SYN-AP01 accepts information separately from decision | EIR-011 | EX-SYN-03 | DEL-SYN-ME01 | AIR-007 remains operator-owned | CH-SYN-BASE01 | Draft

## Decisions blank
DecisionID | PIR_ID | Accountable owner | Information reviewer | Decision date | Review deadline | Stage end | Question | Accepted input versions | Information acceptance | Decision outcome | Evidence and conditions

## Decision example
DecisionID | PIR_ID | Accountable owner | Information reviewer | Decision date | Review deadline | Stage end | Question | Accepted input versions | Information acceptance | Decision outcome | Evidence and conditions
DEC-SYN-007 | PIR-007 | SYN-AP01 | SYN-RR01 | 2026-12-02 | 2026-12-01 | 2026-12-03 | Proceed to next replacement-design step? |  | Not executed | Not executed | Actual exact revisions/hashes, scoped conditions and signed decision pending

## Source criterion
CriterionID | BoD reference | Brief source | Quantified source | Requirement | Unit | Uncertainty method | Source owner | Applicability | Verification
CR-SYN-MAINT01 | SYN-BOD-MAINT01 R01 fictional local interface | BR-SYN-01 R01 | SYN-REQ-A01 R01 | 600 | mm | SYN-MEASURE01 R01 bounded +/-10 mm fictional | Synthetic mechanical design owner | Selected withdrawal task only; not code/office tolerance | Lower bound >=600; actual competent source confirmation pending

## Allocation blank
PIR_ID | EIR_ID | ExchangeID | MilestoneID | Product row | Source alias | Producer | Checker | Submission function | Recipient | Submit by | Review by | DecisionID | State

## Allocation example
PIR_ID | EIR_ID | ExchangeID | MilestoneID | Product row | Source alias | Producer | Checker | Submission function | Recipient | Submit by | Review by | DecisionID | State
PIR-007 | EIR-011 | EX-SYN-03 | DEL-SYN-ME01 | ME-01 | EIR-SYN-03-M01 / LOIN-SYN-ME01 | SYN-MA01 | SYN-MC01 | SYN-LAP01 | SYN-RR01 | 2026-11-26 | 2026-12-01 | DEC-SYN-007 | Proposed
PIR-007 | EIR-011 | EX-SYN-03 | DEL-SYN-ME02 | ME-02 | EIR-SYN-03-M02 / LOIN-SYN-ME02 | SYN-MA02 | SYN-MC02 | SYN-LAP01 | SYN-RR01 | 2026-11-26 | 2026-12-01 | DEC-SYN-007 | Proposed
PIR-007 | EIR-011 | EX-SYN-03 | DEL-SYN-ME03 | ME-03 | EIR-SYN-03-M03 / LOIN-SYN-ME03 | SYN-MA03 | SYN-MC03 | SYN-LAP01 | SYN-RR01 | 2026-11-26 | 2026-12-01 | DEC-SYN-007 | Proposed

## AIR boundary
PIR_ID | Project owner | AIR_ID | Asset owner | Shared objects | Project purpose | Operational purpose | Custody rule
PIR-007 | SYN-AP01 | AIR-007 | Asset-information lead/operator | AHU-001; VLV-001; VLV-002 | Replacement layout decision | Maintenance and replacement priorities | Project information does not update maintained AIM without operator acceptance

## Changes blank
ChangeID | PIR_ID | Current revision | Proposed revision | Proposal | Affected records | Decision owner | State

## Change example
ChangeID | PIR_ID | Current revision | Proposed revision | Proposal | Affected records | Decision owner | State
CH-SYN-PIR01 | PIR-007 | R01 | R02 | Proposed submit 2026-11-30; decision 2026-12-04 | EIR-011; BEP; TIDP ME-01/02/03; MIDP DEL-SYN-ME01; source/BoD impact review | SYN-AP01 | Open

## Notifications
ChangeID | Recipient | Affected record | Notice version | Receipt evidence | State
CH-SYN-PIR01 | SYN-LAP01 | EIR/BEP | Proposed R02; current baseline R01 |  | Pending
CH-SYN-PIR01 | SYN-MA01 | TIDP/MIDP | Proposed R02; current baseline R01 |  | Pending
CH-SYN-PIR01 | SYN-RR01 | Receiving date | Proposed R02; current baseline R01 |  | Pending
CH-SYN-PIR01 | Asset-information lead | AIR interface/source impact | Proposed R02; current baseline R01 |  | Pending

## Tests
TestID | Input | Expected | Method | Actual result
PIR-T01 | 650 mm; +/-10 mm; requirement600 | Lower640 >=600; criterion arithmetic passes | 650-10=640; actual model/source/receiving checks still needed | Not executed
PIR-T02 | 605 mm; +/-10 mm; requirement600 | Lower595 <600; criterion fails | 605-10=595 | Not executed
PIR-T03 | 650 mm; uncertainty missing | Hold | No implicit zero uncertainty | Not executed
PIR-T04 | Duplicate PIR-007 or absent SYN-AP01 | Reject | Unique ID and exactly one accountable owner | Not executed
PIR-T05 | Submit2026-12-03 for decision2026-12-02 | Reject | Delivery/review precede decision | Not executed
PIR-T06 | Mandatory EIR_ID absent or wrong criterion | Hold | Resolve PIR/source/criterion/EIR/exchange/milestone joins | Not executed
PIR-T07 | Model/schedule three IDs match; current note and source accessible to SYN-RR01 | Accept information only after all required checks | Record exact versions/hashes and recipient evidence; owner decides separately | Not executed