## Read me
Field | Instruction
Document | BBM-STD-55-RESPONSIBILITIES-V0.1
State | Private WIP template for office review and adoption
Examples | SYN-P001 is fictional. All role IDs, dates and evidence tokens in examples are synthetic.
Use | Copy blank tables into the restricted project register. Replace synthetic particulars and obtain actual authority before activation.
Inputs | Amber blank rows are editable. Dropdowns are prompts; validate required fields and joins before release.
Authority | A cell is not an appointment, permit, signed licence or receiving-system test.
Revision | Template V0.1. Project records use Rnn with stable IDs, source revisions and ChangeID.
Note 1 | Baseline: BBM-STD-10 V0.3 section 6.2/6.2.1; BBM-STD-03 V0.2; BBM-STD-51 V0.1; existing BBM-STD-MIDP/TIDP V0.2.
Note 2 | Production example preserves PR-SYN-ME01/02/03, DEL-SYN-ME01/02/03 and EX-SYN-03 from the existing synthetic delivery plans. No actual appointment is claimed.
Note 3 | Every active RACI row needs exactly one A or A/R and at least one R or A/R. Every delivery needs distinct author/checker, scoped authoriser/recipient and actual capacity.
Note 4 | Sources: ISO 19650-2:2018 catalogue https://www.iso.org/standard/68080.html; UK BIM Framework Guidance A ed.2 and E ed.2 (February 2021), URLs in Markdown References.

## Chart blank
FunctionID | Function | Reports to FunctionID | Scope | Deputy FunctionID | Escalation FunctionID | Private holder record

## Chart example
FunctionID | Function | Reports to FunctionID | Scope | Deputy FunctionID | Escalation FunctionID | Private holder record
FN-SYN-DIR | Practice director |  | Office adoption | FN-SYN-DDIR | FN-SYN-DIR | SYN-DIRECTORY fictional
FN-SYN-BIM | BIM Manager | FN-SYN-DIR | Office information standards | FN-SYN-DBIM | FN-SYN-DIR | SYN-DIRECTORY fictional
FN-SYN-ME | Mechanical lead | FN-SYN-DIR | Mechanical discipline | FN-SYN-DME | FN-SYN-DIR | SYN-DIRECTORY fictional
FN-SYN-DDIR | Director deputy | FN-SYN-DIR | Scoped acting cover |  | FN-SYN-DIR | SYN-DIRECTORY fictional
FN-SYN-DBIM | BIM deputy | FN-SYN-BIM | Scoped standards cover |  | FN-SYN-DIR | SYN-DIRECTORY fictional
FN-SYN-DME | Mechanical deputy | FN-SYN-ME | Scoped mechanical cover |  | FN-SYN-DIR | SYN-DIRECTORY fictional
FN-SYN-AP | Appointing-party receiving function |  | External project function; not office reporting |  | FN-SYN-AP | SYN-DIRECTORY fictional
FN-SYN-AUTHOR | Mechanical author | FN-SYN-ME | Production only |  | FN-SYN-ME | SYN-DIRECTORY fictional
FN-SYN-CHECK | Mechanical checker | FN-SYN-ME | Independent checking |  | FN-SYN-ME | SYN-DIRECTORY fictional

## Assignments blank
RoleID | FunctionID | Party and appointment | Private holder ID | Deputy ID | Decision scope | Delegation evidence | Effective from | Effective to | Competence evidence | Capacity record | State

## Assignments example
RoleID | FunctionID | Party and appointment | Private holder ID | Deputy ID | Decision scope | Delegation evidence | Effective from | Effective to | Competence evidence | Capacity record | State
SYN-LAP01 | FN-SYN-BIM | SYN-APP01 | SYN-H01 | SYN-DH01 | Delivery lead: requirements preparation and scoped submission authorisation | SYN-DEL01 fictional | 2026-10-16 | 2027-10-16 | SYN-COMP01 fictional | SYN-CAP01 fictional | Draft
SYN-RR01 | FN-SYN-AP | SYN-APP01 | SYN-H02 | SYN-DH02 | Receiving review; AP retains A | Actual delegation pending | 2026-10-16 | 2027-10-16 | SYN-COMP02 fictional | SYN-CAP02 fictional | Draft
SYN-CO01 | FN-SYN-BIM | SYN-APP01 | SYN-H03 | SYN-DH03 | Scope defined by Production example | Fictional appointment only | 2026-10-16 | 2027-10-16 | SYN-COMP03 fictional | SYN-CAP03 fictional | Draft
SYN-MA01 | FN-SYN-AUTHOR | SYN-APP01 | SYN-H04 | SYN-DH04 | Scope defined by Production example | Fictional appointment only | 2026-10-16 | 2027-10-16 | SYN-COMP04 fictional | SYN-CAP04 fictional | Draft
SYN-MC01 | FN-SYN-CHECK | SYN-APP01 | SYN-H05 | SYN-DH05 | Scope defined by Production example | Fictional appointment only | 2026-10-16 | 2027-10-16 | SYN-COMP05 fictional | SYN-CAP05 fictional | Draft
SYN-MA02 | FN-SYN-AUTHOR | SYN-APP01 | SYN-H06 | SYN-DH06 | Scope defined by Production example | Fictional appointment only | 2026-10-16 | 2027-10-16 | SYN-COMP06 fictional | SYN-CAP06 fictional | Draft
SYN-MC02 | FN-SYN-CHECK | SYN-APP01 | SYN-H07 | SYN-DH07 | Scope defined by Production example | Fictional appointment only | 2026-10-16 | 2027-10-16 | SYN-COMP07 fictional | SYN-CAP07 fictional | Draft
SYN-MA03 | FN-SYN-AUTHOR | SYN-APP01 | SYN-H08 | SYN-DH08 | Scope defined by Production example | Fictional appointment only | 2026-10-16 | 2027-10-16 | SYN-COMP08 fictional | SYN-CAP08 fictional | Draft
SYN-MC03 | FN-SYN-CHECK | SYN-APP01 | SYN-H09 | SYN-DH09 | Scope defined by Production example | Fictional appointment only | 2026-10-16 | 2027-10-16 | SYN-COMP09 fictional | SYN-CAP09 fictional | Draft
SYN-AP01 | FN-SYN-AP | SYN-APP01 | SYN-H10 | Private Directory deputy reference | AP accountable requirements and acceptance | Fictional only | 2026-10-16 | 2027-10-16 | SYN-COMP-SYN-AP01 | W-SYN-01 | Draft
SYN-TT01 | FN-SYN-ME | SYN-APP01 | SYN-H11 | Private Directory deputy reference | Task lead production commitments | Fictional only | 2026-10-16 | 2027-10-16 | SYN-COMP-SYN-TT01 | W-SYN-01 | Draft
SYN-IM01 | FN-SYN-BIM | SYN-APP01 | SYN-H01 | Private Directory deputy reference | Information planning; combined with LAP subject to review | Fictional only | 2026-10-16 | 2027-10-16 | SYN-COMP-SYN-IM01 | W-SYN-01 | Draft

## RACI blank
ActivityID | Activity | AP | LAP | TT | IM | P | RR | Appointment scope | Authority evidence

## RACI example
ActivityID | Activity | AP | LAP | TT | IM | P | RR | Appointment scope | Authority evidence
ACT-SYN-01 | Establish project requirements | A | R | C | C | I | C | Upstream appointment SYN-APP01 | Fictional only
ACT-SYN-02 | Prepare TIDP | I | C | A | C | R | I | Task team SYN-ME | Fictional only
ACT-SYN-03 | Authorise submission | I | A/R | R | C | I | C | SYN-LAP01 defined delivery scope | Fictional only
ACT-SYN-04 | Accept exchange | A | C | I | C | I | R | AP retains A; RR performs review | No actual delegation

## Production blank
ProductionID | Requirement alias | Objects | Discipline | Use | Milestone | ExchangeID | DeliveryID | ContainerID | Task team | Author | Checker | Coordinator | Authoriser | Recipient | Authority scope evidence | TIDP row | MIDP baseline | Input dependencies | Required hours | Available hours | Calendar and window

## Production example
ProductionID | Requirement alias | Objects | Discipline | Use | Milestone | ExchangeID | DeliveryID | ContainerID | Task team | Author | Checker | Coordinator | Authoriser | Recipient | Authority scope evidence | TIDP row | MIDP baseline | Input dependencies | Required hours | Available hours | Calendar and window
PR-SYN-ME01 | EIR-SYN-03-M01 | AHU-001; VLV-001; VLV-002 | Mechanical | Coordination | Spatial coordination | EX-SYN-03 | DEL-SYN-ME01 | CLI-OFF-P001-Z01-L01-M3-M-0001 | SYN-ME | SYN-MA01 | SYN-MC01 | SYN-CO01 | SYN-LAP01 | SYN-RR01 | SYN-APP01 fictional; actual scope pending | ME-01 | MIDP-SYN-01 R02; CH-SYN-003 fictional | See existing synthetic TIDP row | 16 | 16 | W-SYN-01 2026-11-04 to 2026-12-01; see per-holder totals
PR-SYN-ME02 | EIR-SYN-03-M02 | AHU-001; VLV-001; VLV-002 | Mechanical | Equipment data | Spatial coordination | EX-SYN-03 | DEL-SYN-ME02 | CLI-OFF-P001-Z01-L01-SH-M-0002 | SYN-ME | SYN-MA02 | SYN-MC02 | SYN-CO01 | SYN-LAP01 | SYN-RR01 | SYN-APP01 fictional; actual scope pending | ME-02 | MIDP-SYN-01 R02; CH-SYN-003 fictional | See existing synthetic TIDP row | 16 | 32 | W-SYN-01 2026-11-04 to 2026-12-01; see per-holder totals
PR-SYN-ME03 | EIR-SYN-03-M03 | AHU-001; VLV-001; VLV-002 | Mechanical | Design/access note | Spatial coordination | EX-SYN-03 | DEL-SYN-ME03 | CLI-OFF-P001-Z01-L01-RP-M-0003 | SYN-ME | SYN-MA03 | SYN-MC03 | SYN-CO01 | SYN-LAP01 | SYN-RR01 | SYN-APP01 fictional; actual scope pending | ME-03 | MIDP-SYN-01 R02; CH-SYN-003 fictional | See existing synthetic TIDP row | 16 | 16 | W-SYN-01 2026-11-04 to 2026-12-01; see per-holder totals

## Conflict cases
CaseID | Defect | Expected finding | Correction | ChangeID | Closure evidence | State
CF-SYN-01 | PR-SYN-ME01 no checker; two producing teams | Orphan checker and duplicate scope | One producing team; SYN-MC01 independent checker | CH-SYN-001 | Corrected scope; appointment; competence; plan notices | Synthetic corrected
CF-SYN-02 | AP=A and RR=A; no R or A/R in adverse acceptance row | Duplicate A and missing responsible performer | Keep AP A; assign RR R until an actual scoped delegation changes accountability | CH-SYN-002 | Delegation and single-A row | Synthetic corrected
CF-SYN-03 | 24 committed hours; 16 available | 8-hour capacity gap | Selected: reassign 8-hour non-delivery duty from SYN-MA01 to SYN-MA02 | CH-SYN-003 | Change example CH-SYN-003; Capacity allocations and Capacity totals R02 | Synthetic corrected

## Change blank
ChangeID | Old matrix revision | New matrix revision | Affected scope | Duty and capacity impact | Decision authority | Decision evidence | BEP reference | TIDP reference | MIDP reference | Notified recipients | Acknowledgments

## Function crosswalk
RACI column | RoleID or selection rule | Holder or selection rule | Appointment scope | Conflict review
AP | SYN-AP01 | SYN-H10 | SYN-APP01 upstream | COMB-SYN-01 oversight
LAP | SYN-LAP01 | SYN-H01 | Requirements preparation and scoped submission authorisation; no AP decision power | COMB-SYN-01
TT | SYN-TT01 | SYN-H11 | SYN-ME production commitments | Distinct from producer
IM | SYN-IM01 | SYN-H01 | Information planning | COMB-SYN-01
P | Production example Author by ProductionID | Assignments private holder of selected Author | Per-delivery production only | Distinct checker for same scope
RR | SYN-RR01 | SYN-H02 | Receiving review; AP retains A | No actual delegation

## Combined roles blank
ReviewID | Combined roles | Holder | Conflict | Independent reviewer | Oversight decision owner | Controls | Evidence | State

## Combined roles
ReviewID | Combined roles | Holder | Conflict | Independent reviewer | Oversight decision owner | Controls | Evidence | State
COMB-SYN-01 | SYN-LAP01 and SYN-IM01 | SYN-H01 | Planner also authorises delivery-team submission | SYN-MC03 | SYN-AP01 | Independent technical checks; AP oversight; no self-check of authored scope | SYN-CRV01 fictional scoped decision | Reviewed

## Adverse production
ProductionID | Producing team | Author | Checker | State
PR-SYN-ME01 | SYN-ME | SYN-MA01 |  | Adverse
PR-SYN-ME01 | SYN-ALT | SYN-MA01 |  | Adverse

## Adverse RACI
ActivityID | AP | LAP | TT | IM | P | RR | State
ACT-SYN-04 | A | C | I | C | I | A | Adverse

## Adverse capacity
Holder | WindowID | Required hours | Available hours | Shortfall hours
SYN-H04 | W-SYN-01 | 24 | 16 | 8

## Capacity allocations
AllocationID | RoleID | Holder | WindowID | From | To | Duty or delivery | Required hours | Baseline
CAP-SYN-01 | SYN-MA01 | SYN-H04 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME01 | 16 | CH-SYN-003 R02
CAP-SYN-02 | SYN-MC01 | SYN-H05 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME01 | 4 | CH-SYN-003 R02
CAP-SYN-03 | SYN-CO01 | SYN-H03 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME01 | 2 | CH-SYN-003 R02
CAP-SYN-04 | SYN-LAP01 | SYN-H01 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME01 | 1 | CH-SYN-003 R02
CAP-SYN-05 | SYN-RR01 | SYN-H02 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME01 | 2 | CH-SYN-003 R02
CAP-SYN-06 | SYN-MA02 | SYN-H06 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME02 | 16 | CH-SYN-003 R02
CAP-SYN-07 | SYN-MC02 | SYN-H07 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME02 | 4 | CH-SYN-003 R02
CAP-SYN-08 | SYN-CO01 | SYN-H03 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME02 | 2 | CH-SYN-003 R02
CAP-SYN-09 | SYN-LAP01 | SYN-H01 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME02 | 1 | CH-SYN-003 R02
CAP-SYN-10 | SYN-RR01 | SYN-H02 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME02 | 2 | CH-SYN-003 R02
CAP-SYN-11 | SYN-MA03 | SYN-H08 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME03 | 16 | CH-SYN-003 R02
CAP-SYN-12 | SYN-MC03 | SYN-H09 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME03 | 4 | CH-SYN-003 R02
CAP-SYN-13 | SYN-CO01 | SYN-H03 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME03 | 2 | CH-SYN-003 R02
CAP-SYN-14 | SYN-LAP01 | SYN-H01 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME03 | 1 | CH-SYN-003 R02
CAP-SYN-15 | SYN-RR01 | SYN-H02 | W-SYN-01 | 2026-11-04 | 2026-12-01 | DEL-SYN-ME03 | 2 | CH-SYN-003 R02
CAP-SYN-16 | SYN-MA02 | SYN-H06 | W-SYN-01 | 2026-11-04 | 2026-12-01 | Non-delivery duty moved from SYN-MA01 | 8 | CH-SYN-003 R02
CAP-SYN-17 | SYN-IM01 | SYN-H01 | W-SYN-01 | 2026-11-04 | 2026-12-01 | Information planning | 4 | CH-SYN-003 R02
CAP-SYN-18 | SYN-AP01 | SYN-H10 | W-SYN-01 | 2026-11-04 | 2026-12-01 | AP oversight/decision | 4 | CH-SYN-003 R02
CAP-SYN-19 | SYN-TT01 | SYN-H11 | W-SYN-01 | 2026-11-04 | 2026-12-01 | Task-lead planning | 4 | CH-SYN-003 R02

## Capacity totals
Holder | WindowID | Required hours | Available hours | Remaining hours | Snapshot evidence
SYN-H01 | W-SYN-01 | 7 | 16 | 9 | Manual sum of all Capacity allocations rows; CH-SYN-003 R02
SYN-H02 | W-SYN-01 | 6 | 16 | 10 | Manual sum of all Capacity allocations rows; CH-SYN-003 R02
SYN-H03 | W-SYN-01 | 6 | 16 | 10 | Manual sum of all Capacity allocations rows; CH-SYN-003 R02
SYN-H04 | W-SYN-01 | 16 | 16 | 0 | Manual sum of all Capacity allocations rows; CH-SYN-003 R02
SYN-H05 | W-SYN-01 | 4 | 16 | 12 | Manual sum of all Capacity allocations rows; CH-SYN-003 R02
SYN-H06 | W-SYN-01 | 24 | 32 | 8 | Manual sum of all Capacity allocations rows; CH-SYN-003 R02
SYN-H07 | W-SYN-01 | 4 | 16 | 12 | Manual sum of all Capacity allocations rows; CH-SYN-003 R02
SYN-H08 | W-SYN-01 | 16 | 16 | 0 | Manual sum of all Capacity allocations rows; CH-SYN-003 R02
SYN-H09 | W-SYN-01 | 4 | 16 | 12 | Manual sum of all Capacity allocations rows; CH-SYN-003 R02
SYN-H10 | W-SYN-01 | 4 | 16 | 12 | Manual sum of all Capacity allocations rows; CH-SYN-003 R02
SYN-H11 | W-SYN-01 | 4 | 16 | 12 | Manual sum of all Capacity allocations rows; CH-SYN-003 R02

## Change example
ChangeID | Old matrix revision | New matrix revision | Selected correction | Authority | Decision evidence | BEP reference | TIDP reference | MIDP reference | Notified recipients | Acknowledgments | State
CH-SYN-003 | R01 | R02 | Reassign 8-hour non-delivery duty from SYN-MA01 to SYN-MA02 | SYN-AP01 fictional programme authority | SYN-DEC003 fictional | BEP-SYN-01 R02 | TIDP-SYN-ME R02 | MIDP-SYN-01 R02 | SYN-MA01; SYN-MA02; SYN-TT01; SYN-LAP01; affected reviewers | SYN-ACK003 fictional all listed recipients | Synthetic corrected