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1 Purpose and source ownership
Determine the actual project jurisdiction and applicable instruments before setting design criteria or releasing a submission. Maintain one code/applicability register and one linked submission/dependency register. This pack covers SG-022 and SG-023. The design director owns the applicability decision with competent specialists; the authority liaison maintains service/checklist evidence. No library entry, BIM model or information-acceptance record is a permit.
Use BBM-STD-51 §3 as the one edition register (O-DEC-111), rights and controlled identity, BBM-STD-85 for UAE authority requirement detail and submission steps, and BBM-STD-55 for scoped appointments, including the consultant of record and authority portal submitter. The editable registers provide blank tables, a fictional SYN-P001 example, change records and adverse release cases. Actual site, appointments, code clauses and authority confirmations are project activation inputs.
The shared codes library index is READ-ONLY. Its current location is held once, as the codes-library asset row in the BBM-STD-51 Master index; at 4 November 2026 the path is BABOOM-BIM-STANDARD\02-LIBRARIES\04-REFERENCES\00-CODES-AND-REGULATIONS\CODES-INDEX.csv (share folders renamed 2026-11-04). Cite the register row, not a hard-coded path. Link to its row, edition and evidence; do not create a competing library index or write to the share. Its header and first DMT building/energy-code records were read on 16 October 2026. A downloaded file and recorded hash prove library identity, not current legal adoption or site applicability.
2 Project jurisdiction and applicability
	Record
	Required project entry

	Project and land
	ProjectID, plot/​site-plan ID and revision, emirate, municipality, master-development/​free-zone boundary and permitted use

	Authorities
	Planning/​building-permit authority, fire authority, infrastructure/​service/​NOC authorities and competent liaison functions

	Scope
	New/​existing/​alteration/​fit-out/​infrastructure, occupancy, phases, appointment discipline scope and relevant exclusions

	Instruments
	Applicable law, planning conditions, building/​fire/​accessibility/​environmental codes, rating/​permit instruments and actual adoption basis

	Evidence
	Controlled official source, edition, clause, effective date, applicability reasoning, specialist decision, verification date and clarification status



The InstrumentID is the BBM-STD-51 §3 register ID (for example ED-DBC); this register does not keep its own edition list (O-DEC-111). The Codes table records InstrumentID, jurisdiction/authority, title/edition, clause or service-checklist item, scope, effective and verification dates, official source URL, library row/path/hash where available, specialist, approval/clarification status and affected BoD criterion/submission IDs. Unknown applicability stays Unverified. Record a reason and authority for N/A; silence does not mean exemption. National/international publications, local adoption instruments and project planning conditions are separate records.
	Instrument (BBM-STD-51 ID)
	Edition fact (from the register)
	Applies to
	Detail

	ED-DBC
	Dubai Building Code (Decree 45/​2021) as amended by DM Administrative Resolution No. 225 of 2024 (13 Aug 2024); apply the DBC plus all DM amending resolutions in force at permit submission
	Dubai buildings under DM permitting; BoD criteria citing the DBC link here
	BBM-STD-85

	ED-DXB-LAW-3-2026
	Dubai Law No. 3 of 2026 on the Quality and Safety of Buildings (emirate law), issued 27 Feb 2026, in force 60 days after Official Gazette publication
	Existing Dubai buildings: Quality & Safety Certificate after 20 years from completion, valid 10 years (5 years if 40+ years); an asset-life obligation, not a design-permit rule
	BBM-STD-75, 76, 85

	ED-DM-11-9-1
	DM circular (11-9-1) of 2026, 1 Oct 2026, applying ED-DXB-LAW-3-2026, with guidance manual 11-9-1-1 (May 2026)
	Existing Dubai buildings 20 or more years from completion, on DM notice: Building Quality and Safety Certificate after an appointed engineering office's assessment against the DM technical checklist; valid 10 years (under 40 years) or 5 years (40+); renewal in the last 90 days before expiry
	BBM-STD-75 §7, BBM-STD-85 §4

	ED-UAE-FLS
	UAE Fire & Life Safety Code of Practice, September 2018 edition, plus the emirate authority's amendments current at project start, recorded in the BEP
	All UAE projects; Fire_Rating per O-DEC-119
	BBM-STD-85

	ED-ADIBC
	The ADIBC edition published by DMT and in force at project start (2013 edition at 2026-11-04)
	Abu Dhabi buildings
	BBM-STD-85

	ED-ESTIDAMA
	Estidama Pearl: private projects minimum 1 Pearl; government-funded minimum 2 Pearl
	Abu Dhabi building permits
	BBM-STD-81, 85

	ED-ALSAFAT
	Al Sa'fat 2nd edition (Jan 2023): Silver Sa'fa mandatory for all new buildings in Dubai
	Dubai new buildings
	BBM-STD-81, 85



The rating rows are statutory minimums, not optional targets. Record the required level, submission stage and evidence for each in the project register; the higher of the statutory minimum and any client target applies.
Applicable law and binding authority conditions cannot be waived by a client instruction or office standard. Contractual hierarchy is recorded by the actual commercial/legal owner. A technical team escalates conflicting instruments or an uncertain transition to the competent specialist/authority; it does not choose the more convenient edition. Preserve the previous project baseline and exact clarification receipt.
3 Separate UAE authority profiles
	Profile
	Researched source boundary
	Project decision still required

	Dubai Municipality /​ DM
	BIM instruments (BBM-STD-51): circulars 196 (2013) and 207 (2015), historical (ED-DM-196-207); 9-1-1 of 2021 on applying BIM (ED-DM-9-1-1); 9-1-2 of 13 Oct 2023 (ED-DM-9-1-2): Open BIM per the Dubai BIM Standard from 1 Jan 2024 above 20 floors (ARC) /​ 40 floors (STR), 20,000 m² (ARC) /​ 30,000 m² (STR), specialised buildings and government projects; 9-1-3 of 15 Jan 2026, effective 1 Apr 2026 (ED-DM-9-1-3): ARC + STR BIM with the permit for new buildings above G+12 or 15,000 m² or more, listed alterations (add/​remove floors, +1,500 m² or more, full redesign, change of main use, relocation on plot) with the application, other alterations final BIM before the completion certificate; drawings extracted from the model
	Threshold test record: storeys, built area, alteration type, building use → BIM permit Yes/​No with instrument IDs. Profile = the IFC schema, export setup and attribute matrix stated in the current Dubai BIM Standard (ED-DUBAI-BIM-STD), checked at project start and recorded in the BEP; openBIM IFC, zipped, within the portal upload limit; portal validation evidence retained. Exchange profile SYN-X-AUTH in BBM-STD-54; steps in BBM-STD-85

	Abu Dhabi DMT /​ ADM
	ADM BIM Code of Practice (Oct 2020; cover v1, headers v1.1), BIM Documentation Guidelines for Infrastructure v1.0 (Oct 2020) and Infrastructure BIM Object Catalogue v2.0 (May 2021) (ED-ADM-BIM); ADIBC (ED-ADIBC). The guidelines and catalogue are infrastructure documents
	Establish whether the appointment/​project adopts them; do not apply them automatically to every building or other emirate. Record the CoP cover/​header revision discrepancy. No universal Abu Dhabi building-permit BIM threshold has been established

	Abu Dhabi building permits /​ BINAA
	DMT officially reports the BINAA construction-permitting platform and BIM/​AI integration
	Confirm the actual current municipality service, project route, checklist, model/​schema and receiving capability; no universal building BIM threshold is inferred

	Dubai Development Authority /​ DDA
	Current Final Design Approval service places final design approval before building permit and lists project-specific supporting material; DDA Circular 400 Drawings Submission Standards, 29 Sep 2021 (ED-DDA-CIRC-400) sets A1 DWF, monochrome and discipline-tab/​sheet-naming conventions
	Verify DDA jurisdiction/​site plan, the current service/​circulars and conditional NOCs; where the current service checklist differs from Circular 400, the checklist governs. Do not substitute a DM or ADM profile

	Fit-out routes (DDA, DM, Civil Defence, Abu Dhabi)
	Per project: each authority's current fit-out service; titles not confirmed from a primary source
	Record authority, fit-out service URL, checklist revision and verification date per route before use (BBM-STD-62 §5 route table)

	UAE Civil Defence /​ FLS
	UAE Fire & Life Safety Code of Practice, September 2018 edition (ED-UAE-FLS), plus emirate authority amendments current at project start
	Approved fire consultant route, fire NOC dependency (DEP-…F), applicable amendments recorded in the BEP, verification date

	Security systems (Dubai SIRA)
	ED-SIRA: no primary source confirmed
	Security-system drawings follow the current SIRA/​DM requirement for the plot, confirmed at permit stage; classified per BBM-STD-87

	Other free-zone authorities
	Per project
	Record authority, current service URL, profile and verification date before use; do not substitute another authority's profile

	Utilities (e.g. DEWA, ADDC, AADC)
	Per project (ED-UTILITY-REGS)
	Record utility, NOC service URL, profile and verification date; NOC dependency rows in section 4

	Roads and transport authority
	Per project
	Record authority, NOC service URL, profile and verification date



The live DDA Final Design Approval page identifies architectural/structural/mechanical drawings, appointment evidence and technical supporting material, with conditional utility, traffic, fire and other NOCs. The workbook records these as a candidate package profile, not a universal nationwide checklist. Older static service cards differ from the current page; retain their dates and seek confirmation rather than merge them into an invented mandatory list. No authority processing duration, charge or project threshold is assumed here.
4 Stage and submission dependency map
SubmissionIDs use the series SUB-<project>-<route><nn> (e.g. SUB-SYN-PER), the AuthoritySubmissionID the MIDP Exchanges table carries. Track each design approval, construction permission, inspection, connection, completion and occupancy decision as its own record, with authority/service, prerequisites, exact revisions, confirmed review-cycle source and gate (O-DEC-127). Maintain StageID, SubmissionID, InstrumentIDs, exact authority/service/profile revision, prerequisites, content list, NOC dependencies, producing/checking/authorising party, actual dates, receipt, comments, conditions, expiry and closure evidence. Separate planned, submitted, approved, conditionally approved, rejected and expired states, plus Unverified for an unconfirmed requirement; this set is canonical (O-DEC-110, O-DEC-140) and is listed once in BBM-STD-93 §7. "Not applicable" is an applicability decision and "Superseded" a record flag, not states. Store the real decision and its scope; an upload receipt proves submission only.
	Gate
	Candidate contents and prerequisites
	Release decision

	Concept /​ planning
	Current plot/​site plan, permitted-use/​planning baseline, design brief/​options and the authority's actual concept service requirements
	Project authority liaison verifies the route and concept decision; stage name alone is not consent

	Permit /​ final design
	Required drawings/​models/​calculations and reports, including the BIM model where ED-DM-9-1-2 /​ ED-DM-9-1-3 apply (drawings extracted from the model); scoped consultant appointments; current service checklist; applicable NOCs and prior design approvals
	All applicable prerequisite conditions and package-profile checks complete; statutory decision remains with authority

	Construction activity
	Valid permit for the exact activity/​phase, approved design revision, specialist/​deferred submissions, inspection/​NOC requirements and conditions
	Competent project owner confirms permission for this activity; a permit for another scope is insufficient

	Completion /​ operation
	Required inspections, as-built/​record information (final BIM before the completion certificate where ED-DM-9-1-3 requires it), tests/​certificates, service clearances and closed conditions under the actual service; Civil Defence /​ FLS records per the record group in BBM-STD-75 §4 and the authority route in BBM-STD-85 §5
	Confirm actual completion/​occupation permissions; information handover acceptance does not confer occupation permission



These four office gate labels are mapping categories: the authority-gate family, mapped against the office stage gates (Manual §2.1) and the BoD gates G0–G5 (BBM-STD-12) in BBM-STD-93 (O-DEC-109). The approval state set in this section and §2 is the canonical approval status vocabulary; BBM-STD-12 C4 maps to it through BBM-STD-93 (O-DEC-110). They do not prescribe a nationwide statutory sequence or equate RIBA stages with permits. RIBA 0–7 remains the planning context in BBM-STD-12. Each authority's actual sequence and conditional dependencies take precedence.
4.1 Fictional dependency example
SYN-P001 is hypothetically inside DDA jurisdiction. Plot SYN-PLOT-001 and every candidate profile require confirmation. The selected fictional route is SUB-SYN-CON01 concept, then SUB-SYN-FD01 Final Design Approval, then SUB-SYN-PER01 building permit, then SUB-SYN-CONST01 scoped construction activity and SUB-SYN-COMP01 completion/operation permission. Final Design Approval is a design decision and never the building permit. Each record has its own candidate ProfileID and stage-specific MIDP row. None is submitted or approved; the concept predecessor is a scenario assumption requiring project-route confirmation.
	DependencyID
	Fictional prerequisite
	Owner and effect

	DEP-SYN-00 /​ DEP-SYN-01
	Concept decision and verified site-plan validity before SUB-SYN-FD01
	Authority liaison; affected submission Hold while unknown

	DEP-SYN-02F /​ DEP-SYN-02U
	Fire-design and utility NOC applicability/​receipt for SUB-SYN-FD01
	Separate fire lead and utility liaison owners; conditional applicability requires evidence

	DEP-SYN-05 /​ DEP-SYN-06
	Actual Final Design Approval decision plus verified building-permit profile/​prerequisites before SUB-SYN-PER01
	Authority liaison; the current building-permit service/​profile remains unconfirmed

	DEP-SYN-03
	SUB-SYN-PER01 valid permit and conditions for SUB-SYN-CONST01
	Authorised construction decision owner; information acceptance cannot close this dependency

	DEP-SYN-04
	Required inspections/​certificates and conditions for SUB-SYN-COMP01
	Completion liaison; record actual decision and permitted use separately



The example identifies dependency ownership without inventing an actual permit, statutory code value or authority assurance. Record the applicable profile's model format/schema, coordinate basis (BBM-STD-86 register key), property/checklist scope, drawing/signature requirements, any Arabic-language text requirement stated in the authority's current checklist (none is assumed; text rules in BBM-STD-66 §3), uploader eligibility and portal validation evidence before release. A filename extension is not a submission profile.
5 BoD criteria and information exchanges
BBM-STD-12 Basis of Design Report and its approval/criteria workbook retain the design-criterion and approval-tracker ownership. Do not copy their criterion values into a second technical source. This register controls applicability/source and submission profiles; the project BoD/workbook controls the linked criterion value, unit, method and evidence. Both records carry the same InstrumentID/source revision and ChangeID where changed.
	Trace field
	Synthetic trace and validation

	Criterion source
	CR-SYN-001 → INS-SYN-DDA01, candidate final-design checklist; project criterion is submission readiness, not an invented engineering value

	BoD record
	SYN-BOD-001 R01 is a fictional project row to be populated under BBM-STD-12; no claim that the office master contains a real project approval

	Exchange
	EX-SYN-FD01 /​ DEL-SYN-FD01 /​ SUB-SYN-FD01; actual date and appointment-specific EIR to be allocated

	Plan link
	Fictional MIDP-SYN-STAGES01 row FD-01; other gates have their own CON-01, PER-01, ACT-01 and CMP-01 rows

	Source and change join
	Candidate source revision SYN-PROFILE-R01 and baseline CH-SYN-BASE01 join Codes, Profiles and Criterion trace. A proposed CH-SYN-CODE01 revision R02 stays pending until approved and propagated

	Separate decisions
	Technical package check; LAP submission authorisation; recipient information acceptance; authority statutory approval, each with its own actor/​date/​evidence



For a design change, the discipline specialist assesses all affected criteria, drawings/models, NOCs, permit conditions and dependent exchanges. The authority liaison obtains required clarification/resubmission; task leads and LAP propagate the same ChangeID through EIR/BEP/TIDP/MIDP. Do not record authority approval from an internal review outcome.
6 Change alerts and release checks
At project mobilisation, each affected submission and material rule/site/use/design change, the liaison checks the official service/circular source, adopted edition and effective date. Record old/new source version, verification date, affected rows, specialist impact decision, required action/owner, notifications and receiving acknowledgment. Office default watch: check authority circular and service pages monthly and at every stage gate and submission (DM issued BIM circulars in Oct 2023 and Jan 2026). A project may shorten this interval, but not lengthen it without BIM Manager approval. This template invents no authority SLA. The controlled change record is the alert evidence, not a second code library.
	Adverse case
	Required response

	Latest library PDF exists but adoption/​effective date is unknown
	Hold affected criterion/​release; obtain the competent applicability decision

	ADM infrastructure profile is assigned to a Dubai building without adoption evidence
	Reject the profile mapping; determine actual authority and appointment scope

	NOC is uploaded but receipt/​decision/​expiry does not cover this submission
	Keep dependency open; verify current valid evidence

	Package is accepted as information but the statutory permit is absent
	Information decision may stand; construction/​occupation permission remains Hold

	Authority changes the checklist after a prior concept exchange
	Assess affected scope and transition/​clarification; update linked baselines before the next applicable release



The release reviewer checks all applicable instruments and clauses, current package profile, prerequisite/NOC ownership, actual valid approvals/conditions, BoD source joins and MIDP delivery joins. Unresolved applicable code or submission profile blocks the affected release. Explicitly accepted non-applicability is recorded with evidence. Office adoption, actual authority confirmation, live portal submission and project approvals are NOT EXECUTED in this template.
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