## Instructions
Control | Instruction
Identity | BBM-STD-62-INTERIORS_MODELLING-V0.1 ¦ V0.1 ¦ 2026-10-16 ¦ private WIP
Use | Copy a Blank sheet into an approved project record; do not overwrite examples.
Examples | All SYN records and observations are fictional expected cases, never executed host/learner evidence.
Blank forms | Header row 4; record rows 5:24 intentionally empty. Complete applicable fields, source and decision.
Execution | Record actual operator/date, inputs and output hashes, tools/full builds, evidence, reviewer and receiving decision.
Authority | Author, independent checker, submission authoriser and recipient are separate scoped functions.
Status | Not executed is default. PASS needs actual evidence; dropdowns are input aids, not release enforcement.
Paths | Relative paths use office-rev as base. Private project evidence stays in approved custody; no credentials.
Decision | All mandatory applicable requirements must pass; no average hides identity, safety or required data failures.
Revisions | Preserve issued baselines; changes use ChangeID and affected dependencies. No office adoption implied.

## Room data
BBM-STD-62-INTERIORS_MODELLING-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
SpaceID / number / name / level / zone | Source revision / room phase-option / base-link phase-room bounding | Boundary / height / uncertainty | Floor-wall-ceiling-skirting finish keys | Fixtures / furniture / joinery IDs | Use / brief / occupancy / performance / BoD sources | MEP / base-build interfaces | Checker-date / evidence / approval | Actual
SYN-SP62-01 / R01 / TRAIN-ROOM-A / L00 / Z01 | SYN-ID62 R01 / Renovation-A / base-build link revision and phase mapping to qualify;room-bounding on for test | Internal4x3m;height3m;door1x2m;synthetic unsurveyed | FF-01 retained12;WF-01 new40;CF-01 net11.75m2;SK-NA(no skirting in fixture;actual brief to decide) | LightsL-01/02;DIF-01;AP-01;S-01;J-01;F-01/02 | Synthetic room-use only;actual brief/occupancy/fire/acoustic/access sources unresolved | Base-build owner / service designers;no duplicate partitions | Actual competent check/evidence and decision required | Not executed

## Room data Blank
BBM-STD-62-INTERIORS_MODELLING-V0.1
BLANK FORM
SpaceID / number / name / level / zone | Source revision / room phase-option / base-link phase-room bounding | Boundary / height / uncertainty | Floor-wall-ceiling-skirting finish keys | Fixtures / furniture / joinery IDs | Use / brief / occupancy / performance / BoD sources | MEP / base-build interfaces | Checker-date / evidence / approval | Actual

## Finishes
BBM-STD-62-INTERIORS_MODELLING-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
FinishKey / SpaceID | State / option / source | Material / substrate / thickness-unit | Spec clause / detail / revision | Quantity / unit / net-gross rule | Quantity owner / exclusions | Source / criteria / rights | Verifier / evidence / decision | Actual
FF-01 / SYN-SP62-01 | Retained / A / SYN-ID62 R01 | MAT62-FF-01 R01;test surface description;actual build-up/thickness to qualify | SP62-FF-01 R01 A1 / DET62-FF-01 R01 | 12m2 horizontal including beneath cabinet | One quantity-bearing source;exclude same compound layer | Source index synthetic records;no product/performance approval | Competent checker;missing required link Hold | Not executed
WF-01 / SYN-SP62-01 | New / A / SYN-ID62 R01 | MAT62-WF-01 R01;test surface description;actual build-up/thickness to qualify | SP62-WF-01 R01 A1 / DET62-WF-01 R01 | 40m2 net face;gross42 minusdoor2;no reveals | One quantity-bearing source;exclude same compound layer | Source index synthetic records;no product/performance approval | Competent checker;missing required link Hold | Not executed
CF-01 / SYN-SP62-01 | New / A / SYN-ID62 R01 | MAT62-CF-01 R01;test surface description;actual build-up/thickness to qualify | SP62-CF-01 R01 A1 / DET62-CF-01 R01 | 11.75m2 net board;gross12 minusAP0.25;never sum gross+net | One quantity-bearing source;exclude same compound layer | Source index synthetic records;no product/performance approval | Competent checker;missing required link Hold | Not executed

## Finishes Blank
BBM-STD-62-INTERIORS_MODELLING-V0.1
BLANK FORM
FinishKey / SpaceID | State / option / source | Material / substrate / thickness-unit | Spec clause / detail / revision | Quantity / unit / net-gross rule | Quantity owner / exclusions | Source / criteria / rights | Verifier / evidence / decision | Actual

## Interfaces
BBM-STD-62-INTERIORS_MODELLING-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
InterfaceID / room / objects | Source owner / revision | Geometry / criterion / unit-source | Expected | Observed / uncertainty | Evidence URI / hashes / builds | Checker / date | Issue / correction / retest / recipient | Actual
I62-CEIL / AP-01 / SYN-SP62-01 | Interiors + base-build/service owner / R01 | Ceiling Z2700;AP500x500mm fixture | Panel accessible/opening and service grid reviewed;actual service clearance source required | No actual observation | Actual source/output/full builds required | Distinct competent checker/date | Owner correction;new ChangeID;scoped receiving decision | Not executed
I62-J / J-01 / SYN-SP62-01 | Interiors + base-build/service owner / R01 | Cabinet2000x600x900;service zone depth800mm test only | No unintended obstruction;actual fixing/service/maintenance criterion Unverified | No actual observation | Actual source/output/full builds required | Distinct competent checker/date | Owner correction;new ChangeID;scoped receiving decision | Not executed
I62-S / S-01 / SYN-SP62-01 | Interiors + base-build/service owner / R01 | Sink at1000,300mm;water/waste by plumber | Connections/loads/isolation/access competent source and check required | No actual observation | Actual source/output/full builds required | Distinct competent checker/date | Owner correction;new ChangeID;scoped receiving decision | Not executed
I62-T-P / J-01 / SYN-SP62-01 | Interiors + base-build/service owner / R01 | Nominal2000,measurement2001+/-0.5,tolerance2mm fictional | 1+0.5=1.5mm passes synthetic conservative rule | No actual observation | Actual source/output/full builds required | Distinct competent checker/date | Owner correction;new ChangeID;scoped receiving decision | Not executed
I62-T-N / J-01 / SYN-SP62-01 | Interiors + base-build/service owner / R01 | Reset measurement2003+/-0.5,tolerance2mm fictional | 3+0.5=3.5mm fails;correct source and retest | No actual observation | Actual source/output/full builds required | Distinct competent checker/date | Owner correction;new ChangeID;scoped receiving decision | Not executed

## Interfaces Blank
BBM-STD-62-INTERIORS_MODELLING-V0.1
BLANK FORM
InterfaceID / room / objects | Source owner / revision | Geometry / criterion / unit-source | Expected | Observed / uncertainty | Evidence URI / hashes / builds | Checker / date | Issue / correction / retest / recipient | Actual

## Phase output
BBM-STD-62-INTERIORS_MODELLING-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
OutputID / view-sheet | Source hash / revision | Phase / option / link mapping | Scope / required categories | Drawing/schedule / expected result | Authority/service source / applicability | Checker-date / whole sheet-nine tiles / evidence | Issue / authorisation / receiving decision | Actual
O62-RCP | Actual native/export source hashes required | Existing/Demolition/Renovation explicit;A selected;B excluded | Ceiling/light/diffuser/access | RCP Z2700 reconciles elevations;2lights/1diffuser/1AP | Actual jurisdiction/service/checklist to verify viaBA-STD-57 | Actual final output inspection/evidence required | Separate design,information and authority decisions | Not executed
O62-FIN | Actual native/export source hashes required | Existing/Demolition/Renovation explicit;A selected;B excluded | Floor/wall/ceiling and room data | 12retainedfloor/40newwall/11.75netnewboard;demolition separate | Actual jurisdiction/service/checklist to verify viaBA-STD-57 | Actual final output inspection/evidence required | Separate design,information and authority decisions | Not executed
O62-JOIN | Actual native/export source hashes required | Existing/Demolition/Renovation explicit;A selected;B excluded | Joinery/elevations/fixtures/furniture | 1cabinet/1sink/2chairs;detail/spec andservice references resolve | Actual jurisdiction/service/checklist to verify viaBA-STD-57 | Actual final output inspection/evidence required | Separate design,information and authority decisions | Not executed
O62-AUTH | Actual native/export source hashes required | Existing/Demolition/Renovation explicit;A selected;B excluded | Approved/proposed partitions/layouts/source | Actual permit/building-modification package;no universal UAEprofile | Actual jurisdiction/service/checklist to verify viaBA-STD-57 | Actual final output inspection/evidence required | Separate design,information and authority decisions | Not executed

## Phase output Blank
BBM-STD-62-INTERIORS_MODELLING-V0.1
BLANK FORM
OutputID / view-sheet | Source hash / revision | Phase / option / link mapping | Scope / required categories | Drawing/schedule / expected result | Authority/service source / applicability | Checker-date / whole sheet-nine tiles / evidence | Issue / authorisation / receiving decision | Actual

## Quantities
BBM-STD-62-INTERIORS_MODELLING-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
QuantityID | SpaceID / population / selected state-option | Expected quantity | Unit / measurement rule | Source / excluded representations | Material-spec-detail link | Actual / evidence / uncertainty | Checker / decision | Actual status
Q62-F | SYN-SP62-01 / FF-01 retained/A | 12 | m2 internal plan;cabinet included | No duplicate new floor | MAT62-FF-01 / SP62-FF-01 R01 A1 / DET62-FF-01 R01 | No measurement | All required references/values before release | Not executed
Q62-W | SYN-SP62-01 / WF-01 new/A | 40 | m2 net face;14x3-1x2 | No reveals/returns/windows | MAT62-WF-01 / SP62-WF-01 R01 A1 / DET62-WF-01 R01 | No measurement | Gross42 separately;not statutory area | Not executed
Q62-C | SYN-SP62-01 / CF-01 new/A | 11.75 | m2 board net;12-0.5x0.5 | AP count separately;gross12 diagnostic | MAT62-CF-01 / SP62-CF-01 R01 A1 / DET62-CF-01 R01 | No measurement | Do not sum gross andnet | Not executed
Q62-OBJ | SYN-SP62-01 / Distinct categories/A | 2lights;1diffuser;1AP;1cabinet;1sink;2chairs | count by category and stable ID | No aggregate mixed-fixture count | MAT62-OBJECTS / SP62-OBJECTS R01 A1 / DET62-OBJECTS R01 | No observation | Reconcile native/schedule/RDS/receiver | Not executed

## Quantities Blank
BBM-STD-62-INTERIORS_MODELLING-V0.1
BLANK FORM
QuantityID | SpaceID / population / selected state-option | Expected quantity | Unit / measurement rule | Source / excluded representations | Material-spec-detail link | Actual / evidence / uncertainty | Checker / decision | Actual status

## Checklist
BBM-STD-62-INTERIORS_MODELLING-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
CheckID / exchange / source hashes | Requirement / mandatory applicability | Expected criterion / source | Observed / units / uncertainty | Responsible owner / independent checker-date | Evidence URI / output hashes / full builds | Defect / corrected revision / retest | Submission authorisation / recipient decision | Actual
C62-ID | All applicable mandatory requirements in selectedroom/A | Stable room/object IDs;phase/option/linked room boundaries | No actual result | Actual competent owner/checker required | Native/finalplot/export/receiver evidence required | Reset independent negative cases;preserve failed record | Separate scoped decisions;none completed | Not executed
C62-FIN | All applicable mandatory requirements in selectedroom/A | Finish keys/material/spec/detail resolve;one quantity source | No actual result | Actual competent owner/checker required | Native/finalplot/export/receiver evidence required | Reset independent negative cases;preserve failed record | Separate scoped decisions;none completed | Not executed
C62-MEP | All applicable mandatory requirements in selectedroom/A | RCP/elevation/access/fixture/support connections and tolerance source | No actual result | Actual competent owner/checker required | Native/finalplot/export/receiver evidence required | Reset independent negative cases;preserve failed record | Separate scoped decisions;none completed | Not executed
C62-Q | All applicable mandatory requirements in selectedroom/A | 12floor,40wall,11.75board plus category-specific counts reconcile | No actual result | Actual competent owner/checker required | Native/finalplot/export/receiver evidence required | Reset independent negative cases;preserve failed record | Separate scoped decisions;none completed | Not executed
C62-NEG | All applicable mandatory requirements in selectedroom/A | Duplicate floor,missing spec,service obstruction oroptionB wrongly included detected | No actual result | Actual competent owner/checker required | Native/finalplot/export/receiver evidence required | Reset independent negative cases;preserve failed record | Separate scoped decisions;none completed | Not executed
C62-EX | All applicable mandatory requirements in selectedroom/A | Final drawings/tags andactual receiver use verified;authorityprofile separate | No actual result | Actual competent owner/checker required | Native/finalplot/export/receiver evidence required | Reset independent negative cases;preserve failed record | Separate scoped decisions;none completed | Not executed

## Checklist Blank
BBM-STD-62-INTERIORS_MODELLING-V0.1
BLANK FORM
CheckID / exchange / source hashes | Requirement / mandatory applicability | Expected criterion / source | Observed / units / uncertainty | Responsible owner / independent checker-date | Evidence URI / output hashes / full builds | Defect / corrected revision / retest | Submission authorisation / recipient decision | Actual

## Source index
BBM-STD-62-INTERIORS_MODELLING-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
SourceID | Revision | Kind | Controlled synthetic content / clause | Scope / limitations | Owner / checker / adoption | Actual
MAT62-FF-01 | R01 | Material | Neutral synthetic surface;not actual product;BBM-STD-71 owner controls actual adoption | Synthetic fixture description only | Interiors lead / distinct checker;no actual office adoption | Not executed
SP62-FF-01 | R01 | Specification | 12m2 horizontal including beneath cabinet;A1 measurement rule;selected phase/option only | Synthetic fixture description only | Interiors lead / distinct checker;no actual office adoption | Not executed
DET62-FF-01 | R01 | Detail specification | SYN-SP62-01;12m2 horizontal including beneath cabinet;FF floor plane/WF wallface withdoor/CF ceiling plane with500x500AP as applicable;no native detail supplied | Synthetic fixture description only | Interiors lead / distinct checker;no actual office adoption | Not executed
MAT62-WF-01 | R01 | Material | Neutral synthetic surface;not actual product;BBM-STD-71 owner controls actual adoption | Synthetic fixture description only | Interiors lead / distinct checker;no actual office adoption | Not executed
SP62-WF-01 | R01 | Specification | 40m2 net face;gross42 minusdoor2;no reveals;A1 measurement rule;selected phase/option only | Synthetic fixture description only | Interiors lead / distinct checker;no actual office adoption | Not executed
DET62-WF-01 | R01 | Detail specification | SYN-SP62-01;40m2 net face;gross42 minusdoor2;no reveals;FF floor plane/WF wallface withdoor/CF ceiling plane with500x500AP as applicable;no native detail supplied | Synthetic fixture description only | Interiors lead / distinct checker;no actual office adoption | Not executed
MAT62-CF-01 | R01 | Material | Neutral synthetic surface;not actual product;BBM-STD-71 owner controls actual adoption | Synthetic fixture description only | Interiors lead / distinct checker;no actual office adoption | Not executed
SP62-CF-01 | R01 | Specification | 11.75m2 net board;gross12 minusAP0.25;never sum gross+net;A1 measurement rule;selected phase/option only | Synthetic fixture description only | Interiors lead / distinct checker;no actual office adoption | Not executed
DET62-CF-01 | R01 | Detail specification | SYN-SP62-01;11.75m2 net board;gross12 minusAP0.25;never sum gross+net;FF floor plane/WF wallface withdoor/CF ceiling plane with500x500AP as applicable;no native detail supplied | Synthetic fixture description only | Interiors lead / distinct checker;no actual office adoption | Not executed
MAT62-OBJECTS | R01 | Material scope | Distinct category IDs/counts perMD4/5;interfaces as specified;actual manufacturer/material/connection records unresolved | Synthetic fixture only;no product/design approval | Interiors/service owner + checker | Not executed
SP62-OBJECTS | R01 | Specification | Distinct category IDs/counts perMD4/5;interfaces as specified;actual manufacturer/material/connection records unresolved | Synthetic fixture only;no product/design approval | Interiors/service owner + checker | Not executed
DET62-OBJECTS | R01 | Detail specification | Distinct category IDs/counts perMD4/5;interfaces as specified;actual manufacturer/material/connection records unresolved | Synthetic fixture only;no product/design approval | Interiors/service owner + checker | Not executed

## Source index Blank
BBM-STD-62-INTERIORS_MODELLING-V0.1
BLANK FORM
SourceID | Revision | Kind | Controlled synthetic content / clause | Scope / limitations | Owner / checker / adoption | Actual