## Instructions
Control | Instruction
Identity | BBM-STD-75-HANDOVER_AND_AIM-V0.1 ¦ V0.1 ¦ 2026-10-16 ¦ private WIP
Use | Copy a Blank sheet into an approved project record; do not overwrite examples.
Examples | All SYN records and observations are fictional expected cases, never executed host/learner evidence.
Blank forms | Header row 4; record rows 5:24 intentionally empty. Complete applicable fields, source and decision.
Execution | Record actual operator/date, inputs and output hashes, tools/full builds, evidence, reviewer and receiving decision.
Authority | Author, independent checker, submission authoriser and recipient are separate scoped functions.
Status | Not executed is default. PASS needs actual evidence; dropdowns are input aids, not release enforcement.
Paths | Relative paths use office-rev as base. Private project evidence stays in approved custody; no credentials.
Decision | All mandatory applicable requirements must pass; no average hides identity, safety or required data failures.
Revisions | Preserve issued baselines; changes use ChangeID and affected dependencies. No office adoption implied.

## Assets
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
Asset_ID | Class | Location_ID | System_ID | Condition | InspectionDate | ServiceInterval | ServiceUnit | Document_ID | Document revision | DesignFlow_m3_s | NominalDiameter_mm | Serial | State | Source revision | Evidence status | Object reference
AHU-001 | AHU | LOC-101 | SYS-AIR01 | Good | 2026-11-30 | 12 | month | DOC-SYN-AHU01 | R01 | 1.2 |  | SN-SYN-AHU001 | Active | SYN-ASSET01 R01 | Fictional fixture; not installed proof | SYN-MODEL01 / AHU001
VLV-001 | VALVE | LOC-101 | SYS-HW01 | Good | 2026-11-30 | 6 | month | DOC-SYN-VLV01 | R01 |  | 50 | SN-SYN-VLV001 | Active | SYN-ASSET01 R01 | Fictional fixture; not installed proof | SYN-MODEL01 / VLV001
VLV-002 | VALVE | LOC-102 | SYS-HW01 | Fair | 2026-11-30 | 6 | month | DOC-SYN-VLV01 | R01 |  | 40 | SN-SYN-VLV002 | Active | SYN-ASSET01 R01 | Fictional fixture; not installed proof | SYN-MODEL01 / VLV002

## Assets Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
Asset_ID | Class | Location_ID | System_ID | Condition | InspectionDate | ServiceInterval | ServiceUnit | Document_ID | Document revision | DesignFlow_m3_s | NominalDiameter_mm | Serial | State | Source revision | Evidence status | Object reference

## Dictionary
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
PropertyID | Field | Meaning | Datatype | Unit or allowed values | Applicability | Mandatory condition | Source | Validation
P-SYN-01 | Asset_ID | Stable facility asset identity | String | Uppercase; max 40 in synthetic profile | All included assets | Always | SYN-DICT-01 R01 | Unique; never recycled
P-SYN-02 | Class | Maintainable asset class | Enum | AHU; VALVE | All included assets | Always | SYN-DICT-01 R01 | Allowed class
P-SYN-03 | Location_ID | Current location key | String | Locations key | All included assets | Always | SYN-LOC-01 R01 | Foreign key exists
P-SYN-04 | System_ID | Serving system key | String | Systems key | All included assets | Always | SYN-SYS-01 R01 | Foreign key exists
P-SYN-05 | Condition | Inspection condition | Enum | Good; Fair; Poor; Not inspected | All included assets | Per inspection exchange | Fictional operator scale R01 | Value plus source/date
P-SYN-06 | InspectionDate | Actual inspection date | Date | Export yyyy-mm-dd | Inspected assets | When Condition is not Not inspected | Inspection source | Real date and evidence
P-SYN-07 | ServiceInterval | Servicing interval | Number | Positive with ServiceUnit | All included assets | Where service plan required | Current instruction | Positive value and source
P-SYN-08 | ServiceUnit | Interval unit | Enum | month | Synthetic asset set only | With ServiceInterval | Current instruction | Explicit approved unit
P-SYN-09 | Document_ID | Current instruction key | String | Documents key | All included assets | Where operational instruction required | Document register | Current revision; authorised access
P-SYN-10 | DesignFlow_m3_s | Design airflow | Number | m3/s | AHU only | AHU selection/operating context | SYN-DESIGN01 R01 | Numeric; do not relabel L/s
P-SYN-11 | NominalDiameter_mm | Valve nominal diameter | Number | mm | VALVE only | Valve identity/maintenance context | SYN-DESIGN01 R01 | Positive numeric
P-SYN-12 | Serial | Manufacturer serial reference | String | Fictional serial in examples | Installed maintainable assets | At actual verified handover | Installed-asset evidence | Not interchangeable with Asset_ID
P-SYN-13 | Document revision | Instruction revision selected for this asset | String | Documents revision | All included assets | With Document_ID | Document register | Must match current Document_ID revision
P-SYN-14 | State | Lifecycle status | Enum | Active; Retired | All included assets | Always | Authorised lifecycle event | Retired identity/history retained
P-SYN-15 | Source revision | Provenance source baseline | String | Container/source and revision | All included assets | Always | Source register | Resolvable approved source for actual use
P-SYN-16 | Evidence status | Verification/provenance qualification | String | Explicit evidence status | All included assets | Always | Check/event evidence | Synthetic does not mean installed
P-SYN-17 | Object reference | Optional source-model locator | String | Model ID and object reference | Model-linked assets | When model link is required | Source model mapping | Distinct from stable Asset_ID; verify mapping

## Dictionary Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
PropertyID | Field | Meaning | Datatype | Unit or allowed values | Applicability | Mandatory condition | Source | Validation

## Locations
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
Location_ID | Title | Facility_ID | Source revision
LOC-101 | Fictional plant space 101 | FAC-SYN-01 | SYN-LOC-01 R01
LOC-102 | Fictional service space 102 | FAC-SYN-01 | SYN-LOC-01 R01

## Locations Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
Location_ID | Title | Facility_ID | Source revision

## Systems
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
System_ID | Title | Facility_ID | Owner function | Source revision
SYS-AIR01 | Fictional air system | FAC-SYN-01 | Mechanical operator | SYN-SYS-01 R01
SYS-HW01 | Fictional hot-water system | FAC-SYN-01 | Mechanical operator | SYN-SYS-01 R01

## Systems Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
System_ID | Title | Facility_ID | Owner function | Source revision

## Documents
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
Document_ID | Revision | Title | Applies to class | Access route | Source and rights | Access test owner | Actual test
DOC-SYN-AHU01 | R01 | Fictional AHU service instruction | AHU | Project controlled document URI to populate | Fictional instruction only; actual rights pending | Operator recipient | Not executed
DOC-SYN-VLV01 | R01 | Fictional valve service instruction | VALVE | Project controlled document URI to populate | Fictional instruction only; actual rights pending | Operator recipient | Not executed

## Documents Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
Document_ID | Revision | Title | Applies to class | Access route | Source and rights | Access test owner | Actual test

## Profile
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Actual
SYN-FM-CSV-01 | FAC-SYN-01 /3 assets | R01; exact17 AIR headers | UTF8 CSV comma/quoted/dot decimal/ISO dates; no extra columns | Asset-data lead / receiver | Full builds Unverified; ID max40 fictional | COBie not selected; actual contract may require legacy profile | Not executed
COBIE75-SEL | If contract requires COBie | Exact version/release/table requirements | Official blank/schema resources https://nibs.org/nbims/v4/resources; acquire/hash controlled copy | Operator / exchange lead | No silent2.4 to3 upgrade; this custom form is not COBie | Real schema/template and ingest conditional adoption task | Not executed
COBIE75-MIG | Only on approved legacy-to-new change | Field-by-field edition audit | Legacy Floor / ComponentNames versus newer Level / Component.Name: verify adopted schema; do not mechanically rename | Schema owner / receiver | All actual required tables, keys, dates and null rules compared | Preserve old delivery; new profile/version and retest approval | Not executed

## Profile Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Actual

## Types and joins
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Actual
T-AHU01 | AHU-001 | AIR-007 / P72-001 | AHU type; SYN-ASSET01 R01 | Mechanical owner / checker | 1 occurrence; fictional | Preserve source IDs | Not executed
T-VLV01 | VLV-001,VLV-002 | AIR-007 / P72-001 | Valve type; SYN-ASSET01 R01 | Mechanical owner / checker | 2 occurrences; locations101/102 | Actual type dictionary to adopt | Not executed

## Types and joins Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Actual

## Records
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Actual
DOC-SYN-AHU01 | AHU-001 | AIR-006/007/008 as applicable | O&M R01; fictional placeholder; no bytes | Competent source owner / receiver | Required evidence absent | Current source/access and acceptance unresolved | Not executed
DOC-SYN-VLV01 | VLV-001,VLV-002 | AIR-006/007/008 as applicable | O&M R01; fictional placeholder; no bytes | Competent source owner / receiver | Required evidence absent | Current source/access and acceptance unresolved | Not executed
COM-AHU01 | AHU-001 | AIR-006/007/008 as applicable | Commissioning R01; fictional placeholder; no bytes | Competent source owner / receiver | Required evidence absent | Current source/access and acceptance unresolved | Not executed
COM-VLV01 | VLV-001,VLV-002 | AIR-006/007/008 as applicable | Commissioning R01; fictional placeholder; no bytes | Competent source owner / receiver | Required evidence absent | Current source/access and acceptance unresolved | Not executed
WAR-AHU01 | AHU-001 | AIR-006/007/008 as applicable | Warranty terms/start/duration R01; fictional placeholder; no bytes | Competent source owner / receiver | Required evidence absent | Current source/access and acceptance unresolved | Not executed
WAR-VLV01 | VLV-001,VLV-002 | AIR-006/007/008 as applicable | Warranty terms/start/duration R01; fictional placeholder; no bytes | Competent source owner / receiver | Required evidence absent | Current source/access and acceptance unresolved | Not executed
SAFE-01 | Applicable facility assets | AIR-006/007/008 as applicable | Residual risk/statutory R01; fictional placeholder; no bytes | Competent source owner / receiver | Required evidence absent | Current source/access and acceptance unresolved | Not executed

## Records Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Actual

## Reconciliation
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Event date / ChangeID | Requested / accepted baseline | Actual due date | Input-output URI / hashes | Recipient acknowledgement / date | Custodian / deputy / transition | Actual
REC75-01 | VLV-002 / LOC-999 negative | Location FK must exist | Expected FAIL; correction to LOC-102 needs verification | Source owner / independent checker | Synthetic case; not installed observation | CH-SYN75-01 corrected revision and retest | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed
REC75-02 | WAR-VLV01 missing source | Applicable warranty evidence | Expected Hold; obtain source terms, no guessed date | Source owner / operator | Index alone not evidence | Source/access check required | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed

## Reconciliation Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Event date / ChangeID | Requested / accepted baseline | Actual due date | Input-output URI / hashes | Recipient acknowledgement / date | Custodian / deputy / transition | Actual

## Receiving
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Event date / ChangeID | Requested / accepted baseline | Actual due date | Input-output URI / hashes | Recipient acknowledgement / date | Custodian / deputy / transition | Actual
R75-C | Create AHU-002 | Reset independently from3-asset baseline | 4 active; valid existing joins | Receiver / independent checker | Import log; before/after query; hashes | Separate authorisation, receipt, receiving decision | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed
R75-U | AHU-001 Good to Poor /2026-12-03 | Reset independently from3-asset baseline | 3 active; same IDs; unchanged fields preserved | Receiver / independent checker | Import log; before/after query; hashes | Separate authorisation, receipt, receiving decision | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed
R75-P | VLV-002 replaced by VLV-003 | Reset independently from3-asset baseline | 3 active;4 historical identities; predecessor link | Receiver / independent checker | Import log; before/after query; hashes | Separate authorisation, receipt, receiving decision | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed
R75-R | Retire VLV-002 only | Reset independently from3-asset baseline | 2 active;3 historical identities | Receiver / independent checker | Import log; before/after query; hashes | Separate authorisation, receipt, receiving decision | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed
R75-D | Duplicate AHU-001 or replay accepted ChangeID | Reset independently from3-asset baseline | Reject duplicate; no repeated event; qualify importer behavior | Receiver / independent checker | Import log; before/after query; hashes | Separate authorisation, receipt, receiving decision | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed
R75-A | Read documents; denied-write role | Reset independently from3-asset baseline | Allowed scope works; denied access/change blocked | Receiver / independent checker | Import log; before/after query; hashes | Separate authorisation, receipt, receiving decision | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed

## Receiving Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Event date / ChangeID | Requested / accepted baseline | Actual due date | Input-output URI / hashes | Recipient acknowledgement / date | Custodian / deputy / transition | Actual

## Trigger event
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Event date / ChangeID | Requested / accepted baseline | Actual due date | Input-output URI / hashes | Recipient acknowledgement / date | Custodian / deputy / transition | Actual
EV75-01 | VLV-002 to VLV-003 | CH-SYN75-REPL / AIR-007 | New serial/install/commissioning/warranty sources required | Authorised updater / competent checker | Retire old ID; history;3 active4 historical | Operator acknowledges exact AIM revision | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed
EV75-02 | Unchanged annual review | Manual12.5 retained cadence | Confirm records/roles/links; event change reopens scope | Custodian / operator | No fabricated yearly inspection or SLA | No unappointed delivery-team duty | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed

## Trigger event Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Event date / ChangeID | Requested / accepted baseline | Actual due date | Input-output URI / hashes | Recipient acknowledgement / date | Custodian / deputy / transition | Actual

## Handover
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Event date / ChangeID | Requested / accepted baseline | Actual due date | Input-output URI / hashes | Recipient acknowledgement / date | Custodian / deputy / transition | Actual
H75-01 | FAC-SYN-01 / appointed scope | Exact AIR/EIR/LOIN revisions | Constructed condition, identity and survey/inspection limitations | Asset-data lead / independent checker | All applicable mandatory requirements pass | LAP authorises; operator accepts tested use/custody | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed
H75-02 | FAC-SYN-01 / appointed scope | Exact AIR/EIR/LOIN revisions | Current O&M, commissioning, warranty, safety and required approvals | Asset-data lead / independent checker | All applicable mandatory requirements pass | LAP authorises; operator accepts tested use/custody | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed
H75-03 | FAC-SYN-01 / appointed scope | Exact AIR/EIR/LOIN revisions | Native/IFC/CSV manifests; actual ingest/change/replace/retire | Asset-data lead / independent checker | All applicable mandatory requirements pass | LAP authorises; operator accepts tested use/custody | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed
H75-04 | FAC-SYN-01 / appointed scope | Exact AIR/EIR/LOIN revisions | AIM URI/revision, owner/deputy/updater, access/training/records | Asset-data lead / independent checker | All applicable mandatory requirements pass | LAP authorises; operator accepts tested use/custody | Not executed; record actual event | Not yet accepted | To agree before execution | Actual evidence required | No acknowledgement | Not appointed / no transition | Not executed

## Handover Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Event date / ChangeID | Requested / accepted baseline | Actual due date | Input-output URI / hashes | Recipient acknowledgement / date | Custodian / deputy / transition | Actual

## Exclusions
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Actual
EX75-01 | Decorative/non-maintainable fixture | Narrow synthetic AIR only | No maintenance purpose; actual owner confirms scope | Requirement owner / receiver | Never omit required safety/contracted assets | Applicability approval before use | Not executed

## Exclusions Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
RecordID | Scope / join | Requirement / profile | Source / expected evidence | Owner / check | Result / restriction | Decision / custody | Actual

## Evidence index
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
RecordID | Asset_ID / Type_ID | Kind / revision | Source URI / SHA256 | Source date / verifier | Warranty guarantor / terms | Start trigger / date | Duration / unit | Access check / evidence | Actual
WAR-VLV01 | T-VLV01 | Warranty / R01 | No source bytes: required evidence absent | Unverified / competent source owner | Actual guarantor and terms required | Actual source trigger/date required | Actual duration/unit required | Operator must open current source | Not executed

## Evidence index Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
RecordID | Asset_ID / Type_ID | Kind / revision | Source URI / SHA256 | Source date / verifier | Warranty guarantor / terms | Start trigger / date | Duration / unit | Access check / evidence | Actual

## Constructed check
BBM-STD-75-HANDOVER_AND_AIM-V0.1
SYNTHETIC WORKED EXAMPLE — NOT EXECUTED
CheckID | Asset_ID / serial | Source model / revision | Survey or installation date | Method / uncertainty / coverage | Expected / actual location-system | Source URI / SHA256 | Verifier / issue / disposition | Actual
C75-01 | VLV-002 / fictional serial | SYN-ASSET01 R01 | No actual date | No survey claim; record limitations | LOC-102 / SYS-HW01 expected; actual unknown | Actual evidence required | Competent checker; unresolved | Not executed

## Constructed check Blank
BBM-STD-75-HANDOVER_AND_AIM-V0.1
BLANK FORM
CheckID | Asset_ID / serial | Source model / revision | Survey or installation date | Method / uncertainty / coverage | Expected / actual location-system | Source URI / SHA256 | Verifier / issue / disposition | Actual