## Instructions
Instructions
SYNTHETIC EXAMPLE ONLY. Native execution and actual approval: Not executed.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
Field | Rule
Document | BBM-STD-79-FOUR_D_PLANNING-V0.1 V0.1; private controlled WIP; drafting owner W5
Purpose | Use the paired empty forms to create project-controlled records; example tabs are training data.
Control required | Record ID/revision, source URI/hash/date, requirement, scope, actual holder and delegated authority.
Evidence states | Expected outcome, calculated fixture value, actual host result and recipient decision are distinct.
Blank forms | Copy matching Blank tab within the approved project record system; replace example banner and allocate real record ID.
Validation | Dropdowns guide entry, not permissions or automatic approval. Paste/import can bypass validation; recheck records.
Null handling | Unknown, missing, withheld and not applicable are distinct; never silently convert to zero.
Privacy | Synthetic examples only. Apply Manual 9.4 and BBM-STD-76 for real access, retention and disposal.
Release | Author/check/review/authorise/accept are separate scoped decisions. No native tests or actual approvals performed.
Form convention | Headers row4; records row5 onward; frozen A5; filters; list validations where applicable.

## Brief
Brief
SYNTHETIC EXAMPLE ONLY. Native execution and actual approval: Not executed.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
SimulationID / rev | Purpose / requirement | Schedule / model | Calendar / time basis | Data date | Owner / status
SYN-SIM79 R01 | Z01 sequence/logistics; SYN-REQ79 | SYN-SCH79 R01 / SYN-MOD79 R01 | SYN-CAL79;7days08-16;Asia/Dubai;half-open | 2026-10-20 16:00 | Planner; Draft

## Blank Brief
Blank Brief
Blank controlled form: populate project identity/revision/authority before use.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
SimulationID / rev | Purpose / requirement | Schedule / model | Calendar / time basis | Data date | Owner / status

## Activities
Activities
SYNTHETIC EXAMPLE ONLY. Native execution and actual approval: Not executed.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
ActivityID | WBS | Task type | Planned start | Planned finish | Work hours | Predecessor / logic | Calendar
A10 | SYN.Z01.TW | Temporary install | 2026-10-19 08:00 | 2026-10-19 16:00 | 8 | None; fixture start | SYN-CAL79
A20 | SYN.Z01.PART | Construct | 2026-10-20 08:00 | 2026-10-21 16:00 | 16 | A10; finish-to-start0lag | SYN-CAL79
A30 | SYN.Z01.TW | Temporary remove | 2026-10-22 08:00 | 2026-10-22 16:00 | 8 | A20; finish-to-start0lag | SYN-CAL79

## Blank Activities
Blank Activities
Blank controlled form: populate project identity/revision/authority before use.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
ActivityID | WBS | Task type | Planned start | Planned finish | Work hours | Predecessor / logic | Calendar

## Links
Links
SYNTHETIC EXAMPLE ONLY. Native execution and actual approval: Not executed.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
LinkID | ActivityID | Native object / model rev | Zone | Scope / task type | Basis / resolved membership
L79-01 | A10 | TW01 / SYN-MOD79 R01 | Z01 | Install scaffold | Exact key;1 object
L79-02 | A20 | W01 / SYN-MOD79 R01 | Z01 | Construct whole | Exact key;1 object
L79-03 | A20 | W02 / SYN-MOD79 R01 | Z01 | Construct whole | Exact key;1 object
L79-04 | A30 | TW01 / SYN-MOD79 R01 | Z01 | Remove scaffold | Exact key;1 object; intentional second event

## Blank Links
Blank Links
Blank controlled form: populate project identity/revision/authority before use.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
LinkID | ActivityID | Native object / model rev | Zone | Scope / task type | Basis / resolved membership

## Progress
Progress
SYNTHETIC EXAMPLE ONLY. Native execution and actual approval: Not executed.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
ProgressID / date | Activity / object | Planned basis / percent | Recorded qty | Total qty / unit | Recorded percent | Variance percentage points | Observation / forecast | Actual
PR79-01 / 2026-10-20 16:00 | A20 / W01+W02 | 8/16 uniform hours;50% | 6 | 20m2 | 30 | -20 | SYN-OBS79 R01; invented6/10 W01 +0/10 W02; no real evidence | Not executed

## Blank Progress
Blank Progress
Blank controlled form: populate project identity/revision/authority before use.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
ProgressID / date | Activity / object | Planned basis / percent | Recorded qty | Total qty / unit | Recorded percent | Variance percentage points | Observation / forecast | Actual

## Coverage
Coverage
SYNTHETIC EXAMPLE ONLY. Native execution and actual approval: Not executed.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
CoverageID | Source / scope | Required objects | Linked unique objects | Required leaf tasks | Represented tasks | Link count | Omissions / duplicates | Actual
COV79 R01 | 3objects;3leaf tasks; no exclusions | 3 | 3 | 3 | 3 | 4 | 0/0 expected; install/remove intentional | Not executed
COV79 T79-01 | Omit W02 link | 3 | 2 | 3 | 3 | 3 | 1object omitted; task remains partially linked | Not executed

## Blank Coverage
Blank Coverage
Blank controlled form: populate project identity/revision/authority before use.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
CoverageID | Source / scope | Required objects | Linked unique objects | Required leaf tasks | Represented tasks | Link count | Omissions / duplicates | Actual

## Changes
Changes
SYNTHETIC EXAMPLE ONLY. Native execution and actual approval: Not executed.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
ChangeID | Baseline retained | Forecast A20 finish | Forecast A30 interval | Reason / consequence | Owner / decision
SYN-CH79-01 | SYN-SCH79 R01; A20finish21Oct;A30on22Oct | 2026-10-22 16:00 | 2026-10-23 08:00-16:00 | Delay; FS predecessor requires removal move | Planner; Hold pending actual approval

## Blank Changes
Blank Changes
Blank controlled form: populate project identity/revision/authority before use.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
ChangeID | Baseline retained | Forecast A20 finish | Forecast A30 interval | Reason / consequence | Owner / decision

## Reviews
Reviews
SYNTHETIC EXAMPLE ONLY. Native execution and actual approval: Not executed.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
IssueID | Tasks / model rev | Concern / role | Correction | Retest evidence | Decision | Actual
Issue79-01 | A20/A30; SYN-MOD79 R01 | Premature TW01 removal; temporary-works/construction/safety roles | Retain through A20; A30 removal only after completion | Critical-time views; scoped specialist sign-off | Hold | Not executed

## Blank Reviews
Blank Reviews
Blank controlled form: populate project identity/revision/authority before use.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
IssueID | Tasks / model rev | Concern / role | Correction | Retest evidence | Decision | Actual

## Tests
Tests
SYNTHETIC EXAMPLE ONLY. Native execution and actual approval: Not executed.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
TestID | Reset / mutation | Expected | Correction / retest | Actual
T79-01 | R01;omit L79-03 W02 | Fail;2/3 objects | Restore L79-03;3/3 | Not executed
T79-02 | R01;A20start19Oct08:00 | Fail;A10 incomplete | Restore20Oct08:00 | Not executed
T79-03 | R01;duplicate L79-02 | Fail;duplicate scope | Remove duplicate;retain TW install/remove | Not executed
T79-04 | R01;100%actual from colour | Hold;no observation | Restore6/20=30% and dated evidence limitation | Not executed
T79-05 | R01;remove scaffold during A20 | Fail;support review | RestoreA30;specialist review | Not executed
T79-06 | CH79-01;A30forecast22Oct08:00 | Fail;overlap A20 | MoveA30forecast23Oct;retain baseline | Not executed

## Blank Tests
Blank Tests
Blank controlled form: populate project identity/revision/authority before use.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
TestID | Reset / mutation | Expected | Correction / retest | Actual

## Acceptance
Acceptance
SYNTHETIC EXAMPLE ONLY. Native execution and actual approval: Not executed.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
RunID | Manifest / tool / profile | Checks / evidence | Checker / authoriser / receiver | Decision | Actual
SYN-RUN79 R01 | Specification only; actual hashes/builds unassigned | Named critical views + coverage/logic tests required | Actual holders unassigned | Hold | Not executed

## Blank Acceptance
Blank Acceptance
Blank controlled form: populate project identity/revision/authority before use.
Companion to BBM-STD-79-FOUR_D_PLANNING-V0.1
RunID | Manifest / tool / profile | Checks / evidence | Checker / authoriser / receiver | Decision | Actual