# Project trackers and registers

BBM-STD-99-PROJECT_TRACKERS-V0.1 | Office standard | 5 November 2026 | V0.1 | Private controlled WIP draft for office review

| Version | Date | Change |
| --- | --- | --- |
| V0.1 | 2026-11-05 | First issue: the one office tracker set (13 trackers) with field definitions, status codes, turnaround defaults, numbering, update duties and evidence rules; tracker kit in BABOOM-BIM-STANDARD\01-TEMPLATES\04-DOCUMENT-CONTROL\03-TRACKERS, built from the office forms, the office and client registers found on the office servers, and the prior art below. Decisions O-DEC-170, O-DEC-173–O-DEC-180, O-DEC-182. |

# 1 Purpose ownership and basis

Every project keeps one set of trackers: the indexes of every submittal, RFI, authority submission, drawing issue, site instruction, inspection, nonconformity, variation, meeting action, design change, deliverable, handover document and review comment. The document controller owns the set on each project; each tracker has one updating role (§5). The BIM Manager owns this standard and the kit; the QA/QC lead computes the BBM-STD-98 KPIs from it. The registers named in the BBM-STD-97 checklists ("submittal register", "RFI register", "NCR register", "instruction register", "visit report register", "document register", "handover register") are these trackers (O-DEC-178). Architect of Record duties that produce the records are in BBM-STD-13.

Basis: what the office already had. A read-only survey on 2026-11-05 of \\BABOOM\specification, \\BABOOM\Ongoing, \\BABOOM\Finished, \\Aws\share and \\Alaa\share (names, sizes and dates; byte copies read in a scratch folder; source modification times checked unchanged before and after; no project rows, names or values reused) found the registers below. Each tracker takes its structure from them and only adds what the prior art and the office codes require.

| Found in office practice (generic description) | Used for |
| --- | --- |
| Office supervision forms (Oct 2021), already in 01-TEMPLATES\04-DOCUMENT-CONTROL | The record behind each tracker row; review codes A–E and "Approved /​ Approved as noted /​ Not approved" decisions; SOR 3-day rule |
| Construction QA/​QC log set held on a PC share (material, shop drawing, method statement submittal logs; RFI, work and material inspection logs; NCR, SOR and quality-finding logs; document submittal log): dashboard block, review duration, A/​B/​C/​D/​UR legend, REV 0–6 history, NCR 14-day close-out, root cause, corrective action and verification columns | TRK-SUB, TRK-RFI, TRK-IR, TRK-NCR fields and dashboard measures |
| Site submittal registers (per-discipline sheets; transmittal ref, supplier, rev, internal action, status AA/​AN/​RR/​D/​UR, received from contractor → submitted to client → received from client → returned to contractor) | TRK-SUB one row per revision and the client relay dates |
| Authority tracking sheets per project (stage milestones with plan/​actual start and approval, dated updates log, application reference, action by; Dubai NOC columns) | TRK-NOC step list (BBM-STD-13 §5), Updates and Action by columns |
| Client and AOR comment trackers (document, rev, section, review comment, reviewer, status, response, final disposition; levels 0–4) | TRK-CMT and the level rule (O-DEC-173) |
| Design and supervision variation logs; variation summary with letter references and amounts | TRK-VO including services variations |
| Meeting minutes workbooks with numbered items; project status /​ tracking sheets | TRK-MOM meetings and actions |
| Deliverables lists per stage and discipline; MIDP Progress sheet (BBM-STD-MIDP) | TRK-DEL (MIDP Progress columns, O-DEC-178) |
| Drawing issue registers (sheet no, title, scale, stage, rev) and transmittal forms | TRK-DWG drawing register and transmittal log |
| Close-out registers (O&M manuals, as-built drawings, warranty certificates, spare parts, keys and access cards) | TRK-HO categories and fields |
| Submittal log summaries by type and code A–D /​ under review | Dashboard measures |
| Not found on any server: a site instruction form, a design change notice and a generic minutes template | Built 2026-11-05 in the office design system: 02-SUPERVISION-FORMS/​BBM-FRM-SUP-SITE-INSTRUCTION-v01.docx, 01-TRANSMITTAL-RFI/​BBM-FRM-DC-DESIGN-CHANGE-NOTICE-v01.docx, 01-TRANSMITTAL-RFI/​BBM-FRM-DC-MINUTES-OF-MEETING-v01.docx (generator 10.TRACKERS/​build_forms.py) |

Prior art read 2026-11-05. Procore submittals (default responses Approved, Approved as noted, Revise and resubmit, Rejected; ball in court; required-on-site minus lead time minus review time back-calculation) and RFI fields (due date from default days, status Draft/Open/Closed); Autodesk Construction Cloud Build submittals (manager, responsible contractor, required and optional reviewers, revisions, Void) and RFIs (Open waiting / In review / Answered / Closed / Void); Oracle Aconex document register (document number, revision, review status, transmittal) and workflow lateness in working days; AIA G710, G714, G716 (instructions, change directives, RFIs); FIDIC 2017 (21-day review, written instructions, Sub-Clause 13.3 variations, Sub-Clause 10.1 taking over); BBM-STD-57 submission register and the MIDP.

# 2 The one tracker set

| Code | Workbook (03-TRACKERS) | Records | Office form behind the row | Updated by | KPI |
| --- | --- | --- | --- | --- | --- |
| TRK-SUB | BBM-FRM-TRK-01-SUBMITTALS-v01.xlsx | Material, shop drawing, method statement, subcontractor, sample, as-built, programme submittals | 04 01, 04 03, 04 05, 04 08 | Supervising engineer (document controller logs receipt) | K-SV-02 |
| TRK-RFI | BBM-FRM-TRK-02-RFI-v01.xlsx | Requests for information | RFI forms | Document controller logs; discipline lead answers | K-SV-03 |
| TRK-NOC | BBM-FRM-TRK-03-AUTHORITY-NOC-v01.xlsx | Authority submissions, NOCs, permits, phase reports, completion approvals | Authority checklists (BBM-STD-85) | Authority liaison | K-AU-01, K-AU-02 |
| TRK-DWG | BBM-FRM-TRK-04-DRAWING-REGISTER-TRANSMITTALS-v01.xlsx | Drawing register; transmittal log | Project Transmittal, Transmittal Form | Document controller | K-DC-01 |
| TRK-SI | BBM-FRM-TRK-05-SITE-INSTRUCTIONS-v01.xlsx | Site instructions; site visit reports | Site Instruction; SOR /​ Field Observation | Supervising /​ resident engineer | K-SV-01 |
| TRK-NCR | BBM-FRM-TRK-06-NCR-SOR-v01.xlsx | SOR, field observations, NCRs | NCR, SOR, Field Observation | Supervising /​ resident engineer | K-SV-04 |
| TRK-VO | BBM-FRM-TRK-07-VARIATIONS-v01.xlsx | Works variations and services variations | VO Template | Supervising engineer; project manager for services | – |
| TRK-MOM | BBM-FRM-TRK-08-MEETINGS-ACTIONS-v01.xlsx | Meetings; actions | Minutes of Meeting; Contractor's Monthly Report | Meeting secretary (project manager) | – |
| TRK-DCN | BBM-FRM-TRK-09-DESIGN-CHANGES-v01.xlsx | Design changes | Design Change Notice | Project manager /​ lead design consultant | – |
| TRK-DEL | BBM-FRM-TRK-10-DELIVERABLES-v01.xlsx | Deliverable status snapshots (MIDP Progress) | MIDP | Information manager | – |
| TRK-IR | BBM-FRM-TRK-11-INSPECTION-REQUESTS-v01.xlsx | Work and material inspection requests | Inspection Request, Material Inspection Request | Supervising /​ resident engineer | – |
| TRK-HO | BBM-FRM-TRK-12-HANDOVER-OM-v01.xlsx | O&M, as-built, warranties, spares, keys, T&C, certificates, asset data | Handing over and taking over certificates, snagging list | Supervising engineer with document controller | – |
| TRK-CMT | BBM-FRM-TRK-13-REVIEW-COMMENTS-v01.xlsx | Review comments from client, authority, peer and AOR reviews | Comment sheets (QP-03) | Discipline lead responding; reviewer closes | K-DR-02 |

TRK-NOC keeps the 23 columns of the BBM-STD-57 §4 submission register first and in order, and TRK-DEL the MIDP Progress columns, so a project keeps one of each and never both (O-DEC-178). The 13th tracker, TRK-CMT, is the one the office already uses most (O-DEC-182).

Every workbook has the same sheets: Read me (use, field list), Dashboard (counts, overdue, on-time %, average days, KPI, by-discipline matrix; formulas only), Settings (project codes, data date, turnaround days, weekend, holidays), the register sheet(s) with 500 pre-formulated rows, and Lists (all drop-downs). White cells are typed; grey cells are formulas and are never overwritten. The kit carries no sample data.

# 3 Numbering

•  Record IDs read <PROJ>-<KIND>-<ROLE>-<NNNN> and are formulas from the Settings PROJ code, the KIND, the 1-letter ROLE (BBM-STD-93 §2) and the sequence; a sequence number is never reused (O-DEC-177). Example (synthetic): P001-SD-A-0007.

•  KIND values: submittals MS material, SD shop drawing, MT method statement, SC subcontractor/supplier, SP sample/mock-up, AB as-built, TS programme, DS other document; RFI; NOC; TRN transmittal; SI; SVR site visit report; SOR, FO, NCR; VI variation by instruction, VP by request for proposal, VC contractor claim, VS services variation; MOM (actions are <meeting no>/<item>); DCN; WIR, MIR; HO; CMT. TRK-DEL uses the MIDP DeliveryID and TRK-DWG the container ID CLIENT-BBM-PROJ-VOLUME-LEVEL-TYPE-ROLE-NUMBER (BBM-STD-93 §2.2).

•  Revisions are numbers 0, 1, 2 … shown R00, R01 (BBM-STD-93 §3). A resubmission is a new row with the same ID and the next revision; the "Current" formula marks the latest and the dashboard counts current rows only; "Cycles" counts the submissions of an ID (O-DEC-175).

•  A project copy of a workbook is a container named CLIENT-BBM-PROJ-ZZ-XX-SH-Z-NNNN.xlsx and lives in the project CDE; the library file is never filled in.

# 4 Status codes

| Code set | Values | Used in | Rule |
| --- | --- | --- | --- |
| Construction review code | A Approved, B Approved as noted, C Revise and resubmit, D Rejected, E Information/​records, UR Under review | TRK-SUB, TRK-IR, TRK-HO | Office forms; maps to the gate outcome only where a gate needs it: A→A, B→B, C and D→C (O-DEC-174) |
| Client decision | No objection - proceed, Objection - resubmit, Not required | TRK-SUB | Separate from the consultant code |
| Authority status | Unverified, Planned, Submitted, Conditionally approved, Approved, Rejected, Expired, Not applicable | TRK-NOC | BBM-STD-93 §7 canonical vocabulary |
| Comment level | 0 Rejected, 1 Significant, 2 Minor, 3 Closed, 4 Note | TRK-CMT | Level 2 not answered at the next review becomes Level 1 (O-DEC-173) |
| NCR /​ SOR | Open, Closed (formula from the close-out date); consultant decision on the corrective action Approved, Approved as noted, Not approved | TRK-NCR | Closed only with the verifying inspection request |
| RFI | Open, Answered, Closed, Void | TRK-RFI | Closed when the originator confirms |
| Site instruction | Issued, Acknowledged, Executed, Closed, Cancelled | TRK-SI |  |
| Variation | Draft, Under evaluation, Recommended, Approved, Rejected, Withdrawn | TRK-VO | Employer approves |
| Action | Open, In progress, Closed, Carried, Dropped | TRK-MOM |  |
| Design change | Pending, Approved, Rejected, Deferred | TRK-DCN |  |
| Deliverable | Not started, In progress, Shared, Submitted, Accepted, Rejected, On hold | TRK-DEL |  |
| Handover item | Not submitted, Submitted, Under review, Approved, Rejected | TRK-HO |  |
| Suitability, CDE state | SU-WIP … SU-ISSUE; WIP, Shared, Published, Archive | TRK-DWG | BBM-STD-93 §3, §4 |

# 5 Turnaround targets and update duties

The defaults below sit in each workbook's Settings sheet; the construction contract or appointment replaces them per project (O-DEC-176). Working days use the Settings weekend (Saturday and Sunday) and holiday list. Ageing and overdue flags are computed against the Settings data date (O-DEC-180).

| Tracker | Clock starts | Default | Flag | KPI and target (BBM-STD-98) |
| --- | --- | --- | --- | --- |
| TRK-SUB | Complete submittal received | 14 calendar days | OVERDUE until returned; On time /​ Late | K-SV-02 >= 90% |
| TRK-RFI | RFI received | 7 calendar days, or the originator's date if earlier | OVERDUE until answered | K-SV-03 >= 90% |
| TRK-NOC | Submitted | Authority service days per row, else 14 calendar days; expiry warning 30 days | OVERDUE, EXPIRING, EXPIRED | K-AU-01 >= 80%; K-AU-02 <= 1.3 |
| TRK-DWG | Transmittal date | Acknowledgement 2 working days | OVERDUE until acknowledged | K-DC-01 100% |
| TRK-SI | Instruction issued; visit date | Acknowledgement 2 working days; visit report 2 working days | OVERDUE | K-SV-01 >= 95% |
| TRK-NCR | Issued | SOR /​ FO 3 working days; NCR close-out 14 calendar days | OVERDUE until closed | K-SV-04 baseline |
| TRK-VO | Complete proposal received | 14 calendar days to recommendation | OVERDUE | – |
| TRK-MOM | Meeting date; action raised | Minutes 2 working days; actions by the agreed date | OVERDUE | – |
| TRK-DCN | Raised | Decision at the next coordination meeting | Days open | – |
| TRK-DEL | Baseline date | MIDP baseline | LATE | – |
| TRK-IR | Submitted | At least 1 working day before the requested inspection | Short notice; OVERDUE if not inspected by the requested date | – |
| TRK-HO | Taking-over date | Warranty end; warning 30 days | EXPIRING, EXPIRED; shortfall | – |
| TRK-CMT | Comment received | 10 working days, or by the next issue | OVERDUE until responded | K-DR-02 >= 95% |

Update duties: a row is opened the working day the record is received or issued (QP-10 §5: incoming items logged within 1 working day); the updating role in §2 closes it the day the decision goes out; the document controller checks every tracker weekly against the CDE; the QA/QC lead reports the KPIs monthly or quarterly per BBM-STD-98 from a dated snapshot (data date fixed, dashboard printed to PDF).

# 6 Evidence rules

•  The tracker is an index; the signed form, transmittal or authority decision in the CDE is the record. A row is closed only with its "Evidence (CDE link)" filled (O-DEC-179).

•  Rows are never deleted. A row raised in error is set Void (or Cancelled / Withdrawn / Dropped) with the reason in Remarks.

•  A resubmission never overwrites the earlier row; the earlier decision stays as evidence of the cycle.

•  When the office refuses to sign or stamp (BBM-STD-13 §7) the row says "held: <condition>" in Remarks.

•  Authority rows carry the receipt or application number once submitted; "Approved" needs the decision document.

•  Reported snapshots are kept as PDF with data date, population and period (BBM-STD-83 stale-snapshot rule); project trackers are retained with the project record (BBM-STD-90).

•  Trackers hold no personal data beyond names and roles needed for the record; contact details stay in the project directory.

# 7 Field definitions

The tables are generated from the kit builder (50.TOOLING/52.AEC-LIBRARIES/52.03-BBM-STANDARD/10.TRACKERS/build_trackers.py --md), the one source of the workbooks; a field change is made there and the kit and this section are rebuilt together.

## TRK-SUB Submittals register (material, shop drawing, method statement, subcontractor, sample, as-built)

File 03-TRACKERS/BBM-FRM-TRK-01-SUBMITTALS-v01.xlsx. One row per submittal revision from the contractor: review against the contract documents, office code A-E, client decision, cycles and turnaround. Office form: Material Submittal 04 01, Shop Drawing Submittal 04 03, SubContractor Submittal 04 05, Time Schedule Approval 04 08 (02-SUPERVISION-FORMS). KPI: K-SV-02 Submittals reviewed within the contract period (>= 90%).

Sheet "Register":

| Field | Type | Rule |
| --- | --- | --- |
| Record ID | formula | Formula: PROJ-KIND-ROLE-NNNN (O-DEC-177). Do not type |
| Kind | list SUBKIND | MS material, SD shop drawing, MT method statement, SC subcontractor/​supplier, SP sample/​mock-up, AB as-built, TS programme, DS other document |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Rev | rev | Revision 0, 1, 2 … shown R00, R01; a resubmission is a new row with the next revision (O-DEC-175) |
| Current | formula | Formula: Y on the latest revision of the ID; only current rows count on the dashboard |
| Cycles | formula | Formula: number of submissions of this ID |
| Description | text | Item or drawing set |
| Spec section /​ drawing ref | text | Contract reference reviewed against |
| Manufacturer /​ supplier | text |  |
| Origin | text | Country of origin (materials) |
| Priority | list PRIORITY |  |
| Contractor transmittal ref | text |  |
| Required on site | date | Date the approved item is needed on site |
| Lead time (days) | num | Manufacture and delivery |
| Submit by | formula | Formula: required on site - lead time - review days (back-calculated, Procore practice) |
| Received | date | Date the complete submittal was received |
| Reviewer | text | Discipline reviewer |
| Sent to client | date | Where the appointment requires client review |
| Returned by client | date |  |
| Client decision | list CLIENTDEC | As on the office forms |
| Code | list REVIEW | A Approved, B Approved as noted, C Revise and resubmit, D Rejected, E Information/​records, UR Under review (O-DEC-174) |
| Returned to contractor | date | Closes the review |
| Due | formula | Formula: Received + TA_SUB calendar days (Settings) |
| Days open | formula | Formula: Returned to contractor (or the data date) minus Received |
| Overdue | formula | Formula: OVERDUE when no Returned to contractor and the data date is past Due |
| On time | formula | Formula: Returned to contractor on or before Due |
| Status | formula | Formula: the code once returned, otherwise UR |
| Rating credit affected | list YN | Y when a sustainability credit depends on it (QP-06) |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-RFI Requests for information register

File 03-TRACKERS/BBM-FRM-TRK-02-RFI-v01.xlsx. One row per RFI: question, references, owner, answer, cost and time impact, turnaround. Office form: Request For Information; RFI form (01-TRANSMITTAL-RFI). KPI: K-SV-03 RFIs answered within the agreed time (>= 90%).

Sheet "Register":

| Field | Type | Rule |
| --- | --- | --- |
| Record ID | formula | Formula: PROJ-KIND-ROLE-NNNN (O-DEC-177). Do not type |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Subject | text |  |
| Question | text |  |
| References | text | Drawings, specification, submittal |
| Raised by | list PARTY |  |
| Raised | date | Date received |
| Required by | date | Date asked for by the originator |
| Priority | list PRIORITY |  |
| Assigned to | text | Discipline lead answering |
| Answer | text |  |
| Answered | date | Date the answer was sent |
| Variation | list YNT | "This clarification will constitute a variation" (office form) |
| Time impact | list YNT |  |
| Revised drawing /​ SI ref | text |  |
| Status | list RFISTATUS | Open, Answered, Closed (originator confirmed), Void |
| Due | formula | Formula: earlier of Required by and Raised + RFI days |
| Days open | formula | Formula: Answered (or the data date) minus Raised |
| Overdue | formula | Formula: OVERDUE when no Answered and the data date is past Due |
| On time | formula | Formula: Answered on or before Due |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-NOC Authority submissions and NOC register (BBM-STD-57 submission register in working form)

File 03-TRACKERS/BBM-FRM-TRK-03-AUTHORITY-NOC-v01.xlsx. One row per authority submission cycle, in the office authority sequence (registration, studies, NOCs, preparatory, access, municipality, design, construction, completion). Office form: Authority checklists per BBM-STD-85; QP-07 checklist 06-SUBMISSIONS. KPI: K-AU-01 First-time authority approval rate (>= 80%); K-AU-02 Authority comment rounds per submission (<= 1.3).

Sheet "Register":

| Field | Type | Rule |
| --- | --- | --- |
| SubmissionID | formula | Formula: PROJ-NOC-ROLE-NNNN; the BBM-STD-57 SubmissionID |
| ProjectID | formula | Formula from Settings |
| PlotID | text | Plot /​ affection plan reference |
| Gate | list GATE | BBM-STD-93 §6 authority gate |
| Authority | list AUTHORITY |  |
| Service and profile ID | text | Authority service, NOC or permit (BBM-STD-85 profile) |
| InstrumentIDs | text | BBM-STD-57 codes register rows |
| Required contents | text | Checklist revision downloaded on the submission date |
| Prerequisite IDs | text |  |
| NOC dependency IDs | text |  |
| Producer | text |  |
| Checker | text |  |
| Authoriser | text | LAP authorisation before upload |
| Information recipient | text |  |
| Planned date | date | Planned submission |
| Actual receipt | text | Authority receipt /​ application number (required once submitted) |
| Authority decision | list NOCSTATUS | BBM-STD-93 §7 canonical status |
| Conditions and expiry | text | Every condition; activity released only when closed |
| BoD row | text | BBM-STD-12 approval /​ criterion row |
| MIDP row | text |  |
| State | list RECSTATE |  |
| Source revision | text |  |
| ChangeID | text |  |
| Step | list NOCGROUP | Office authority sequence (BBM-STD-13 §5) |
| Jurisdiction | list JURIS |  |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Rev | rev | Revision 0, 1, 2 … shown R00, R01; a resubmission is a new row with the next revision (O-DEC-175) |
| Current | formula | Formula: Y on the latest revision of the ID; only current rows count on the dashboard |
| Cycles | formula | Formula: number of submissions of this ID |
| Submitted | date | Actual upload date |
| Service days | num | Authority service time; blank = Settings TA_NOC |
| Decision date | date | Date of the authority decision |
| Expiry date | date | From the decision; blank = no expiry stated |
| Due | formula | Formula: Submitted + service days |
| Days open | formula | Formula: Decision date (or the data date) minus Submitted |
| Overdue | formula | Formula: OVERDUE when no Decision date and the data date is past Due |
| Expiring | formula | Formula: EXPIRED /​ EXPIRING within the warning days |
| Action by | list PARTY | Ball in court |
| Updates | text | Dated log: "dd-mm: what happened" |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-DWG Drawing register and transmittal log

File 03-TRACKERS/BBM-FRM-TRK-04-DRAWING-REGISTER-TRANSMITTALS-v01.xlsx. Drawing register: one row per container (drawing, model, report) with its latest issue computed from the transmittal log; transmittal log: one row per container per transmittal. Office form: Project Transmittal; Transmittal Form (01-TRANSMITTAL-RFI). KPI: K-DC-01 Transmittals acknowledged within the agreed time (proxy for complete issue records) (100%).

Sheet "Drawing register":

| Field | Type | Rule |
| --- | --- | --- |
| Container ID | formula | Formula: CLIENT-ORG-PROJ-VOLUME-LEVEL-TYPE-ROLE-NUMBER (BBM-STD-93 §2.2; ORG = BABOOM) |
| VOLUME | text | ZZ, XX or 01-99 |
| LEVEL | text | ZZ, XX, GF, RF, 01-99, B1, M1 |
| TYPE | text | DR, M3, RP, SP … (BBM-STD-93 §2.2) |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| NUMBER | num | 0001-9999, never reused |
| Sheet number | text | DISC-CAT-INDEX |
| Title | text |  |
| Scale | text |  |
| Size | text | A0-A4 |
| Stage | list STAGE | RIBA stage |
| Latest issue | formula | Formula: latest transmittal date of this container |
| Current rev | formula | Formula: highest revision issued (blank before the first issue or at R00) |
| Issues | formula | Formula: number of issues |
| CDE state | list CDE |  |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

Sheet "Transmittal log":

| Field | Type | Rule |
| --- | --- | --- |
| Transmittal no | formula | Formula: PROJ-TRN-ROLE-NNNN (one number per transmittal) |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Date | date | Issue date |
| To | list PARTY |  |
| Recipient | text | Organisation /​ person |
| Container ID | text | Copy from the drawing register (one row per container) |
| Rev | rev | Revision 0, 1, 2 … shown R00, R01; a resubmission is a new row with the next revision (O-DEC-175) |
| Suitability | list SUIT | BBM-STD-93 §3 |
| Purpose | text | Approval, information, construction, tender, record |
| Format | list FORMAT |  |
| Approved by | text | Approval before sending (QP-10 §4) |
| Acknowledged | date | Receipt acknowledged |
| Due | formula | Formula: Date + TA_TRN working days (Settings weekend and holidays) |
| Overdue | formula | Formula: OVERDUE when no Acknowledged and the data date is past Due |
| On time | formula | Formula: Acknowledged on or before Due |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-SI Site instructions and site visit reports

File 03-TRACKERS/BBM-FRM-TRK-05-SITE-INSTRUCTIONS-v01.xlsx. Site instructions: written, within the consultant authority, client approval where cost or time changes. Site visit reports: one row per visit (KPI K-SV-01). Office form: Site Instruction (02-SUPERVISION-FORMS); Field Observation / SOR forms for observations. KPI: K-SV-01 Site visit reports issued on time (>= 95%).

Sheet "Site instructions":

| Field | Type | Rule |
| --- | --- | --- |
| Record ID | formula | Formula: PROJ-KIND-ROLE-NNNN (O-DEC-177). Do not type |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Issued | date |  |
| Subject | text |  |
| Instruction | text |  |
| Origin | text | RFI, NCR, DCN, client request (record ref) |
| Contract clause | text | Authority basis, e.g. FIDIC 3.5 |
| Client approval needed | list YN | Y where cost or time changes |
| Client approval ref | text |  |
| Cost impact | list IMPACT |  |
| Time impact | list IMPACT |  |
| VO ref | text | TRK-VO record |
| Acknowledged | date | Contractor acknowledgement |
| Status | list SISTATUS |  |
| Due | formula | Formula: Issued + TA_SI working days (Settings weekend and holidays) |
| Days open | formula | Formula: Acknowledged (or the data date) minus Issued |
| Overdue | formula | Formula: OVERDUE when no Acknowledged and the data date is past Due |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

Sheet "Site visit reports":

| Field | Type | Rule |
| --- | --- | --- |
| Report no | formula | Formula: PROJ-SVR-ROLE-NNNN |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Visit date | date |  |
| Visited by | text |  |
| Areas /​ activities | text |  |
| Observations raised | num | Number of SOR/​FO raised (TRK-NCR) |
| Report issued | date |  |
| Due | formula | Formula: Visit date + TA_SVR working days (Settings weekend and holidays) |
| Overdue | formula | Formula: OVERDUE when no Report issued and the data date is past Due |
| On time | formula | Formula: Report issued on or before Due |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-NCR Non-conformance, site observation and field observation register

File 03-TRACKERS/BBM-FRM-TRK-06-NCR-SOR-v01.xlsx. SOR and field observations answered in 3 working days or converted to an NCR; NCR closed only after the corrective action is verified by an approved inspection request. Office form: NCR, Site Observation Report (SOR), Field Observation (02-SUPERVISION-FORMS). KPI: K-SV-04 Design-origin site NCRs (count; divide by 10,000 m2 GFA under construction for the KPI) (Baseline).

Sheet "Register":

| Field | Type | Rule |
| --- | --- | --- |
| Record ID | formula | Formula: PROJ-KIND-ROLE-NNNN (O-DEC-177). Do not type |
| Kind | list NCRKIND | SOR site observation, FO field observation, NCR non-conformance |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Issued | date |  |
| Location | text |  |
| Level | text |  |
| Description | text |  |
| Requirement type | list NCRREF | Document not conformed with (office NCR form) |
| Requirement ref | text |  |
| Originator | text |  |
| Severity | list SEV |  |
| Root cause | list ROOT |  |
| Design origin | list YN | Y raises an office NC under QP-11 |
| Contractor reply | list AGREE |  |
| Corrective action proposed | date |  |
| Consultant decision | list DECISION3 | On the proposed corrective action |
| Implemented | date | Contractor implementation date |
| Verification IR | text | Approved IR closing it (TRK-IR) |
| Closed | date | Close-out date |
| Converted to NCR | text | For SOR/​FO not answered in time: the NCR ID |
| Due | formula | Formula: NCR = Issued + NCR days; SOR/​FO = Issued + SOR working days |
| Days open | formula | Formula: Closed (or the data date) minus Issued |
| Overdue | formula | Formula: OVERDUE when no Closed and the data date is past Due |
| Status | formula | Formula: Closed once the close-out date is entered |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-VO Variations register (works and consultant services)

File 03-TRACKERS/BBM-FRM-TRK-07-VARIATIONS-v01.xlsx. One row per variation: origin, proposal, consultant valuation, employer approval, time; services variations of the office appointment too (BBM-STD-13 §3). Office form: VO Template (02-SUPERVISION-FORMS).

Sheet "Register":

| Field | Type | Rule |
| --- | --- | --- |
| Record ID | formula | Formula: PROJ-KIND-ROLE-NNNN (O-DEC-177). Do not type |
| Kind | list VOKIND | VI by instruction, VP by request for proposal, VC contractor claim, VS services variation of the consultant appointment |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Initiated | date |  |
| Origin ref | text | SI, RFI, DCN, client letter |
| Description | text |  |
| Proposal received | date | Complete proposal |
| Proposal amount | num |  |
| Consultant valuation | num |  |
| Approved amount | num | Employer-approved |
| Days claimed | num |  |
| Days agreed | num |  |
| Recommended | date | Consultant recommendation sent |
| Employer decision | date |  |
| Status | list VOSTATUS |  |
| Cumulative approved | formula | Formula: approved total up to this row date |
| % of contract | formula | Formula: cumulative approved /​ contract sum |
| Due | formula | Formula: Proposal received + TA_VO calendar days (Settings) |
| Days open | formula | Formula: Recommended (or the data date) minus Proposal received |
| Overdue | formula | Formula: OVERDUE when no Recommended and the data date is past Due |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-MOM Meetings and action log

File 03-TRACKERS/BBM-FRM-TRK-08-MEETINGS-ACTIONS-v01.xlsx. Meetings: one row per meeting with minutes issue time. Actions: one row per numbered action with owner, due date and close-out. Office form: Minutes of Meeting (01-TRANSMITTAL-RFI); Contractor's Monthly Report format (02-SUPERVISION-FORMS).

Sheet "Meetings":

| Field | Type | Rule |
| --- | --- | --- |
| Meeting no | formula | Formula: PROJ-MOM-ROLE-NNNN |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Type | list MTYPE |  |
| Date | date |  |
| Chair | text |  |
| Attendees | text | Organisations |
| Minutes issued | date |  |
| Due | formula | Formula: Date + TA_MOM working days (Settings weekend and holidays) |
| Overdue | formula | Formula: OVERDUE when no Minutes issued and the data date is past Due |
| On time | formula | Formula: Minutes issued on or before Due |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

Sheet "Actions":

| Field | Type | Rule |
| --- | --- | --- |
| Action ID | formula | Formula: meeting number /​ item |
| Meeting no | text | Copy from Meetings |
| Item | num |  |
| Action | text |  |
| Owner | list PARTY |  |
| Owner person | text |  |
| Raised | date |  |
| Due | date | Agreed in the meeting |
| Status | list ACTSTATUS |  |
| Closed | date |  |
| Closed at meeting | text |  |
| Days open | formula | Formula: Closed (or the data date) minus Raised |
| Overdue | formula | Formula: OVERDUE when no Closed and the data date is past Due |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-DCN Design change log

File 03-TRACKERS/BBM-FRM-TRK-09-DESIGN-CHANGES-v01.xlsx. One row per design change: origin, affected containers and disciplines, cost, programme, fee and authority impact, decision and the issue that implements it. Office form: Design Change Notice (01-TRANSMITTAL-RFI); MIDP Changes sheet for plan-baseline changes.

Sheet "Register":

| Field | Type | Rule |
| --- | --- | --- |
| Record ID | formula | Formula: PROJ-KIND-ROLE-NNNN (O-DEC-177). Do not type |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Raised | date |  |
| Origin | list DCNORIGIN |  |
| Stage | list STAGE | RIBA stage |
| Description | text |  |
| Reason | text |  |
| Affected containers | text | Container IDs /​ sheet numbers |
| Affected disciplines | text | ROLE letters |
| Cost impact | num | Estimate |
| Programme impact (days) | num |  |
| Fee impact | list YN | Y raises a TRK-VO kind VS |
| Authority re-approval | list YN | Y raises a TRK-NOC row |
| Decision | list DCNDEC |  |
| Decided by | text |  |
| Decision date | date |  |
| Implemented in | text | Transmittal /​ revision |
| MIDP ChangeID | text | Plan-baseline change where dates move |
| Days open | formula | Formula: Decision date (or the data date) minus Raised |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-DEL Deliverables status (MIDP Progress in working form)

File 03-TRACKERS/BBM-FRM-TRK-10-DELIVERABLES-v01.xlsx. One row per delivery and snapshot, with the MIDP Progress columns in order (O-DEC-178); a project keeps this or the MIDP workbook Progress sheet, never both. Office form: BBM-STD-MIDP Progress sheet (04-DOCUMENTS).

Sheet "Register":

| Field | Type | Rule |
| --- | --- | --- |
| DeliveryID | text | MIDP DeliveryID |
| SnapshotDate | date |  |
| Baseline dates | date | Baseline submission |
| forecast dates | date | Forecast submission |
| actual started timestamps | date |  |
| Shared timestamps | date |  |
| submitted timestamps | date |  |
| accepted timestamps | date |  |
| stage evidence | text |  |
| status | list DELSTATUS |  |
| remaining duration | num | Days |
| issue/​blocker IDs | text |  |
| variance | formula | Formula: forecast - baseline (days) |
| next action | text |  |
| owner | text |  |
| due | date |  |
| Description | text | Added: deliverable title |
| Stage | list STAGE | Added |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Late | formula | Formula: LATE when not submitted and the baseline date has passed |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-IR Inspection requests register (work and material)

File 03-TRACKERS/BBM-FRM-TRK-11-INSPECTION-REQUESTS-v01.xlsx. One row per inspection request revision: hold and witness points, result code, re-inspection and NCR links. Office form: Inspection Request; Material Inspection Request (02-SUPERVISION-FORMS).

Sheet "Register":

| Field | Type | Rule |
| --- | --- | --- |
| Record ID | formula | Formula: PROJ-KIND-ROLE-NNNN (O-DEC-177). Do not type |
| Kind | list IRKIND | WIR work inspection, MIR material inspection |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Rev | rev | Revision 0, 1, 2 … shown R00, R01; a resubmission is a new row with the next revision (O-DEC-175) |
| Current | formula | Formula: Y on the latest revision of the ID; only current rows count on the dashboard |
| Cycles | formula | Formula: number of submissions of this ID |
| Submitted | date |  |
| Requested inspection | date | Date (and time in Remarks) |
| Activity /​ material | text |  |
| Location | text |  |
| Drawing /​ spec ref | text |  |
| Approved submittal ref | text | MIR: TRK-SUB record |
| ITP point | list HOLDPT |  |
| Inspected by | text |  |
| Inspected | date |  |
| Result | list REVIEW | A-E as on the office MIR form; UR pending |
| NCR raised | text | TRK-NCR record |
| Notice OK | formula | Formula: at least the notice working days before the requested date |
| Overdue | formula | Formula: not inspected by the requested date |
| Status | formula | Formula |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-HO Handover and O&M documents register

File 03-TRACKERS/BBM-FRM-TRK-12-HANDOVER-OM-v01.xlsx. One row per handover item: O&M manuals, as-built drawings, warranties, spare parts, extra material, keys, T&C, training, completion certificates, asset data. Office form: Initial / Final Handing Over Certificates, Taking Over Certificate, snagging list (02-SUPERVISION-FORMS); BBM-STD-75.

Sheet "Register":

| Field | Type | Rule |
| --- | --- | --- |
| Record ID | formula | Formula: PROJ-KIND-ROLE-NNNN (O-DEC-177). Do not type |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Category | list HOCAT |  |
| System | text |  |
| Title | text |  |
| Contract /​ spec ref | text | Section and clause |
| Supplier /​ company | text |  |
| Required qty | num | Spare parts, extra material, copies |
| Received qty | num |  |
| Format | list FORMAT |  |
| Submitted | date |  |
| Code | list REVIEW | A-E |
| Approved | date |  |
| Status | list HOSTATUS |  |
| Warranty start (TOC) | date | Taking-over date |
| Warranty months | num |  |
| Warranty end | formula | Formula: start + months |
| Expiring | formula | Formula |
| Shortfall | formula | Formula: required - received |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

## TRK-CMT Review comments tracker (client, authority, peer and AOR reviews)

File 03-TRACKERS/BBM-FRM-TRK-13-REVIEW-COMMENTS-v01.xlsx. One row per comment on a reviewed document: level 0-4, response, final disposition; an unanswered Level 2 becomes Level 1 at the next stage (O-DEC-173). Office form: Office practice: client and AOR comment trackers; QP-03 design review. KPI: K-DR-02 Review comments closed by next issue (>= 95%).

Sheet "Register":

| Field | Type | Rule |
| --- | --- | --- |
| Record ID | formula | Formula: PROJ-KIND-ROLE-NNNN (O-DEC-177). Do not type |
| ROLE | list ROLE | Discipline 1-letter ROLE (BBM-STD-93 §2) |
| Seq | num | Sequence per KIND and ROLE, from 1, never reused |
| Document | text | Container ID |
| Rev | rev | Revision 0, 1, 2 … shown R00, R01; a resubmission is a new row with the next revision (O-DEC-175) |
| Section | text | Volume /​ section /​ sheet |
| Reviewer party | list REVIEWER |  |
| Reviewer | text |  |
| Comment | text |  |
| Commented | date |  |
| Level | list CMTLEVEL | 0 Rejected, 1 Significant, 2 Minor, 3 Closed, 4 Note |
| Response | text |  |
| Responder | text |  |
| Responded | date |  |
| Final disposition | list DISPO | By the reviewer |
| Closed in rev | text |  |
| Status | formula | Formula: closed at Level 3/​4 or accepted |
| Due | formula | Formula: Commented + TA_CMT working days (Settings weekend and holidays) |
| Days open | formula | Formula: Responded (or the data date) minus Commented |
| Overdue | formula | Formula: OVERDUE when no Responded and the data date is past Due |
| Evidence (CDE link) | text | Link to the signed form, transmittal or decision; required to close (O-DEC-179) |
| Remarks | text | Free text; "held: <condition>" when the office refuses to sign |

# 8 Acceptance

| Check | Evidence |
| --- | --- |
| One set | Each project holds one copy of each tracker it needs, named as a container, and no other register of the same records |
| Valid kit | Every workbook opens in Excel with 0 formula errors, blank and with a test row (build check 2026-11-05) |
| Settings filled | PROJ, CLIENT, holidays and contract turnaround days entered before the first row |
| Evidence | Every closed row has a CDE link |
| KPIs | BBM-STD-98 KPIs reported from dated dashboard snapshots |

# References

All checked 2026-11-05.

•  Procore, default submittal responses: https://v2.support.procore.com/faq-what-are-the-default-submittal-responses-in-procore; submittal project configurations (lead time, review times, planned dates, ball in court): https://v2.support.procore.com/process-guides/best-practices-submittals/project-configurations; RFI field descriptions: https://v2.support.procore.com/fieldlist-rfi-field-descriptions

•  Autodesk Construction Cloud Build, process submittal items: https://help.autodesk.com/view/BUILD/ENU/?guid=Process_Submittal; submittal roles: https://help.autodesk.com/cloudhelp/ENU/Build-Submittals/files/admin-submittals/Submittals_Permissions.html; process RFI: https://help.autodesk.com/cloudhelp/ENU/Build-Rfis/files/work-rfis/Process_RFI.html

•  Oracle Aconex, documents subject area (register, revision, review status, transmittal): https://docs.oracle.com/en/industries/construction-engineering/intelligence/subject-area-reference-guide/aconex---documents.html; reports glossary (workflow due and end dates, lateness): https://help.aconex.com/insights/reports-glossary

•  AIA contract administration forms G710, G714, G716: https://learn.aiacontracts.com/contract-doc-pages/27516-contract-administration-and-project-management-forms

•  FIDIC 2017 Rainbow Suite: https://fidic.org/sites/default/files/press%20release_rainbow%20suite_2018_03_1.pdf; Fenwick Elliott, the role of the Engineer in FIDIC 2017: https://www.fenwickelliott.com/sites/default/files/the_role_of_the_engineer_in_fidic_contracts_-_fenwick_elliott.pdf

•  UPPC Circular No. 9 of 2026 (phase reports): https://www.Project.ae/en/article/c2qm3pn-uppc-issues-circular-streamline-construction

•  Office: BBM-STD-13, 57, 83, 90, 93, 97, 98; BBM-STD-MIDP; office forms in BABOOM-BIM-STANDARD\01-TEMPLATES\04-DOCUMENT-CONTROL; tracker kit in 03-TRACKERS there.