## Read me
BBM-STD-97 Design review and coordination checklist V1.0
Design review and verification per discipline, interdisciplinary coordination and constructability (BBM-STD-97 QP-03, QP-04).
How to use
1. Save a copy into the project QA folder (03.REPORTS) named to the project naming register. Never work in the office copy.
2. Fill the header row on each sheet. Work every sheet that applies; Result is Pass, Fail or NA. NA needs a reason in Comment.
3. Mandatory = Y (crimson) must Pass or carry an approved scoped exception; a mandatory Fail is an NC under BBM-STD-97 QP-11.
4. Sign-off totals every sheet and holds the signatures. File the signed copy with the issue, submission or decision it supports.
5. Model, container, drawing-output and authority-BIM checks are in 07-QA-QC/01-BIM/BBM-STD-68-CHECKLIST-V1.0.xlsx; they are linked here, not repeated.
6. Rules behind these checks: BBM-STD-96 QMS manual, BBM-STD-97 quality procedures, BBM-STD-98 quality KPIs (04-DOCUMENTS).
Sheets
Sheet | ID prefix | Checks | Mandatory | What it covers
General | DR-GN | 11 | 11 | Every package review: brief, codes, independence, comments, calculations, change, risk, output.
ARC | DR-AR | 12 | 11 | Architecture design review (BBM-STD-58).
INT | DR-IN | 9 | 7 | Interior design review (BBM-STD-62). Discipline code INT (legacy tab "ID").
LSC | DR-LS | 8 | 6 | Landscape design review (BBM-STD-61).
STR | DR-ST | 8 | 7 | Structural design review (BBM-STD-59).
MEP | DR-MP | 10 | 10 | Mechanical, plumbing and electrical design review (BBM-STD-60).
FLS | DR-FL | 7 | 7 | Fire and life safety design review (BBM-STD-85 §5).
Coordination | DR-CO | 10 | 9 | Interdisciplinary coordination check before each issue (QP-04).
Constructability | DR-CB | 7 | 5 | Constructability review at Stage 3 end and before tender (QP-04 §5).
Source standards (primary sources, read 2026-11-04; edition register BBM-STD-51 §3)
Code | Source | Where
AIACR | AIA Best Practices: Reviewing a contract, what architects need to know | https://www.aia.org/sites/default/files/2025-12/AIA_BestPractices_Reviewingacontract-Whatarchitectsneed.pdf
AIAQC | AIA Best Practices: Quality control, preparation of working drawings; Managing quality in the design development phase | https://www.aia.org/sites/default/files/2025-12/AIA_BestPractices_Qualitycontrol-Preparationofworking.pdf
BABOOM | Office standards BBM-STD-xx (04-DOCUMENTS) and BBM-STD-96/97/98 (QMS) | 04-DOCUMENTS
BIMCL | Office BIM QA/QC checklist BBM-STD-68-CHECKLIST V1.0 (07-QA-QC/01-BIM): models, containers, drawings, IDS, authority BIM. Linked, not repeated | 07-QA-QC/01-BIM/BBM-STD-68-CHECKLIST-V1.0.xlsx
CSI | CSI/CSC SectionFormat/PageFormat (three-part section, page arrangement); MasterFormat 2020 Edition (50 divisions) | https://www.csiresources.org/standards/sectionformat-pageformat
DBC | Dubai Building Code 2021 edition (consultant demonstrates performance-based alternatives; check the latest version) | https://dmpmedia.dm.gov.ae/uploads/2021/12/Dubai%20Building%20Code_English_2021%20Edition_compressed.pdf
DMBP | Dubai Municipality building permit procedures and the single-window platform (request permit, unified inspection, execution and service delivery) | https://www.dm.gov.ae/municipality-business/building-permit-steps
DMQ | DM Administrative Resolution 255 of 2021 (consultancy classification categories) and 253 of 2021 (technical qualification of engineers) | https://dlp.dubai.gov.ae/Legislation%20Reference/2021/Administrative%20Resolution%20No.%20%28255%29%20of%202021%20Amending%20Administrative%20Resolution%20No.%20%2851%29%20of%201998.html
FHWA | FHWA Constructability Review Checklist (reviews at 50/70/95% and final; buildable, biddable, maintainable) | https://highways.dot.gov/media/49146
FIDIC | FIDIC Quality Management briefing note (2019) and Organisational and Project Quality report (firm system to project delivery, learning from failure) | https://fidic.org/policy/quality
ISO19650 | ISO 19650-2:2018 cl. 5.1-5.8 (appointment, information delivery, 5.6.3 check, 5.6.4 review, 5.7 acceptance) | https://www.iso.org/standard/68080.html
ISO9001 | ISO 9001:2026 Quality management systems, Requirements (Edition 6, published 16 Sep 2026; clauses 4-10 kept, 5.1.1 i) quality culture and ethical behaviour, 6.1.1-6.1.3 risks and opportunities split, 6.3 e)-g), 7.3 e), 9.3.2 c)) | https://www.iso.org/standard/9001
LEG | Office legacy document checklist BBM-QC-AR-00 (cover, index, title block, concept checks) | 07-QA-QC/98-ARCHIVE/BBM-QC-AR-00.xlsx
PANY | Port Authority NY&NJ Architectural Quality Control Checklist and Consultant Design Content Audit Checklist V1.0 (12 Jun 2026) | https://aemstage.panynj.gov/content/dam/port-authority/pdfs/-available-engineering-documents/ENG-CHECK-QCArchitectural.pdf
PBRS | Estidama Pearl Building Rating System, Design & Construction V1.0 (Apr 2010): IDP 13, NS 12, LB 37, PW 43, RE 44, SM 28, IP 3 bonus; 1 Pearl = all mandatory, 2 Pearl = +60 points | https://www.dmt.gov.ae/-/media/Project/DMT/DMT/E-Library/0001-Manuals/PBRS/PBRS-Version-10.pdf
RIBA | RIBA Plan of Work 2020 Overview: stages 0-7, Project Strategies, Quality Aspirations, Stage 5 "Inspect Construction Quality" | https://www.riba.org/work/insights-and-resources/riba-plan-of-work
SAFAT | Al Sa'fat Dubai Green Building System, 2nd edition (Jan 2023): sections 300 Ecology & Planning, 400 Building Vitality, 500 Energy, 600 Water, 700 Materials & Waste | https://dmpmedia.dm.gov.ae/uploads/2023/01/Al-Safat-%E2%80%93-Dubai-Green-Building-System-2nd-editionJan2023.pdf

## General
General
Every package review: brief, codes, independence, comments, calculations, change, risk, output.
Project code |  | Package / stage |  | Revision |  | RIBA stage |  | Reviewer |  | Review date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
DR-GN-01 | Basis | Package reviewed against the current brief, Basis of Design and appointment scope | Open the BoD (BBM-STD-12) and the appointment scope; compare the package contents line by line | Every brief/BoD requirement in scope is shown or listed as open with an owner | Y | BBM-STD-97 QP-03 §3; BBM-STD-12 | ISO9001, RIBA | 2-4
DR-GN-02 | Basis | Codes and editions used are the ones recorded for the plot | Compare code references on drawings/reports with the BBM-STD-51 §3 edition register and BBM-STD-57 §2 jurisdiction record | No superseded or unrecorded edition; every ED- key quoted | Y | BBM-STD-57 §2; BBM-STD-85 | DBC, BABOOM | 2-4
DR-GN-03 | Review | Review tier and reviewer recorded (L1 discipline, L2 cross-discipline, L3 committee) | Read the review record header | Tier, reviewer, date, package revision and scope filled | Y | BBM-STD-93 §8; BBM-STD-97 QP-03 §4 | ISO9001, FIDIC | All
DR-GN-04 | Review | Reviewer is independent of the author for the scope reviewed | Compare author and reviewer names per sheet/report | Author and checker are different competent people | Y | BBM-STD-55 §2; BBM-STD-97 QP-03 §4 | ISO9001, AIAQC | All
DR-GN-05 | Review | Previous review comments all closed or carried with owner | Open the previous comment sheet; check each status | No comment silently dropped; open items carried with owner and date | Y | BBM-STD-97 QP-03 §5 | PANY, FIDIC | All
DR-GN-06 | Verification | Design calculations exist for every sized element and are independently checked | List calculations against the drawing elements they size; check checker signature | Each calculation has author, checker, date, inputs and code edition | Y | BBM-STD-97 QP-03 §6 | ISO9001, PANY | 3-4
DR-GN-07 | Verification | Drawings, schedules and specification agree | Sample 10 items (finishes, doors, equipment) across drawings, schedules and spec sections | Same type, size, rating and reference everywhere | Y | BBM-STD-97 QP-05 | AIAQC, CSI | 3-4
DR-GN-08 | Change | Design changes since the last issue are listed, reasoned and approved | Compare revision clouds/tables with the change log and client instructions | Every change has a reason, approver and affected disciplines notified | Y | BBM-STD-97 QP-03 §7 | ISO9001 | All
DR-GN-09 | Risk | Design risks and hazards recorded and reduced where designable | Open the design risk register / safety information (BBM-STD-88) | Residual risks listed with owner; nothing unassessed in the package | Y | BBM-STD-88 | ISO9001, RIBA | 2-4
DR-GN-10 | Sustainability | Sustainability targets of the project are reflected in the package | Compare with the sustainability tracker (05-SUSTAINABILITY checklist) | Each targeted credit/regulation has its design evidence or an open action | Y | BBM-STD-97 QP-06 | PBRS, SAFAT | 2-4
DR-GN-11 | Output | BIM and drawing-output checks done in the BIM checklist | Open the BBM-STD-68-CHECKLIST for this container | BIM checklist issued with no mandatory Fail; ID recorded here | Y | BBM-STD-68; BBM-STD-97 QP-08 | BIMCL | All

## ARC
ARC
Architecture design review (BBM-STD-58).
Project code |  | Package / stage |  | Revision |  | RIBA stage |  | Reviewer |  | Review date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
DR-AR-01 | Planning | Plot regulations met: setbacks, height, coverage, FAR/GFA, parking | Measure against the affection plan / plot regulations; check the area statement | All values within the plot limits, area method stated | Y | BBM-STD-58; BBM-STD-85 §4 | DBC | 2-4
DR-AR-02 | Planning | Area schedule reconciles with the model and the brief | Compare area schedule totals with room/area schedules and brief areas | Differences explained; GFA and saleable/leasable areas use the stated method | Y | BBM-STD-58 | PANY | 2-4
DR-AR-03 | Function | Every brief space is provided with its area, adjacencies and clear heights | Room-by-room against the brief schedule of accommodation | All spaces present; deviations recorded as derogations | Y | BBM-STD-97 QP-03 | RIBA | 2-3
DR-AR-04 | Access | Accessibility: routes, door widths, ramps, lifts, accessible WCs and parking | Check plans against DBC Part C / the applicable accessibility code | Every accessible route continuous; counts and sizes meet the code | Y | BBM-STD-85 §4 | DBC, SAFAT | 2-4
DR-AR-05 | Means of escape | Exits, travel distances and stair widths agree with the FLS strategy | Overlay the FLS strategy drawings on the plans | No plan change after the FLS check; stairs/doors match the strategy | Y | BBM-STD-97 QP-03; FLS sheet | PANY | 2-4
DR-AR-06 | Envelope | Facade performance (U-value, shading coefficient, light transmittance, WWR) recorded per elevation | Read the facade schedule and the energy/green calculation | Values meet the green building minimum for the plot | Y | BBM-STD-97 QP-06 | SAFAT, PBRS | 3-4
DR-AR-07 | Envelope | Waterproofing, roofing and below-ground protection detailed at every interface | Check roof, podium, wet-area and basement details | Continuous membrane, falls, upstands and outlets shown | Y | BBM-STD-70 | PANY, FHWA | 4
DR-AR-08 | Details | Typical wall sections and key details complete and cross-referenced | Follow callouts from plans/sections to detail sheets | Every callout resolves; no "TBC" in issued details | Y | BBM-STD-67 | AIAQC, LEG | 4
DR-AR-09 | Openings | Door and window schedules complete: type, size, rating, hardware, finish | Compare schedule to plans and to the specification | Every opening tagged, scheduled and specified; fire ratings match FLS | Y | BBM-STD-58 | PANY | 4
DR-AR-10 | Vertical transport | Lifts and stairs sized for the traffic and code (lift analysis, stair riser/going) | Check lift traffic study and stair sections | Study exists for buildings with lifts; risers/goings within code | N | BBM-STD-97 QP-03 | DBC | 3-4
DR-AR-11 | Coordination | Ceiling heights and zones confirmed with STR and MEP | Section through the deepest services zone per floor | Clear height met under beams, ducts and sprinklers | Y | BBM-STD-97 QP-04 | AIAQC, PANY | 3-4
DR-AR-12 | Materials | Finishes and materials selected per room and specified | Room finish schedule against spec sections | Every finish code has a spec section; durability/slip ratings stated | Y | BBM-STD-71 | CSI | 4

## INT
INT
Interior design review (BBM-STD-62). Discipline code INT (legacy tab "ID").
Project code |  | Package / stage |  | Revision |  | RIBA stage |  | Reviewer |  | Review date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
DR-IN-01 | Brief | Interior concept matches the approved brief, budget class and brand standards | Compare mood/finish boards and plans with the brief | Deviations listed and approved | Y | BBM-STD-62 | RIBA | 2-3
DR-IN-02 | Layout | Furniture layouts keep escape widths, door swings and accessible clearances | Measure aisles, door clearances and turning circles on plans | Clearances meet the code and the FLS strategy | Y | BBM-STD-62 | DBC | 3-4
DR-IN-03 | Finishes | Finish schedule complete with code, material, supplier-neutral spec and fire reaction class | Schedule against plans, elevations and spec | Every finish scheduled and specified; reaction-to-fire class meets FLS | Y | BBM-STD-62; BBM-STD-71 | CSI, PANY | 4
DR-IN-04 | Joinery | Joinery drawings dimensioned with materials, fixings and services cut-outs | Check joinery elevations and sections | Buildable without RFIs; services coordinated | Y | BBM-STD-62 | FHWA | 4
DR-IN-05 | Ceilings | Reflected ceiling plans coordinated: lights, diffusers, sprinklers, detectors, access panels | Overlay RCP with MEP and FLS layouts | No clash; access panels at every serviceable item | Y | BBM-STD-97 QP-04 | PANY, AIAQC | 4
DR-IN-06 | Wet areas | Wet areas: falls, waterproofing, slip resistance, accessible fittings | Check wet-area details and finish schedule | Details and ratings shown | Y | BBM-STD-62 | PANY | 4
DR-IN-07 | FF&E | FF&E schedule complete and separated from the contractor scope | Compare FF&E list with BOQ/spec responsibility | Every item has scope owner (contractor / client / FF&E supplier) | N | BBM-STD-62 | AIACR | 4
DR-IN-08 | Sustainability | Low-emitting materials and finishes targeted where the rating needs them | Compare finish selections with the sustainability tracker | VOC limits stated in the spec where the credit is targeted | N | BBM-STD-97 QP-06 | PBRS, SAFAT | 4
DR-IN-09 | Fit-out approval | Fit-out permit route identified (landlord NOC, DM/DDA/free zone fit-out approval) | Check the jurisdiction record and landlord requirements | Route and documents listed in the submission register | Y | BBM-STD-85 §10 | DMBP | 3-4

## LSC
LSC
Landscape design review (BBM-STD-61).
Project code |  | Package / stage |  | Revision |  | RIBA stage |  | Reviewer |  | Review date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
DR-LS-01 | Site | Levels and drainage: falls, outlets and finished levels tie to the survey and architecture | Check grading plan against survey and building thresholds | Every hard area drains; thresholds protected | Y | BBM-STD-61; BBM-STD-63 | FHWA | 3-4
DR-LS-02 | Planting | Plant schedule meets the indigenous/adapted species share | Compute indigenous share of planted area | At least 25% of planted area native/adapted where Al Sa'fat 302.01 applies (or the Estidama credit target) | Y | BBM-STD-97 QP-06 | SAFAT, PBRS | 3-4
DR-LS-03 | Irrigation | Irrigation design and water source meet the green building rule | Check irrigation layout, demand calculation and water source | Efficient irrigation; non-potable source where Al Sa'fat 601.04 / Estidama PW credit applies | Y | BBM-STD-97 QP-06 | SAFAT, PBRS | 3-4
DR-LS-04 | Hardscape | Hardscape materials, SRI / shade for heat-island reduction recorded | Check hardscape schedule and shade calculation | Target met or documented as not targeted | N | BBM-STD-61 | SAFAT, PBRS | 3-4
DR-LS-05 | Structure | Landscape loads on podium/roof slabs agreed with STR (soil depth, trees, water features) | Check load plan sent to STR and the STR response | Loads accepted in writing by STR | Y | BBM-STD-97 QP-04 | PANY | 3-4
DR-LS-06 | Services | Lighting, irrigation and drainage routes coordinated with MEP and utilities | Overlay utilities and landscape services | No conflict with utility corridors or tree pits | Y | BBM-STD-97 QP-04 | FHWA | 4
DR-LS-07 | Safety | Play, water features and edges meet safety and access rules | Check edge protection, depths and surfacing | Guarding/surfacing per code; accessible routes kept | Y | BBM-STD-88 | DBC | 3-4
DR-LS-08 | Authority | Landscape/irrigation approval route identified (municipality landscape, DEWA/ADDC, master developer) | Check the submission register | Approvals listed with owner and stage | N | BBM-STD-85 | DMBP | 3-4

## STR
STR
Structural design review (BBM-STD-59).
Project code |  | Package / stage |  | Revision |  | RIBA stage |  | Reviewer |  | Review date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
DR-ST-01 | Basis | Structural design basis: codes, loads, materials, soil report and seismic/wind parameters stated | Read the structural design basis report | Every parameter sourced; soil report referenced with revision | Y | BBM-STD-59 | PANY, DBC | 2-3
DR-ST-02 | Analysis | Analysis model checked independently (load cases, combinations, supports) | Checker reviews input summary and reactions | Independent check signed; reactions balance applied loads | Y | BBM-STD-59; BBM-STD-97 QP-03 §6 | ISO9001 | 3-4
DR-ST-03 | Members | Member sizes on drawings match the latest calculation | Sample members from drawings and compare with output | All sampled members match | Y | BBM-STD-59 | PANY | 3-4
DR-ST-04 | Openings | Openings and penetrations from MEP approved and shown on structural drawings | Compare builders-work requests with STR drawings | Every approved opening shown; no unapproved openings | Y | BBM-STD-97 QP-04 | AIAQC, PANY | 4
DR-ST-05 | Durability | Exposure class, cover and concrete grades stated per element | Check general notes and schedules | Cover/grade per exposure; sustainable concrete target where rated | Y | BBM-STD-59 | SAFAT | 4
DR-ST-06 | Foundations | Foundation design matches the soil report recommendations | Compare bearing/pile design with geotechnical report | Values within report limits; settlement checked | Y | BBM-STD-59 | FHWA | 3-4
DR-ST-07 | Temporary | Construction sequence, temporary works and propping assumptions stated | Check notes and sequence drawings | Assumptions stated for the contractor | N | BBM-STD-97 QP-04 | FHWA | 4
DR-ST-08 | Authority | Structural drawings and calculations stamped by the registered consultant of record | Check stamp/registration against the Directory | Registered engineer and classification category valid for the building height | Y | BBM-STD-55 §2 | DMQ | 4

## MEP
MEP
Mechanical, plumbing and electrical design review (BBM-STD-60).
Project code |  | Package / stage |  | Revision |  | RIBA stage |  | Reviewer |  | Review date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
DR-MP-01 | Basis | MEP design basis: design conditions, loads, diversity and codes stated | Read the MEP design basis report | Conditions per DBC/authority; every assumption sourced | Y | BBM-STD-60 | DBC | 2-3
DR-MP-02 | HVAC | Heat load calculation done with authority parameters and matches equipment selections | Compare load calc output with schedules | Equipment capacity within design margin | Y | BBM-STD-60 | SAFAT, PBRS | 3-4
DR-MP-03 | HVAC | Ventilation rates meet ASHRAE 62.1 / authority minimum | Check fresh-air calculation per space | Every occupied space meets the minimum | Y | BBM-STD-60 | SAFAT | 3-4
DR-MP-04 | Energy | Equipment efficiencies, lighting power density and controls meet the green building minimum | Compare schedules with the energy compliance sheet | All values compliant (elemental or performance method recorded) | Y | BBM-STD-97 QP-06 | SAFAT, PBRS | 3-4
DR-MP-05 | Plumbing | Water fixtures flow rates, metering and drainage sized and compliant | Check fixture schedule, water balance and drainage calc | Flow rates within the rating limits; sub-meters shown | Y | BBM-STD-60 | SAFAT, PBRS | 3-4
DR-MP-06 | Electrical | Load schedule, single-line diagram, earthing and emergency supply consistent | Compare SLD with load schedule and panel schedules | Totals agree; emergency loads on the right supply | Y | BBM-STD-60 | PANY | 3-4
DR-MP-07 | Utilities | Utility authority requirements identified (DEWA/ADDC/Etisalat/du, district cooling) | Check NOC list and utility load letters | Each utility has its NOC/load approval route | Y | BBM-STD-85 | DMBP | 3-4
DR-MP-08 | Access | Plant rooms, risers and shafts sized with maintenance access | Check plant room layouts and access routes | Clearances and replacement routes shown | Y | BBM-STD-97 QP-04 | FHWA, AIAQC | 3-4
DR-MP-09 | Commissioning | Commissioning requirements and testing specified | Check spec and commissioning plan | Commissioning plan exists where Al Sa'fat 503 / Estidama IDP requires it | Y | BBM-STD-97 QP-06 | SAFAT, PBRS | 4
DR-MP-10 | Coordination | MEP coordination (clash) cycle closed for the issue | Read the BBM-STD-50 clash report | No open S1/S2 clash in the issued zone | Y | BBM-STD-50 | BIMCL | 3-4

## FLS
FLS
Fire and life safety design review (BBM-STD-85 §5).
Project code |  | Package / stage |  | Revision |  | RIBA stage |  | Reviewer |  | Review date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
DR-FL-01 | Strategy | Fire strategy report issued for the stage, with the code edition and occupancy classification | Read the fire strategy report | Report current; UAE Fire & Life Safety Code edition recorded (ED-UAE-FLS) | Y | BBM-STD-85 §5 | DBC | 2-4
DR-FL-02 | Means of escape | Occupant load, exit numbers, widths and travel distances calculated per floor | Check the means of escape calculation against the plans | All values compliant on every floor | Y | BBM-STD-85 §5 | PANY | 2-4
DR-FL-03 | Compartmentation | Compartment walls/floors, fire doors and penetration seals shown and rated | Overlay compartment plans with door schedule and services | Every opening in a fire line rated; seals specified | Y | BBM-STD-97 QP-04 | PANY | 3-4
DR-FL-04 | Systems | Detection, alarm, sprinklers, smoke control and emergency lighting designed and coordinated | Check FLS systems drawings against the strategy | Each required system designed; cause-and-effect matrix exists | Y | BBM-STD-60 | PANY | 3-4
DR-FL-05 | Facade | External wall materials meet the facade fire rules | Check facade material test reports/listing | Every facade material listed/tested per the code | Y | BBM-STD-85 §5 | DBC | 3-4
DR-FL-06 | Access | Fire service access: roads, hydrants, fire command centre, firefighting lifts | Check site plan and core layouts | Access and equipment per code | Y | BBM-STD-85 §5 | DBC | 2-4
DR-FL-07 | Approval | Civil Defence submission status known for this issue | Read the submission register | Status recorded (Planned/Submitted/Approved); comments closed | Y | BBM-STD-57 §4 | DMBP | 3-4

## Coordination
Coordination
Interdisciplinary coordination check before each issue (QP-04).
Project code |  | Package / stage |  | Revision |  | RIBA stage |  | Reviewer |  | Review date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
DR-CO-01 | Grid and levels | All disciplines use the same grids, levels and coordinates | Overlay discipline drawings/models at shared points | No offset; shared coordinates per BBM-STD-86 | Y | BBM-STD-86; BBM-STD-64 | BIMCL, AIAQC | 2-4
DR-CO-02 | Revisions | Each discipline worked on the current revision of the others | Compare referenced revisions in each package with the register | No package based on a superseded background | Y | BBM-STD-97 QP-10 | ISO19650 | All
DR-CO-03 | Interfaces | Interface matrix (ARC/STR/MEP/FLS/INT/LSC) reviewed and open items owned | Walk the interface list in the coordination meeting | Every interface item closed or owned with date | Y | BBM-STD-97 QP-04 | RIBA, FIDIC | 2-4
DR-CO-04 | Spaces | Plant rooms, shafts and risers agreed across ARC, STR, MEP | Compare shaft sizes/locations in all disciplines | Same size and location in every discipline | Y | BBM-STD-97 QP-04 | AIAQC | 2-4
DR-CO-05 | Ceilings | Ceiling zones and clear heights confirmed after clash resolution | Section check through critical zones | Clear height met; no unresolved clash | Y | BBM-STD-50 | AIAQC, PANY | 3-4
DR-CO-06 | Openings | Builders-work openings issued by MEP and approved by STR | Compare opening register across disciplines | Register closed for the zone | Y | BBM-STD-97 QP-04 | PANY | 4
DR-CO-07 | Fire lines | Fire-rated lines identical on ARC, MEP and FLS drawings | Overlay fire-line drawings | Lines and ratings identical | Y | BBM-STD-97 QP-04 | PANY | 3-4
DR-CO-08 | Schedules | Equipment and door/hardware interfaces (access control, fire alarm release) coordinated | Compare door hardware schedule with ELV/FLS | Every controlled door listed in both | N | BBM-STD-97 QP-04 | PANY | 4
DR-CO-09 | Clash | Federated clash test run per the clash matrix and report issued | Read the BBM-STD-50 report for the issue | No open S1 clash; S2 owned with date | Y | BBM-STD-50 | BIMCL | 3-4
DR-CO-10 | Specification | Spec sections of all disciplines cross-referenced without gaps or overlaps | Check related-sections articles across disciplines | Every interface specified once | Y | BBM-STD-97 QP-05 | CSI | 4

## Constructability
Constructability
Constructability review at Stage 3 end and before tender (QP-04 §5).
Project code |  | Package / stage |  | Revision |  | RIBA stage |  | Reviewer |  | Review date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
DR-CB-01 | Buildability | Design is buildable with locally available methods, materials and skills | Constructability review meeting with a construction-experienced reviewer | Comments logged; no unbuildable item left open | Y | BBM-STD-97 QP-04 §5 | FHWA, AIAQC | 3-4
DR-CB-02 | Sequence | Construction sequence and phasing feasible (site access, crane, laydown, live operations) | Review logistics plan against the drawings | Sequence possible without redesign | N | BBM-STD-97 QP-04 §5 | FHWA | 4
DR-CB-03 | Tolerances | Tolerances and movement joints stated at interfaces (facade, slabs, finishes) | Check general notes and interface details | Tolerances stated for every interface package | Y | BBM-STD-70 | FHWA | 4
DR-CB-04 | Procurement | Long-lead items and specialist packages identified | Check spec and design responsibility matrix | List issued to the client with lead-time risk | N | BBM-STD-97 QP-04 §5 | FHWA, RIBA | 4
DR-CB-05 | Design responsibility | Contractor-designed portions defined with performance requirements | Check the design responsibility matrix and performance specs | Each CDP has a performance spec and review route | Y | BBM-STD-97 QP-05 | RIBA, CSI | 4
DR-CB-06 | Maintenance | Maintenance access and replacement routes designed (facade, plant, high ceilings) | Review access strategy | Every maintainable item reachable safely | Y | BBM-STD-88 | FHWA | 3-4
DR-CB-07 | Tender | Documents are biddable: quantities measurable, no conflicting requirements | Sample BOQ items against drawings/spec | Sampled items measurable and consistent | Y | BBM-STD-97 QP-04 §5 | FHWA | 4

## Sign-off
Sign-off
Results of every sheet, the status rule and the signatures for this check.
Sheet | Checks | Pass | Fail | NA | Not checked | Mandatory Fail
General
ARC
INT
LSC
STR
MEP
FLS
Coordination
Constructability
Total
Rule | Mark sheets that do not apply NA with a reason in Comment. Any mandatory Fail is a nonconformity (BBM-STD-97 QP-11): it holds the issue, submission or decision until corrected and re-checked. No count or score overrides it.
Status
Role | Name | Date | Decision / note
Prepared by
Checked by (independent of the work)
QA/QC lead
Approved by (discipline lead / project director)