## Read me
BBM-STD-97 Sustainability rating checklist V1.0
Estidama Pearl (per credit section), Al Sa'fat (per regulation section) and LEED tracking through design and construction (BBM-STD-97 QP-06). Mark the schemes that do not apply NA.
How to use
1. Save a copy into the project QA folder (03.REPORTS) named to the project naming register. Never work in the office copy.
2. Fill the header row on each sheet. Work every sheet that applies; Result is Pass, Fail or NA. NA needs a reason in Comment.
3. Mandatory = Y (crimson) must Pass or carry an approved scoped exception; a mandatory Fail is an NC under BBM-STD-97 QP-11.
4. Sign-off totals every sheet and holds the signatures. File the signed copy with the issue, submission or decision it supports.
5. Model, container, drawing-output and authority-BIM checks are in 07-QA-QC/01-BIM/BBM-STD-68-CHECKLIST-V1.0.xlsx; they are linked here, not repeated.
6. Rules behind these checks: BBM-STD-96 QMS manual, BBM-STD-97 quality procedures, BBM-STD-98 quality KPIs (04-DOCUMENTS).
Sheets
Sheet | ID prefix | Checks | Mandatory | What it covers
Estidama design | SU-ES | 11 | 10 | Abu Dhabi Pearl Building Rating System, design rating (IDP, NS, LB, PW, RE, SM, IP).
Estidama construction | SU-EC | 3 | 3 | Pearl construction rating evidence and submission.
Al Sa'fat | SU-SA | 10 | 10 | Dubai green building system, 2nd edition: sections 300 to 700 and the certificate.
LEED | SU-LD | 4 | 3 | LEED where the client targets it (version per registration).
Source standards (primary sources, read 2026-11-04; edition register BBM-STD-51 §3)
Code | Source | Where
AR154 | DM Administrative Resolution 154 of 2020, Al Sa'fat bylaw: Silver mandatory, Gold/Platinum optional; Silver valid 15 years (indefinite for private villas and industrial), Gold/Platinum 5 years | https://dlp.dubai.gov.ae/Legislation%20Reference/2020/Administrative%20Resolution%20No.%20(154)%20of%202020%20Concerning%20the%20Bylaw%20on%20the%20Dubai%20Green.html
DBC | Dubai Building Code 2021 edition (consultant demonstrates performance-based alternatives; check the latest version) | https://dmpmedia.dm.gov.ae/uploads/2021/12/Dubai%20Building%20Code_English_2021%20Edition_compressed.pdf
IB19 | Estidama Information Bulletin #19 (May 2025): villas over 2,000 m2 conditioned area assessed under PBRS | https://www.dmt.gov.ae/-/media/Project/DMT/DMT/E-Library/06-25/Estidama-Pearl-Rating-System_-Information-Bulletin-No-19.pdf
LEED | USGBC LEED rating system: version and credit library as registered for the project (record the version in BBM-STD-51 §3 before use) | https://www.usgbc.org/leed
PBRS | Estidama Pearl Building Rating System, Design & Construction V1.0 (Apr 2010): IDP 13, NS 12, LB 37, PW 43, RE 44, SM 28, IP 3 bonus; 1 Pearl = all mandatory, 2 Pearl = +60 points | https://www.dmt.gov.ae/-/media/Project/DMT/DMT/E-Library/0001-Manuals/PBRS/PBRS-Version-10.pdf
PBRSC | Estidama Construction Rating Site Audit Protocol V1.0 (Mar 2012): Design/Construction/Operational ratings, PQP role, submission 3-4 weeks after completion certificate | https://pages.dmt.gov.ae/en/Urban-Planning/-/media/13F91E3DD2F94577B9298A260C0D9325.ashx
SAFAT | Al Sa'fat Dubai Green Building System, 2nd edition (Jan 2023): sections 300 Ecology & Planning, 400 Building Vitality, 500 Energy, 600 Water, 700 Materials & Waste | https://dmpmedia.dm.gov.ae/uploads/2023/01/Al-Safat-%E2%80%93-Dubai-Green-Building-System-2nd-editionJan2023.pdf

## Estidama design
Estidama design
Abu Dhabi Pearl Building Rating System, design rating (IDP, NS, LB, PW, RE, SM, IP).
Project code |  | Rating scheme |  | Target level |  | RIBA stage |  | PQP / assessor |  | Check date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
SU-ES-01 | Applicability | Pearl rating system and minimum level confirmed (PBRS / PVRS / PCRS; 1 Pearl private, 2 Pearl government-funded) | Check plot, use, GFA (villas >2,000 m2 conditioned use PBRS, IB#19) and funding | System and minimum Pearl recorded in the BEP and BoD (ED-ESTIDAMA) | Y | BBM-STD-85 §7 | PBRS, IB19 | 1-2
SU-ES-02 | Team | Pearl Qualified Professional (PQP) appointed for design and construction stages | Check PQP number and appointment | PQP named; change between stages recorded | Y | BBM-STD-97 QP-06 §3 | PBRSC, PBRS | 1-2
SU-ES-03 | IDP | IDP: integrated development process, workshop and team charter held; commissioning and guide requirements planned | Check IDP workshop minutes and commissioning plan | All IDP mandatory credits evidenced | Y | BBM-STD-97 QP-06 §4 | PBRS | 1-4
SU-ES-04 | NS | NS: natural systems assessment, ecological protection and habitat credits | Check site ecological assessment | NS mandatory credits evidenced; optional targets tracked | Y | BBM-STD-97 QP-06 §4 | PBRS | 2-4
SU-ES-05 | LB | LB: livable buildings outdoor (shading, thermal comfort) and indoor (ventilation, daylight, materials emissions) credits | Check shading study, ventilation calc, low-emitting materials spec | LB mandatory credits evidenced | Y | BBM-STD-97 QP-06 §4 | PBRS | 2-4
SU-ES-06 | PW | PW: water calculator, fixture flow rates, exterior water use and metering | Run the Estidama water calculator; check fixture schedule | Minimum interior/exterior water reduction met; meters shown | Y | BBM-STD-97 QP-06 §4 | PBRS | 2-4
SU-ES-07 | RE | RE: energy performance (calculator or simulation), commissioning, refrigerant ODP zero, metering | Check energy model/calculator output and schedules | Minimum energy performance met; refrigerants zero ODP | Y | BBM-STD-97 QP-06 §4 | PBRS | 2-4
SU-ES-08 | SM | SM: waste management plan, materials (recycled, regional, certified timber), design for flexibility | Check waste plan and materials tracker | SM mandatory credits evidenced; material percentages tracked | Y | BBM-STD-97 QP-06 §4 | PBRS | 2-5
SU-ES-09 | IP | IP: innovation and regional/cultural practice credits claimed with evidence | Check innovation submissions | Each claimed IP credit has evidence; bonus points not counted toward minimum | N | BBM-STD-97 QP-06 §4 | PBRS | 2-4
SU-ES-10 | Design rating | Design rating submission compiled by the PQP at construction documentation, with credit evidence file structure | Check the submission index against the Estidama template | Every targeted credit has its evidence; submission before permit | Y | BBM-STD-97 QP-06 §5 | PBRSC | 4
SU-ES-11 | Design rating | Pearl Assessor comments answered and Design Rating awarded before construction | Read assessor comments log | All comments closed; Design Rating certificate filed | Y | BBM-STD-97 QP-06 §5 | PBRSC | 4

## Estidama construction
Estidama construction
Pearl construction rating evidence and submission.
Project code |  | Rating scheme |  | Target level |  | RIBA stage |  | PQP / assessor |  | Check date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
SU-EC-01 | Construction rating | Construction-stage credits tracked by the contractor and checked by the supervision team | Monthly review of construction credit evidence | Evidence current each month | Y | BBM-STD-97 QP-06 §6 | PBRSC | 5
SU-EC-02 | Construction rating | Procurement checked against rated requirements (materials, fixtures, equipment) | Compare approved submittals with the credit requirements | No approved product breaks a targeted credit | Y | BBM-STD-97 QP-09 | PBRSC | 5
SU-EC-03 | Construction rating | Construction Rating submission issued within 3-4 weeks of the completion certificate | Check submission date against completion certificate date | Submission within the window | Y | BBM-STD-97 QP-06 §6 | PBRSC | 6

## Al Sa'fat
Al Sa'fat
Dubai green building system, 2nd edition: sections 300 to 700 and the certificate.
Project code |  | Rating scheme |  | Target level |  | RIBA stage |  | PQP / assessor |  | Check date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
SU-SA-01 | Applicability | Al Sa'fat edition, building typology and target Sa'fa level recorded (Silver mandatory; Gold/Platinum optional) | Check typology (villa / Project-commercial / public / industrial) and the client target | Edition (2nd ed. Jan 2023, ED-ALSAFAT) and level recorded in BEP and BoD | Y | BBM-STD-85 §7 | SAFAT, AR154 | 1-2
SU-SA-02 | 300 Ecology & Planning | 301 access and mobility (enabled access, parking for low-emitting/EV), 302 local species (25% of planted area) | Check access drawings, parking schedule, planting schedule | Silver requirements met; level-specific percentages met | Y | BBM-STD-97 QP-06 §4 | SAFAT | 2-4
SU-SA-03 | 300 Ecology & Planning | 303 exterior light pollution, 304 microclimate (heat rejection height, heat island, glazing orientation), 305 EIA | Check lighting design, roof plant layout, hardscape/roof SRI, EIA report | Each regulation evidenced or marked not applicable with reason | Y | BBM-STD-97 QP-06 §4 | SAFAT, DBC | 2-4
SU-SA-04 | 400 Building Vitality | 401 ventilation and indoor air quality (ASHRAE 62.1/62.2/170, IAQ during construction, sealing), thermal and acoustic comfort, hazardous materials | Check ventilation calc, IAQ plan, specs | All 400-series Silver requirements evidenced | Y | BBM-STD-97 QP-06 §4 | SAFAT | 3-5
SU-SA-05 | 400 Building Vitality | 407 responsible construction: construction/demolition impact, certified consultant/contractor (Gold/Platinum), sustainable concrete (7% / 15% below baseline) | Check CEMP requirement and concrete mix submittals | Requirements met for the target level | Y | BBM-STD-97 QP-06 §4 | SAFAT | 4-5
SU-SA-06 | 500 Energy | 501 envelope (roof U 0.3; wall U 0.57 Silver / 0.42 Gold+; glazing per WWR band), 502 HVAC and lighting efficiency | Compare facade schedule and MEP schedules with tables 501.01 | Values within the table for the target level | Y | BBM-STD-97 QP-06 §4 | SAFAT | 3-4
SU-SA-07 | 500 Energy | 503 commissioning (cooling load 1 MW or more), 504 on-site renewables, 505 energy demand reduction (Gold/Platinum) | Check commissioning plan, PV design and demand study | Requirements met for the target level | Y | BBM-STD-97 QP-06 §4 | SAFAT | 3-5
SU-SA-08 | 600 Water | 601 fixtures and irrigation efficiency, condensate recovery; 603 wastewater reuse (15% Gold / 30% Platinum), cooling tower water | Check water calculation and drainage/irrigation design | Elemental or performance method recorded and met | Y | BBM-STD-97 QP-06 §4 | SAFAT | 3-4
SU-SA-09 | 700 Materials & Waste | 701 materials (certified timber, asbestos-free, refrigerants, recycled content 15% Gold+, regional material 10/20/30%), 702 waste management | Check materials tracker and waste plan | Percentages tracked by cost; waste storage designed | Y | BBM-STD-97 QP-06 §4 | SAFAT | 4-5
SU-SA-10 | Certificate | Sa'fa certificate issued and validity recorded (Silver 15 years, or indefinite for private villa/industrial; Gold/Platinum 5 years) | Check certificate and expiry | Certificate filed; renewal trigger in the handover record | Y | BBM-STD-75 | AR154 | 6

## LEED
LEED
LEED where the client targets it (version per registration).
Project code |  | Rating scheme |  | Target level |  | RIBA stage |  | PQP / assessor |  | Check date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
SU-LD-01 | Registration | LEED version, rating system (BD+C, ID+C, O+M) and target level registered; version added to the edition register | Check registration and BBM-STD-51 §3 | Version recorded before credit work | Y | BBM-STD-51 §3 | LEED | 1-2
SU-LD-02 | Prerequisites | All prerequisites of the registered version identified with owner and evidence plan | Credit scorecard review | Every prerequisite owned | Y | BBM-STD-97 QP-06 §4 | LEED | 2-4
SU-LD-03 | Scorecard | Scorecard (yes/maybe/no) reviewed each stage against design evidence | Stage review of the scorecard | Points with evidence at least the target plus margin | Y | BBM-STD-97 QP-06 §4 | LEED | 2-5
SU-LD-04 | Submission | Design and construction reviews submitted with complete evidence | Check submission tracker | Reviewer comments closed | N | BBM-STD-97 QP-06 §5 | LEED | 4-6

## Sign-off
Sign-off
Results of every sheet, the status rule and the signatures for this check.
Sheet | Checks | Pass | Fail | NA | Not checked | Mandatory Fail
Estidama design
Estidama construction
Al Sa'fat
LEED
Total
Rule | Mark sheets that do not apply NA with a reason in Comment. Any mandatory Fail is a nonconformity (BBM-STD-97 QP-11): it holds the issue, submission or decision until corrected and re-checked. No count or score overrides it.
Status
Role | Name | Date | Decision / note
Prepared by
Checked by (independent of the work)
QA/QC lead
Approved by (discipline lead / project director)