## Read me
BBM-STD-97 Site supervision and inspection checklist V1.0
Consultant supervision: mobilisation, submittals, inspections and hold points, NCRs/RFIs/instructions and completion (BBM-STD-97 QP-09).
How to use
1. Save a copy into the project QA folder (03.REPORTS) named to the project naming register. Never work in the office copy.
2. Fill the header row on each sheet. Work every sheet that applies; Result is Pass, Fail or NA. NA needs a reason in Comment.
3. Mandatory = Y (crimson) must Pass or carry an approved scoped exception; a mandatory Fail is an NC under BBM-STD-97 QP-11.
4. Sign-off totals every sheet and holds the signatures. File the signed copy with the issue, submission or decision it supports.
5. Model, container, drawing-output and authority-BIM checks are in 07-QA-QC/01-BIM/BBM-STD-68-CHECKLIST-V1.0.xlsx; they are linked here, not repeated.
6. Rules behind these checks: BBM-STD-96 QMS manual, BBM-STD-97 quality procedures, BBM-STD-98 quality KPIs (04-DOCUMENTS).
Sheets
Sheet | ID prefix | Checks | Mandatory | What it covers
Mobilisation | SV-MB | 6 | 6 | Before site start.
Submittals | SV-SM | 6 | 4 | Shop drawings, materials, samples, substitutions.
Inspections | SV-IP | 10 | 10 | Hold and witness points per ITP; phase reports.
NCR and RFI | SV-NR | 5 | 5 | Non-conforming work, RFIs, instructions and design feedback.
Completion | SV-CP | 7 | 7 | Snagging, commissioning, authority completion, certificate and handover.
Source standards (primary sources, read 2026-11-04; edition register BBM-STD-51 §3)
Code | Source | Where
ADC9 | Abu Dhabi UPPC Circular No. 9 of 2026 (14 Oct 2026): supervision consultant and contractor roles, notice before each major phase, joint certified technical report per phase via the Unified Permitting System, joint liability | https://www.Project.ae/en/article/c2qm3pn-uppc-issues-circular-streamline-construction
AIACR | AIA Best Practices: Reviewing a contract, what architects need to know | https://www.aia.org/sites/default/files/2025-12/AIA_BestPractices_Reviewingacontract-Whatarchitectsneed.pdf
AR154 | DM Administrative Resolution 154 of 2020, Al Sa'fat bylaw: Silver mandatory, Gold/Platinum optional; Silver valid 15 years (indefinite for private villas and industrial), Gold/Platinum 5 years | https://dlp.dubai.gov.ae/Legislation%20Reference/2020/Administrative%20Resolution%20No.%20(154)%20of%202020%20Concerning%20the%20Bylaw%20on%20the%20Dubai%20Green.html
ART821 | UAE Civil Transactions Law, Federal Decree-Law 25 of 2025 Art. 821 (Art. 880 of the 1985 law for contracts before 1 June 2026): ten-year joint liability of the supervising engineer and contractor (cannot be excluded, Art. 823); professional indemnity needed for classification | https://uaelegislation.gov.ae/en/legislations/4011?keyword=Article%20(821)
CSI | CSI/CSC SectionFormat/PageFormat (three-part section, page arrangement); MasterFormat 2020 Edition (50 divisions) | https://www.csiresources.org/standards/sectionformat-pageformat
DMAR275 | DM Administrative Resolution 275 of 2024: replacing engineering firms and contractors and issuing completion certificates (Art. 16 repeals Resolution 10 of 2019); engineering firms registered and classified under Dubai Law No. 14 of 2025 | https://dlp.dubai.gov.ae/Legislation%20Reference/2024/Administrative%20Resolution%20No.%20(275)%20of%202024%20Replacing%20Engineering%20Firms%20and%20Contracting%20Companies.html
DMBP | Dubai Municipality building permit procedures and the single-window platform (request permit, unified inspection, execution and service delivery) | https://www.dm.gov.ae/municipality-business/building-permit-steps
FHWA | FHWA Constructability Review Checklist (reviews at 50/70/95% and final; buildable, biddable, maintainable) | https://highways.dot.gov/media/49146
FIDIC | FIDIC Quality Management briefing note (2019) and Organisational and Project Quality report (firm system to project delivery, learning from failure) | https://fidic.org/policy/quality
ISO10005 | ISO 10005:2018 Guidelines for quality plans; ISO 10006:2017 Quality management in projects (confirmed 2023) | https://www.iso.org/standard/70376.html
ISO19650 | ISO 19650-2:2018 cl. 5.1-5.8 (appointment, information delivery, 5.6.3 check, 5.6.4 review, 5.7 acceptance) | https://www.iso.org/standard/68080.html
ISO9001 | ISO 9001:2026 Quality management systems, Requirements (Edition 6, published 16 Sep 2026; clauses 4-10 kept, 5.1.1 i) quality culture and ethical behaviour, 6.1.1-6.1.3 risks and opportunities split, 6.3 e)-g), 7.3 e), 9.3.2 c)) | https://www.iso.org/standard/9001
OFF | Office forms in use (reused, not re-invented): BABOOM control forms for the engineering site supervision (Oct 2021), Project Transmittal, RFI form, Site Observation Report, VO template, snagging list; UPDATED SPECIFICATIONS MASTERLIST | \\BABOOM\specification\03 Specs. Files\Project Submittals\Template ; \\BABOOM\specification\01 Library\Specification Checklist (to move into 01-TEMPLATES\04.DOCUMENT-CONTROL after owner OK, survey 2026-11-04)
PBRSC | Estidama Construction Rating Site Audit Protocol V1.0 (Mar 2012): Design/Construction/Operational ratings, PQP role, submission 3-4 weeks after completion certificate | https://pages.dmt.gov.ae/en/Urban-Planning/-/media/13F91E3DD2F94577B9298A260C0D9325.ashx
RIBA | RIBA Plan of Work 2020 Overview: stages 0-7, Project Strategies, Quality Aspirations, Stage 5 "Inspect Construction Quality" | https://www.riba.org/work/insights-and-resources/riba-plan-of-work
SAFAT | Al Sa'fat Dubai Green Building System, 2nd edition (Jan 2023): sections 300 Ecology & Planning, 400 Building Vitality, 500 Energy, 600 Water, 700 Materials & Waste | https://dmpmedia.dm.gov.ae/uploads/2023/01/Al-Safat-%E2%80%93-Dubai-Green-Building-System-2nd-editionJan2023.pdf

## Mobilisation
Mobilisation
Before site start.
Project code |  | Work package / zone |  | Inspection ref |  | RIBA stage |  | Inspector |  | Inspection date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
SV-MB-01 | Appointment | Supervision scope, authority of the consultant and site staff defined and communicated to the contractor | Read appointment and construction contract consultant clauses; site handed over on the office Site Hand Over To Contractor form | Scope, visit frequency and certifying powers stated | Y | BBM-STD-97 QP-09 §3 | AIACR, ADC9, OFF | 5
SV-MB-02 | Plan | Supervision plan issued: inspection points, hold/witness points, visit schedule, staff | Check supervision plan | Plan issued before site start; hold points tied to the ITPs | Y | BBM-STD-97 QP-09 §3 | ISO10005, RIBA | 5
SV-MB-03 | Contractor QA | Contractor's quality plan, ITPs and method statements reviewed | Review contractor QP and ITP list; programme on the office Time Schedule Approval form; monthly report on the office Contractor Monthly Report format | QP accepted; ITP for every major work package | Y | BBM-STD-97 QP-09 §4 | ISO10005, OFF | 5
SV-MB-04 | Permits | Building permit, approved drawings and NOCs on site before work | Site check of permit board and approved set | Approved set is the one being built | Y | BBM-STD-97 QP-09 §3 | DMBP, ADC9 | 5
SV-MB-05 | Safety | Site safety arrangements checked against the authority safety guide (consultant duties) | Check site safety plan and safety officer appointment | Plan in place; consultant duties recorded | Y | BBM-STD-88 | DMBP | 5
SV-MB-06 | Information | Construction issue drawings controlled on site (latest revision only) | Compare site set with the register | No superseded drawing in use | Y | BBM-STD-97 QP-10 | ISO19650 | 5

## Submittals
Submittals
Shop drawings, materials, samples, substitutions.
Project code |  | Work package / zone |  | Inspection ref |  | RIBA stage |  | Inspector |  | Inspection date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
SV-SM-01 | Register | Submittal register (shop drawings, materials, samples, mock-ups) set up from the spec | Compare register with spec submittal articles; submittals on the office Material / Shop Drawing / SubContractor Submittal forms (04 01, 04 03, 04 05) | Every required submittal listed with due date | Y | BBM-STD-97 QP-09 §5 | CSI, OFF | 5
SV-SM-02 | Review | Each submittal reviewed by the responsible discipline against drawings, spec and approvals | Check review stamp and comments | Status code (A/B/C) and reviewer recorded | Y | BBM-STD-97 QP-09 §5 | ISO9001 | 5
SV-SM-03 | Review | Review period met as agreed in the contract | Compare received/returned dates | Within the agreed period or delay reason recorded | N | BBM-STD-98 K-SV-02 | AIACR | 5
SV-SM-04 | Sustainability | Rated items checked against the sustainability tracker before approval | Compare submittal with credit requirement | No approval breaks a targeted credit | Y | BBM-STD-97 QP-06 | PBRSC, SAFAT | 5
SV-SM-05 | Substitution | Substitutions evaluated for equal performance and approved by the client where required | Check substitution request form | Performance comparison and approval recorded | Y | BBM-STD-97 QP-09 §5 | CSI | 5
SV-SM-06 | Mock-up | Mock-ups and samples approved and kept as the quality benchmark | Check mock-up approval record and photos | Approved benchmark recorded | N | BBM-STD-97 QP-09 §5 | CSI | 5

## Inspections
Inspections
Hold and witness points per ITP; phase reports.
Project code |  | Work package / zone |  | Inspection ref |  | RIBA stage |  | Inspector |  | Inspection date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
SV-IP-01 | Inspection | Setting out checked against the approved site plan and survey | Survey check of grid and levels | Within tolerance; record signed | Y | BBM-STD-97 QP-09 §6 | ADC9, DMBP | 5
SV-IP-02 | Inspection | Excavation, foundations and substructure inspected before concealment | Hold-point inspection per ITP on the office Inspection Request / Material Inspection Request forms | Inspection request approved before pour/backfill | Y | BBM-STD-97 QP-09 §6 | ADC9, DMBP, OFF | 5
SV-IP-03 | Inspection | Reinforcement and concrete (cover, grade, tests, curing) inspected per pour | Pre-pour checklist; cube test results | Pour approved; test results within specification | Y | BBM-STD-97 QP-09 §6 | ADC9 | 5
SV-IP-04 | Inspection | Waterproofing inspected and flood-tested before cover | Witness flood test | Test passed and recorded | Y | BBM-STD-97 QP-09 §6 | FHWA | 5
SV-IP-05 | Inspection | MEP rough-in, pressure tests and penetrations (fire stopping) inspected before ceilings/closing | Witness tests; check fire-stopping | Tests passed; seals installed per approved system | Y | BBM-STD-97 QP-09 §6 | ADC9 | 5
SV-IP-06 | Inspection | Facade and envelope installation inspected against approved shop drawings and mock-up | Inspection per ITP | Fixings, tolerances and seals per approval | Y | BBM-STD-97 QP-09 §6 | ADC9 | 5
SV-IP-07 | Inspection | Finishes inspected against approved samples and mock-ups | Room-by-room inspection | Defects recorded on snag list | Y | BBM-STD-97 QP-09 §6 | RIBA | 5
SV-IP-08 | Inspection | FLS systems installation and testing witnessed | Witness detection, alarm, sprinkler and smoke control tests | Tests passed before Civil Defence inspection | Y | BBM-STD-97 QP-09 §6 | DMBP | 5-6
SV-IP-09 | Phase report | Phase technical report signed by consultant and contractor and submitted (Abu Dhabi Circular 9/2026; authority stage inspections elsewhere) | Check report per completed phase | Report dated, signed by both and submitted | Y | BBM-STD-97 QP-09 §6 | ADC9 | 5
SV-IP-10 | Record | Site visit report issued after every visit with observations, instructions and photos | Check visit report register (office Field Observation / Site Observation Report SOR forms) | One report per visit, issued within the agreed time | Y | BBM-STD-98 K-SV-01 | RIBA, OFF | 5

## NCR and RFI
NCR and RFI
Non-conforming work, RFIs, instructions and design feedback.
Project code |  | Work package / zone |  | Inspection ref |  | RIBA stage |  | Inspector |  | Inspection date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
SV-NR-01 | NCR | Non-conforming work recorded on an NCR with location, requirement and evidence | Check NCR register (office NCR form NCR-00) | Each NCR has requirement reference and photo | Y | BBM-STD-97 QP-09 §6; QP-11 | ISO9001, ADC9, OFF | 5
SV-NR-02 | NCR | Contractor corrective action proposed, approved and re-inspected before closure | Check NCR close-out | Closure only after re-inspection pass | Y | BBM-STD-97 QP-11 | ISO9001 | 5
SV-NR-03 | RFI | RFIs answered by the responsible discipline within the agreed time, with drawing revisions where needed | Check RFI register (office Request For Information form) | Answer references revised drawing/sketch; time recorded | Y | BBM-STD-98 K-SV-03 | ISO9001, OFF | 5
SV-NR-04 | Variations | Site instructions and variations issued in writing within the consultant authority | Check instruction register; variations on the office VO Template | No verbal instruction; client approval where required | Y | BBM-STD-97 QP-09 §5 | AIACR, OFF | 5
SV-NR-05 | Design feedback | Design errors found on site raised as office NCs and lessons learned | Check office NC log | Design-origin NCRs have an office NC with cause | Y | BBM-STD-97 QP-11 | FIDIC | 5

## Completion
Completion
Snagging, commissioning, authority completion, certificate and handover.
Project code |  | Work package / zone |  | Inspection ref |  | RIBA stage |  | Inspector |  | Inspection date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
SV-CP-01 | Snagging | Snag list issued and closed before practical completion | Walk-through and snag register (office snagging list); Initial / Final Handing Over and Taking Over Certificate forms | Open snags only those agreed in the handover certificate | Y | BBM-STD-97 QP-09 §7 | RIBA, OFF | 5-6
SV-CP-02 | Testing | Testing and commissioning results reviewed and accepted | Check commissioning reports | All systems commissioned; seasonal commissioning planned if needed | Y | BBM-STD-97 QP-09 §7 | RIBA, SAFAT | 6
SV-CP-03 | Authority | Authority completion inspections passed (DM/DMT, Civil Defence, utilities) | Check certificates | Certificates filed | Y | BBM-STD-97 QP-07 | DMAR275, DMBP | 6
SV-CP-04 | Certificate | Consultant approval of the completion certificate given only when works conform to the permit and approved plans | Check the approval record and outstanding NCRs | No open NCR affecting conformity | Y | BBM-STD-97 QP-09 §7 | DMAR275, ART821 | 6
SV-CP-05 | As-built | As-built drawings, O&M manuals and warranties received and reviewed | Check handover register | Complete set received and reviewed | Y | BBM-STD-75 | RIBA | 6
SV-CP-06 | Rating | Green rating construction submission issued (Estidama construction rating / Sa'fa certificate) | Check sustainability checklist | Submission or certificate filed | Y | BBM-STD-97 QP-06 | PBRSC, AR154 | 6
SV-CP-07 | Feedback | Client feedback requested and project lessons workshop held | Check feedback form and lessons log | Feedback received or chased twice; lessons logged | Y | BBM-STD-97 QP-11; QP-12 | RIBA, FIDIC | 6

## Sign-off
Sign-off
Results of every sheet, the status rule and the signatures for this check.
Sheet | Checks | Pass | Fail | NA | Not checked | Mandatory Fail
Mobilisation
Submittals
Inspections
NCR and RFI
Completion
Total
Rule | Mark sheets that do not apply NA with a reason in Comment. Any mandatory Fail is a nonconformity (BBM-STD-97 QP-11): it holds the issue, submission or decision until corrected and re-checked. No count or score overrides it.
Status
Role | Name | Date | Decision / note
Prepared by
Checked by (independent of the work)
QA/QC lead
Approved by (discipline lead / project director)