## Read me
BBM-STD-96 QMS audit, review and improvement checklist V1.0
Internal audit against ISO 9001:2026 clauses 4-10, management review inputs and outputs, client feedback, nonconformity/corrective action/lessons learned, project quality plan audit, and the KPI register (BBM-STD-96, BBM-STD-97 QP-02, QP-11 to QP-14, BBM-STD-98).
How to use
1. Save a copy into the project QA folder (03.REPORTS) named to the project naming register. Never work in the office copy.
2. Fill the header row on each sheet. Work every sheet that applies; Result is Pass, Fail or NA. NA needs a reason in Comment.
3. Mandatory = Y (crimson) must Pass or carry an approved scoped exception; a mandatory Fail is an NC under BBM-STD-97 QP-11.
4. Sign-off totals every sheet and holds the signatures. File the signed copy with the issue, submission or decision it supports.
5. Model, container, drawing-output and authority-BIM checks are in 07-QA-QC/01-BIM/BBM-STD-68-CHECKLIST-V1.0.xlsx; they are linked here, not repeated.
6. Rules behind these checks: BBM-STD-96 QMS manual, BBM-STD-97 quality procedures, BBM-STD-98 quality KPIs (04-DOCUMENTS).
Sheets
Sheet | ID prefix | Checks | Mandatory | What it covers
Internal audit | QA-IA | 24 | 22 | ISO 9001:2026 clause audit of the office QMS (QP-13). Auditor independent of the area audited.
Management review | QA-MR | 11 | 11 | ISO 9001:2026 9.3 inputs and outputs (QP-14).
Client feedback | QA-CF | 4 | 4 | Feedback and complaints (QP-12).
NC and lessons | QA-NC | 7 | 6 | Nonconformity, corrective action and lessons learned (QP-11).
Project quality plan | QA-QP | 4 | 4 | Audit of one project quality plan (QP-02).
KPI register | K- | 26 | - | The BBM-STD-98 KPIs with formula, target and owner.
Source standards (primary sources, read 2026-11-04; edition register BBM-STD-51 §3)
Code | Source | Where
BIMCL | Office BIM QA/QC checklist BBM-STD-68-CHECKLIST V1.0 (07-QA-QC/01-BIM): models, containers, drawings, IDS, authority BIM. Linked, not repeated | 07-QA-QC/01-BIM/BBM-STD-68-CHECKLIST-V1.0.xlsx
FIDIC | FIDIC Quality Management briefing note (2019) and Organisational and Project Quality report (firm system to project delivery, learning from failure) | https://fidic.org/policy/quality
GACI | Global ACI TECH-3-TR, Transition requirements for ISO 9001:2026 (three years, 2015 certificates invalid after 30 Sep 2029) | https://sys.global-aci.org/uploads/documents/TECH-3-TR_2029-09-30_(M)_ISO_9001_2026_Transition_v1_12.pdf
ISO10002 | ISO 10002:2018 Customer satisfaction, complaints handling; ISO 10004:2018 monitoring and measuring | https://www.iso.org/standard/71580.html
ISO10005 | ISO 10005:2018 Guidelines for quality plans; ISO 10006:2017 Quality management in projects (confirmed 2023) | https://www.iso.org/standard/70376.html
ISO19011 | ISO 19011:2018 Guidelines for auditing management systems (edition per BBM-STD-51 §3) | https://www.iso.org/standard/70017.html
ISO19650 | ISO 19650-2:2018 cl. 5.1-5.8 (appointment, information delivery, 5.6.3 check, 5.6.4 review, 5.7 acceptance) | https://www.iso.org/standard/68080.html
ISO9001 | ISO 9001:2026 Quality management systems, Requirements (Edition 6, published 16 Sep 2026; clauses 4-10 kept, 5.1.1 i) quality culture and ethical behaviour, 6.1.1-6.1.3 risks and opportunities split, 6.3 e)-g), 7.3 e), 9.3.2 c)) | https://www.iso.org/standard/9001
RIBA | RIBA Plan of Work 2020 Overview: stages 0-7, Project Strategies, Quality Aspirations, Stage 5 "Inspect Construction Quality" | https://www.riba.org/work/insights-and-resources/riba-plan-of-work
RIBAQM | RIBA Plan of Work stage checklists (Stage 1: establish project quality management procedures; RIBA Quality Management Toolkit for Chartered Practices) | https://www.riba.org/media/w3epmqnb/1-preparation-and-brief-checklist-pdf.pdf

## Internal audit
Internal audit
ISO 9001:2026 clause audit of the office QMS (QP-13). Auditor independent of the area audited.
Audit / review ID |  | Scope (office / project code) |  | Period |  | Auditor |  | Auditee |  | Date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
QA-IA-01 | 4 Context | 4.1/4.2 Internal and external issues (incl. climate change) and interested parties reviewed in the last year | Read the context and interested-parties register | Register reviewed within 12 months; climate change considered | Y | BBM-STD-96 §4 | ISO9001 | All
QA-IA-02 | 4 Context | 4.3/4.4 QMS scope and process map current | Compare BBM-STD-96 §3 with actual services | Scope matches services; every process has an owner and procedure | Y | BBM-STD-96 §3 | ISO9001 | All
QA-IA-03 | 5 Leadership | 5.1 Leadership: directors promote quality culture and ethical behaviour (5.1.1 i)) with evidence | Interview a director; look for communications, decisions, resources | At least one documented example in the period | Y | BBM-STD-96 §5 | ISO9001, GACI | All
QA-IA-04 | 5 Leadership | 5.2 Quality policy approved, communicated and understood | Ask 3 staff to explain the policy | Policy displayed; staff can explain its intent | Y | BBM-STD-96 §2 | ISO9001 | All
QA-IA-05 | 5 Leadership | 5.3 Roles, responsibilities and authorities assigned (RACI current) | Compare RACI with the organisation chart | Every QMS process has an accountable role | Y | BBM-STD-96 §5; BBM-STD-55 | ISO9001 | All
QA-IA-06 | 6 Planning | 6.1.1-6.1.3 Risks and opportunities determined, with separate actions for each | Read the office risk and opportunity register | Both registers current; actions owned | Y | BBM-STD-96 §6 | ISO9001, GACI | All
QA-IA-07 | 6 Planning | 6.2 Quality objectives measurable and monitored (BBM-STD-98 KPIs) | Compare KPI results with targets | KPIs calculated for the period; misses have actions | Y | BBM-STD-98 | ISO9001 | All
QA-IA-08 | 6 Planning | 6.3 Changes planned with effectiveness monitoring, communication and review (6.3 e)-g)) | Sample one QMS change | Change record has monitoring method, communication and review result | Y | BBM-STD-96 §6 | ISO9001, GACI | All
QA-IA-09 | 7 Support | 7.1 Resources, infrastructure (IT, CDE, software) and work environment adequate | Review capacity and IT incident log | No unresolved resource issue affecting delivery | N | BBM-STD-96 §7 | ISO9001 | All
QA-IA-10 | 7 Support | 7.1.6 Organisational knowledge kept and shared (standards, lessons, details library) | Check lessons log use and library updates | Lessons reused in at least one new project | Y | BBM-STD-96 §7 | ISO9001, FIDIC | All
QA-IA-11 | 7 Support | 7.2 Competence: required competence defined per role, training records, checker competence | Sample 3 staff files | Competence evidence matches role; training done | Y | BBM-STD-82 | ISO9001 | All
QA-IA-12 | 7 Support | 7.3 Awareness including quality culture and ethical behaviour (7.3 e)) | Interview staff | Staff aware of policy, objectives, their contribution and ethics | Y | BBM-STD-96 §7 | ISO9001, GACI | All
QA-IA-13 | 7 Support | 7.5 Documented information controlled (standards register, versions, archive) | Check BBM-STD-51 register against 04-DOCUMENTS | Current versions only in use; old versions archived | Y | BBM-STD-51 | ISO9001 | All
QA-IA-14 | 8 Operation | 8.2 Requirements and contract review done before every proposal | Sample 3 proposals: proposals checklist present | Checklist completed and signed | Y | BBM-STD-97 QP-01 | ISO9001 | All
QA-IA-15 | 8 Operation | 8.3 Design planning, inputs, controls (review, verification, validation), outputs and changes | Sample 2 projects: quality plan, design review checklists, change log | All present for each stage completed | Y | BBM-STD-97 QP-02, QP-03 | ISO9001 | All
QA-IA-16 | 8 Operation | 8.4 External providers (subconsultants) selected, controlled and evaluated | Sample 2 subconsultants | Evaluation and control evidence present | Y | BBM-STD-97 QP-15 | ISO9001 | All
QA-IA-17 | 8 Operation | 8.5 Service provision controlled: supervision, site records, client property | Sample one site | Supervision checklist and visit reports present | Y | BBM-STD-97 QP-09 | ISO9001 | All
QA-IA-18 | 8 Operation | 8.6 Release: issues released only after the required checks | Sample 3 issues | Each issue has checklist and approval before transmittal | Y | BBM-STD-97 QP-08 | ISO9001, BIMCL | All
QA-IA-19 | 8 Operation | 8.7 Nonconforming outputs identified and controlled | Check NC log | NCs recorded with disposition | Y | BBM-STD-97 QP-11 | ISO9001 | All
QA-IA-20 | 9 Evaluation | 9.1.2 Client satisfaction monitored | Check feedback records | Feedback rate and scores calculated | Y | BBM-STD-97 QP-12 | ISO9001, ISO10002 | All
QA-IA-21 | 9 Evaluation | 9.2 Internal audit programme done as planned, with objectives for each audit | Compare audit programme with reports | Every planned audit done; each has stated objectives | Y | BBM-STD-97 QP-13 | ISO9001, ISO19011 | All
QA-IA-22 | 9 Evaluation | 9.3 Management review held with all required inputs and outputs | Read the last review minutes | Minutes cover the inputs list (MR sheet) | Y | BBM-STD-97 QP-14 | ISO9001 | All
QA-IA-23 | 10 Improvement | 10.2 Corrective actions address root cause and are checked for effectiveness | Sample 3 CARs | Cause, action and effectiveness check recorded | Y | BBM-STD-97 QP-11 | ISO9001 | All
QA-IA-24 | 10 Improvement | 10.3 Continual improvement: improvements implemented from lessons and KPIs | Check improvement log | At least one improvement implemented per quarter | N | BBM-STD-96 §10 | ISO9001, FIDIC | All

## Management review
Management review
ISO 9001:2026 9.3 inputs and outputs (QP-14).
Audit / review ID |  | Scope (office / project code) |  | Period |  | Auditor |  | Auditee |  | Date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
QA-MR-01 | Inputs | Status of actions from previous management reviews | Read previous minutes | Every action closed or carried | Y | BBM-STD-97 QP-14 | ISO9001 | All
QA-MR-02 | Inputs | Changes in external and internal issues, and in interested parties needs (9.3.2 c)) | Context register update | Changes discussed | Y | BBM-STD-97 QP-14 | ISO9001, GACI | All
QA-MR-03 | Inputs | Client satisfaction and feedback | KPI K-CL-01/02 report | Discussed with trend | Y | BBM-STD-98 | ISO9001 | All
QA-MR-04 | Inputs | Quality objectives and KPI results | BBM-STD-98 KPI register | All KPIs reported against target | Y | BBM-STD-98 | ISO9001 | All
QA-MR-05 | Inputs | Process performance and conformity of services (design review results, authority rejections) | KPI report | Discussed | Y | BBM-STD-98 | ISO9001 | All
QA-MR-06 | Inputs | Nonconformities and corrective actions | NC/CAR log summary | Open NCs and overdue CARs listed | Y | BBM-STD-97 QP-11 | ISO9001 | All
QA-MR-07 | Inputs | Audit results (internal, client, certification) | Audit reports | Findings summarised | Y | BBM-STD-97 QP-13 | ISO9001 | All
QA-MR-08 | Inputs | Performance of subconsultants and suppliers | Evaluation summary | Poor performers actioned | Y | BBM-STD-97 QP-15 | ISO9001 | All
QA-MR-09 | Inputs | Adequacy of resources and effectiveness of risk and opportunity actions | Resource plan and risk register | Discussed | Y | BBM-STD-96 §6 | ISO9001 | All
QA-MR-10 | Inputs | Opportunities for improvement and lessons learned | Lessons log | Top lessons reviewed | Y | BBM-STD-97 QP-11 | ISO9001, FIDIC | All
QA-MR-11 | Outputs | Decisions on improvement, QMS changes and resource needs recorded with owners and dates | Read minutes | Each decision has owner and date | Y | BBM-STD-97 QP-14 | ISO9001 | All

## Client feedback
Client feedback
Feedback and complaints (QP-12).
Audit / review ID |  | Scope (office / project code) |  | Period |  | Auditor |  | Auditee |  | Date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
QA-CF-01 | Feedback | Client feedback requested at each stage end and at project completion | Check feedback register | Request sent for every stage completed | Y | BBM-STD-97 QP-12 | ISO10002, RIBA | All
QA-CF-02 | Feedback | Scores and comments analysed and shared with the project team | Check analysis record | Analysis within 10 working days of receipt | Y | BBM-STD-97 QP-12 | ISO10002 | All
QA-CF-03 | Complaints | Complaints logged, acknowledged and answered by a person not involved | Check complaints log | Acknowledged in 2 working days; answer by an independent senior | Y | BBM-STD-97 QP-12 | ISO10002 | All
QA-CF-04 | Complaints | Each complaint raised as an NC where a nonconformity is found | Cross-check complaints log with NC log | Linked NC for every justified complaint | Y | BBM-STD-97 QP-11 | ISO10002, ISO9001 | All

## NC and lessons
NC and lessons
Nonconformity, corrective action and lessons learned (QP-11).
Audit / review ID |  | Scope (office / project code) |  | Period |  | Auditor |  | Auditee |  | Date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
QA-NC-01 | NC | Office NCs recorded with source (review, audit, site, client, authority rejection), requirement and evidence | Check NC log | All fields filled; class NC-1/2/3 set | Y | BBM-STD-97 QP-11; BBM-STD-68 §5 | ISO9001 | All
QA-NC-02 | NC | Correction done and verified | Check correction evidence | Retest/re-review recorded | Y | BBM-STD-97 QP-11 | ISO9001 | All
QA-NC-03 | CAR | Root cause analysed (5 whys / fishbone) for recurring or NC-1 items | Read CAR | Cause supported by evidence | Y | BBM-STD-97 QP-11 | ISO9001, FIDIC | All
QA-NC-04 | CAR | Effectiveness checked after the agreed period | Check effectiveness record | No recurrence in the monitoring period | Y | BBM-STD-97 QP-11 | ISO9001 | All
QA-NC-05 | Lessons | Lessons learned logged at stage ends, project close and after significant NCs | Check lessons log | Lesson, cause, action and owner recorded | Y | BBM-STD-97 QP-11 | FIDIC, RIBA | All
QA-NC-06 | Lessons | Lessons turned into standard/checklist/template changes where systemic | Check change records linked to lessons | Systemic lessons have a change record | Y | BBM-STD-97 QP-11; BBM-STD-51 | ISO9001, FIDIC | All
QA-NC-07 | Lessons | Lessons reviewed at the start of new similar projects | Check project start record | Lessons review recorded in the quality plan | N | BBM-STD-97 QP-02 | RIBA, FIDIC | 0-1

## Project quality plan
Project quality plan
Audit of one project quality plan (QP-02).
Audit / review ID |  | Scope (office / project code) |  | Period |  | Auditor |  | Auditee |  | Date
ID | Section | Check | How to check (tool / manual) | Pass criterion | Mandatory | BBM-STD clause | Source standard | Stage (RIBA) | Result | Comment
QA-QP-01 | Plan | Project quality plan issued at mobilisation (scope, organisation, procedures applied, checks, records) | Read the PQP | PQP approved by the project director | Y | BBM-STD-97 QP-02 | ISO10005, RIBAQM | 1
QA-QP-02 | Plan | PQP links the BEP / BBM-STD-68 QMP for information quality instead of repeating it | Check PQP section on information | Link to BEP and QMP IDs/revisions | Y | BBM-STD-97 QP-02 | ISO10005, ISO19650 | 1
QA-QP-03 | Plan | Review and inspection schedule per stage set (which checklists, when, by whom) | Read the PQP schedule | Each stage lists checklists, tier and reviewer | Y | BBM-STD-97 QP-02 | ISO10005 | 1-6
QA-QP-04 | Plan | PQP updated at each stage gate and after significant change | Check PQP revision history | Revision at each gate | Y | BBM-STD-97 QP-02 | ISO10005 | All

## KPI register
KPI register (BBM-STD-98)
Office quality objectives (ISO 9001:2026 6.2). Enter the actual per period; status compares with the target. Targets marked "baseline" are set after the first year of data.
KPI | Area | Indicator | Formula | Target | Frequency | Data source | Owner | Period | Actual | Status / action
K-PR-01 | Proposals | Go/no-go done before bid | proposals with signed go/no-go / proposals submitted x 100 | 100% | Quarterly | Proposals checklist PR-GO-07 | Practice director
K-PR-02 | Proposals | Contract review done before signature | appointments with completed scope and contract review / appointments signed x 100 | 100% | Quarterly | Proposals checklist PR-CR | Practice director
K-PR-03 | Proposals | Bid success rate (quality-based bids) | awards / proposals decided x 100 | Baseline year 1, then +5 points | Quarterly | Bid register | Practice director
K-DR-01 | Design review | Issues reviewed before release | issues with design review checklist and no mandatory Fail / issues x 100 | 100% | Monthly | Design review checklist; transmittals | QA/QC lead
K-DR-02 | Design review | Review comments closed by next issue | comments closed or carried with owner / comments raised x 100 | >= 95% | Monthly | Comment sheets | Discipline leads
K-DR-03 | Coordination | Open S1 clashes at issue | count of open S1 clashes in issued zones | 0 | Per issue | BBM-STD-50 clash report | BIM coordinator
K-AU-01 | Authority | First-time authority approval rate | submissions approved or conditionally approved at first submission / submissions decided x 100 | >= 80% (baseline year 1) | Quarterly | BBM-STD-57 submission register | Authority liaison
K-AU-02 | Authority | Authority comment rounds per submission | resubmissions / submissions decided | <= 1.3 | Quarterly | BBM-STD-57 submission register | Authority liaison
K-SU-01 | Sustainability | Rating target met | projects certified at or above target level / projects certified x 100 | 100% statutory minimum; >= 90% of client targets | Yearly | Sustainability checklist | Sustainability lead / PQP
K-SP-01 | Specifications | Specification issues with no open placeholder | spec issues with zero TBC/TBA / spec issues x 100 | 100% | Per issue | Specification checklist SP-SC-07 | Specifier
K-SV-01 | Supervision | Site visit reports issued on time | reports issued within 2 working days / visits x 100 | >= 95% | Monthly | Visit report register | Resident / supervising engineer
K-SV-02 | Supervision | Submittals reviewed within the contract period | submittals returned on time / submittals received x 100 | >= 90% | Monthly | Submittal register | Supervising engineer
K-SV-03 | Supervision | RFIs answered within the agreed time | RFIs answered on time / RFIs received x 100 | >= 90% | Monthly | RFI register | Discipline leads
K-SV-04 | Supervision | Design-origin site NCRs | design-origin NCRs per 10,000 m2 GFA under construction | Baseline year 1, then -10% a year | Quarterly | NCR register; office NC log | QA/QC lead
K-DC-01 | Document control | Issues with complete transmittal | issues with transmittal matching files / issues x 100 | 100% | Monthly | Transmittal audit | Document controller
K-DC-02 | Document control | Naming compliance | files passing the naming check / files checked x 100 | 100% | Monthly | Naming check log | Information manager
K-NC-01 | Improvement | NC-1 closed within due date | NC-1 closed on time / NC-1 due x 100 | >= 90% | Monthly | NC log | QA/QC lead
K-NC-02 | Improvement | Corrective actions effective | CARs with no recurrence in monitoring period / CARs verified x 100 | >= 85% | Quarterly | CAR log | QA/QC lead
K-NC-03 | Improvement | Lessons logged per completed stage | stages with at least one lesson logged / stages completed x 100 | 100% | Quarterly | Lessons log | Project managers
K-CL-01 | Client | Client feedback response rate | feedback forms returned / forms sent x 100 | >= 60% | Quarterly | Feedback register | Practice director
K-CL-02 | Client | Client satisfaction score | mean overall score (1-5) | >= 4.0 | Quarterly | Feedback register | Practice director
K-CL-03 | Client | Complaints answered within 10 working days | complaints answered on time / complaints x 100 | 100% | Quarterly | Complaints log | Practice director
K-AD-01 | Audit | Internal audit programme completed | audits done / audits planned x 100 | 100% | Yearly | Audit programme | QMS owner
K-AD-02 | Audit | Management reviews held | reviews held / reviews planned (quarterly + material incident) | 4 per year minimum | Yearly | Review minutes | Practice director
K-CP-01 | Competence | Staff with role competence evidence and checker authorisation | staff with current competence record / staff x 100 | 100% | Yearly | Training records (BBM-STD-82) | BIM Manager / HR
K-PQ-01 | Planning | Projects with approved quality plan at mobilisation | projects with approved PQP within 4 weeks of appointment / new projects x 100 | 100% | Quarterly | PQP register | Project directors

## Sign-off
Sign-off
Results of every sheet, the status rule and the signatures for this check.
Sheet | Checks | Pass | Fail | NA | Not checked | Mandatory Fail
Internal audit
Management review
Client feedback
NC and lessons
Project quality plan
Total
Rule | Mark sheets that do not apply NA with a reason in Comment. Any mandatory Fail is a nonconformity (BBM-STD-97 QP-11): it holds the issue, submission or decision until corrected and re-checked. No count or score overrides it.
Status
Role | Name | Date | Decision / note
Prepared by
Checked by (independent of the work)
QA/QC lead
Approved by (discipline lead / project director)